## Tasks v2
Backend functions — v2
110 FR gốc + 27 task bổ sung v2. Không đổi status gốc một cách máy móc: đánh giá implementation và acceptance; API hiện có được kiểm tra từ source.
Task ID | Phase | Feature | Chức năng | Owner chức năng | Bảng liên quan (đúng v2) | Dependency | Ưu tiên | Status | Mức triển khai | API Swagger hiện có | Acceptance / nghiệp vụ | Đã code / bằng chứng | Còn phải làm | Schema / policy gap | Ghi chú giới hạn | Status file (3)
BE-FR-ACC-01-01 | W0 ¦ Tài khoản và quyền truy cập | ACC | Register và verify email service | BE1 – An | users, roles, user_roles | Contract theo module | High | In-progress | Một phần | POST /api/auth/register POST /api/auth/verify-email | Done: Đăng ký hợp lệ tạo một User; submit lặp không tạo account trùng; sửa payload role=ADMIN không cấp quyền. | Đã có register, CUSTOMER role cố định, email unique, verify handler. | Kiểm thử/sửa token iat theo giây so với users.updated_at có phần lẻ; xác minh link vừa phát không bị từ chối. Chưa có bằng chứng UAT email thật. |  |  | done
BE-FR-ACC-01-02 | W0 ¦ Tài khoản và quyền truy cập | ACC | Email verification/reset delivery adapter | BE1 – An | users | BE-FR-ACC-01-01 | High | In-progress | Một phần | POST /api/auth/resend-verification POST /api/auth/forgot-password | Done: Token replay không xác minh hai lần; provider failure giữ trạng thái chưa verified. | SMTP adapter và signed token; lỗi gửi không tự verify. | Chưa lưu delivery result/retry bền vững; chỉ log lỗi. Chốt phương án phù hợp yêu cầu không tạo token/outbox table. |  |  | done
BE-FR-ACC-02-01 | W0 ¦ Tài khoản và quyền truy cập | ACC | Authentication/session/logout và reset password service | BE1 – An | users, roles, user_roles, storefronts | BE-FR-ACC-01-01 | High | In-progress | Một phần | POST /api/auth/login POST /api/auth/logout GET /api/auth/me | Done: Account active đăng nhập được; banned bị chặn; reset token cũ không dùng lại; logout chặn thao tác cần đăng nhập. | Login active/status check, JWT, logout all sessions qua updated_at, profile/capabilities. | Kiểm tra phân biệt access JWT với email-purpose token; chuẩn hóa thời gian token/session và test auth boundary đầy đủ. |  |  | done
BE-FR-ACC-02-02 | W0 ¦ Tài khoản và quyền truy cập | ACC | Reset token và session revocation integration | BE1 – An | users | BE-FR-ACC-01-01, BE-FR-ACC-02-01 | High | In-progress | Một phần | POST /api/auth/forgot-password POST /api/auth/reset-password | Done: Không lộ email tồn tại; token đã dùng không reset; mật khẩu đổi thu hồi phiên cũ phù hợp. | Reset password, expiry/purpose/recipient checks và revoke sessions. | Kiểm thử token reset dùng ngay sau phát, expiry và replay dưới concurrency; iat/updated_at khác precision cần sửa trước Done. |  |  | done
BE-FR-ACC-03-01 | W0 ¦ Tài khoản và quyền truy cập | ACC | Profile/avatar own APIs và address snapshot independence | BE1 – An | users, user_bank_accounts, audit_logs | BE-FR-ACC-02-01 | High | Done | Đã triển khai | GET /api/auth/me PATCH /api/users/me POST /api/users/me/avatar | Done: User A không cập nhật profile B; avatar corrupt không lưu usable URL giả; profile update không thay snapshot order cũ. | Profile/date_of_birth, phone verification invalidation, avatar Cloudinary Avatar; kiểm tra ảnh hỏng/size; URL chỉ lưu sau upload thành công. |  |  | Done cho implementation đang có; Cloudinary credential/network và schema Supabase cần UAT. Không có Google Login chỉ vì đã map google_id. | done
BE-FR-ACC-03-02 | W0 ¦ Tài khoản và quyền truy cập | ACC | Address book own CRUD/default transaction | BE1 – An | users, user_addresses, physical_orders | BE-FR-ACC-02-01, BE-FR-ACC-03-01 | High | Done | Đã triển khai | GET /api/users/me/addresses POST /api/users/me/addresses PATCH /api/users/me/addresses/{id} DELETE /api/users/me/addresses/{id} POST /api/users/me/addresses/{id}/default | Done: User A không sửa địa chỉ B; đổi default không có hai defaults; sửa address không đổi order cũ. | Own address CRUD, province/district/ward; lock user và flush khi đổi default; order lấy snapshot riêng. |  |  | Xóa địa chỉ đã được FK sử dụng có thể bị DB từ chối; không sửa order snapshot để xóa cưỡng ép. | done
BE-FR-ACC-03-03 | W0 ¦ Tài khoản và quyền truy cập | ACC | Bank account masked own CRUD và verification invalidation | BE1 – An | users, user_bank_accounts, audit_logs | BE-FR-ACC-02-01, BE-FR-ACC-03-01 | High | In-progress | Một phần | GET /api/users/me/bank-accounts POST /api/users/me/bank-accounts PATCH /api/users/me/bank-accounts/{id} DELETE /api/users/me/bank-accounts/{id} POST /api/users/me/bank-accounts/{id}/default | Done: User khác không đọc bank data; không tự nhận verified từ client; account update không giữ verification sai. | Own CRUD, masked number, invalidate khi bank/phone thay đổi; audit JSONB. | Bổ sung policy validation account number/phone và provider tokenization (hiện hash sandbox không phải token ngân hàng có thể resolve). |  |  | done
BE-FR-ACC-03-04 | W0 ¦ Tài khoản và quyền truy cập | ACC | User bank verification evidence/read policy | BE1 – An | users, user_bank_accounts, audit_logs | BE-FR-ACC-02-01, BE-FR-ACC-03-01 | High | In-progress | Một phần | GET /api/users/me/bank-accounts PATCH /api/admin/bank-accounts/{id}/verification | Done: User A không đọc bank B; edit account quan trọng không giữ verified cũ. | Admin approve/reject, verifiedAt, own masked read và audit. | Reviewer evidence/reference, lý do bắt buộc ở service, guard inactive/self review theo policy và test quyền đầy đủ. |  |  | done
BE-FR-ACC-05-01 | W0 ¦ Tài khoản và quyền truy cập | ACC | Resource authorization và account capabilities | BE1 – An | users, roles, user_roles, storefronts | BE-FR-ACC-02-01 | High | In-progress | Một phần | GET /api/auth/me | Done: Gọi API trực tiếp bằng account không có quyền bị từ chối; ẩn nút FE không thay kiểm tra backend. | Capabilities theo account/role/storefront, @PreAuthorize và ownership tại các API hiện có. | Hoàn thiện permission theo action mới, role revocation/access token boundary, membership/assigned Designer khi module đó được triển khai. |  |  | done
BE-FR-PAY-01-01 | W0 ¦ Thanh toán và payment attempts | PAY | Payment obligation/source/stage và provider attempt adapter | BE1 – An | transactions, transaction_attempts | BE-FR-ACC-05-01 | High | In-progress | Một phần | POST /api/payments/zalopay | Done: Payment amount khớp order/quote; payload gán cả order và POD bị chặn. | ZaloPay create/query/signature, source amount resolver, attempt/provider fields v2, physical payment->PAID và late payment reconciliation có code. | Wallet method + snapshot/lock source đầy đủ; POD remaining gate, quote lifecycle; top-up chưa credit ledger; end-to-end provider tests. |  | Provider thật chưa được kiểm thử. Không đánh Done chỉ vì có callback route. | done
BE-FR-PAY-01-02 | W0 ¦ Thanh toán và payment attempts | PAY | Gateway adapter + mock payment scenarios | BE1 – An | transactions, transaction_attempts | BE-FR-ACC-05-01, BE-FR-PAY-01-01 | High | In-progress | Một phần | POST /api/payments/zalopay POST /api/payments/{transactionId}/refund | Done: Secret chỉ server; một Payment một source; mock không được UI trình bày như giao dịch thật. | ZaloPay create/query/signature, source amount resolver, attempt/provider fields v2, physical payment->PAID và late payment reconciliation có code. | Chưa có mock success/fail/late đầy đủ; refund endpoint hiện HTTP 409, chưa có refund obligation/execution; chốt provider contract. |  | Provider thật chưa được kiểm thử. Không đánh Done chỉ vì có callback route. | done
BE-FR-PAY-02-01 | W0 ¦ Thanh toán và payment attempts | PAY | Verified callback xử lý đúng một lần | BE1 – An | transactions, transaction_attempts | BE-FR-PAY-01-01 | High | In-progress | Một phần | POST /api/payments/zalopay/callback | Done: Callback success gửi ba lần chỉ một order confirm/ledger credit; refresh payment result không charge lại. | ZaloPay create/query/signature, source amount resolver, attempt/provider fields v2, physical payment->PAID và late payment reconciliation có code. | Đảm bảo duplicate nhiều attempt không double effect; UAT signed callback, provider/currency/reference và handler Wallet/POD/Rental/Subscription. |  | Provider thật chưa được kiểm thử. Không đánh Done chỉ vì có callback route. | done
BE-FR-PAY-02-02 | W0 ¦ Thanh toán và payment attempts | PAY | Out-of-order callback và unknown reconciliation worker | BE1 – An | transactions, transaction_attempts | BE-FR-PAY-01-01, BE-FR-PAY-02-01 | High | In-progress | Một phần | Worker nội bộ; không có endpoint riêng | Done: Replay success 10 lần một effect; success sau expiry vào exception; không downgrade succeeded bằng stale failure. | ZaloPay create/query/signature, source amount resolver, attempt/provider fields v2, physical payment->PAID và late payment reconciliation có code. | Worker hiện scan REQUESTED; chưa durable unknown event/worker theo từng attempt + bounded batches, retry/backoff, terminal/late cases và tests race. |  | Provider thật chưa được kiểm thử. Không đánh Done chỉ vì có callback route. | done
BE-FR-WAL-01-01 | W0 ¦ Wallet doanh thu commission và payout | WAL | Wallet ledger/read/topup verified credit | BE1 – An | wallets, wallet_ledgers, seller_earnings, transactions, transaction_attempts | BE-FR-PAY-02-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Topup callback lặp chỉ tăng một lần; User chỉ thấy ledger mình; pending không có action chi tiêu. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | in_process
BE-FR-WAL-01-02 | W0 ¦ Wallet doanh thu commission và payout | WAL | Top-up credit ledger exactly once | BE1 – An | wallets, wallet_ledgers, seller_earnings, transactions, transaction_attempts | BE-FR-PAY-02-01, BE-FR-WAL-01-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Callback lặp một credit; ledger sum khớp balance; không đụng AI credits. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-OPS-01-01 | W0 ¦ Notification dashboard cấu hình và audit | OPS | Versioned config/effective time và historical snapshots | BE1 – An | platform_configs, audit_logs, physical_orders, transactions | BE-FR-ACC-05-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Đổi refund window không dịch deadline order cũ; Seller không update commission bằng API. | Chưa tìm thấy implementation trong workspace. | platform_configs chỉ current value/updated_at; chưa có version/effective-time history để đáp ứng đầy đủ task. | platform_configs chỉ current value/updated_at; chưa có version/effective-time history để đáp ứng đầy đủ task. |  | Chưa bắt đầu
BE-FR-OPS-04-01 | W0 ¦ Notification dashboard cấu hình và audit | OPS | Sensitive audit/status history append và authorized query | BE1 – An | audit_logs, order_status_history, print_request_status_history | BE-FR-ACC-05-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Từ một settlement truy ra actor/reference/time; gọi delete audit bằng Seller bị từ chối. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-OPS-05-01 | W0 ¦ Notification dashboard cấu hình và audit | OPS | Admin internal roles/accounts và sanctions invariants | BE1 – An | users, roles, user_roles, audit_logs | BE-FR-ACC-05-01, BE-FR-OPS-04-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Ban seller chặn giao dịch mới; Staff vẫn xử lý case/order liên quan; Designer account không tự có Storefront. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-ACC-04-01 | W1 ¦ Tài khoản và quyền truy cập | ACC | Seller verification submit/review và eligibility | BE1 – An | users, user_bank_accounts, user_roles, storefronts, audit_logs | BE-FR-ACC-03-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: User chưa đủ email/phone/bank không activate Storefront; reject có lý do và resubmit được. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-STR-01-01 | W1 ¦ Storefront và subscription | STR | Create subscription và activation sau verified payment | BE1 – An | storefronts, storefront_subscriptions, users, transactions | BE-FR-ACC-04-01, BE-FR-PAY-01-01, BE-FR-PAY-02-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Payment success activate một lần; failed không có Seller capability; callback lặp không kéo dài hai tháng. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-STR-02-01 | W1 ¦ Storefront và subscription | STR | Manual renewal và storefront profile APIs | BE1 – An | storefronts, storefront_subscriptions, users, transactions | BE-FR-STR-01-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Renew sớm không mất ngày còn lại; renew sau expiry khôi phục capability theo trạng thái listing hợp lệ. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-STR-03-01 | W1 ¦ Storefront và subscription | STR | Expiry guard và bảo toàn existing orders | BE1 – An | storefronts, storefront_subscriptions, users, transactions | BE-FR-STR-01-01, BE-FR-ACC-05-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Expiry trong lúc buyer mở trang vẫn chặn checkout; seller vẫn cập nhật đơn trước expiry. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-STR-03-02 | W1 ¦ Storefront và subscription | STR | Storefront expiry scheduled notification | BE1 – An | storefronts, storefront_subscriptions, users, transactions | BE-FR-STR-01-01, BE-FR-ACC-05-01, BE-FR-STR-03-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Job chậm vẫn không checkout mới; existing orders/rentals không bị hủy. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-CAT-01-01 | W1 ¦ Landing Page và khám phá Marketplace | CAT | Public landing/catalog discovery API | BE1 – An | products, product_media, product_variants, storefronts | Contract theo module | High | Done | Đã triển khai | GET /api/catalog | Done: Guest lọc Physical được; Digital chưa triển khai có trạng thái rõ và không có nút mua giả; login giữ đường dẫn quay lại. | Public Physical catalog: PUBLISHED, storefront active/verified/chưa hết hạn, lọc trước paging. |  |  | Physical W1 scope. Digital catalog cần feature flag và schema hỗ trợ; chưa triển khai giao dịch số. | done
BE-FR-CAT-02-01 | W1 ¦ Landing Page và khám phá Marketplace | CAT | Catalog filter/search/sort/paging query | BE1 – An | products, product_media, product_variants, storefronts | BE-FR-CAT-01-01 | High | In-progress | Một phần | GET /api/catalog | Done: Hai lần truy vấn cùng filter có kết quả phân trang ổn định; reset filter bỏ toàn bộ điều kiện; không result không hiện lỗi server. | Keyword/category/page/size, nullable params cast đúng PostgreSQL, stable createdAt+id sort. | Chưa price min/max, loại sản phẩm và lựa chọn sort theo request; test filter edge cases. |  |  | done
BE-FR-CAT-04-01 | W1 ¦ Landing Page và khám phá Marketplace | CAT | Public storefront và listings query | BE1 – An | products, product_media, product_variants, storefronts | BE-FR-STR-03-01, BE-FR-CAT-02-01 | High | In-progress | Một phần | Chưa có API cho chức năng này | Done: Guest thấy gian hàng và sản phẩm hợp lệ; inactive hiển thị trạng thái, không đưa buyer vào checkout mới. |  | Chưa có public storefront profile/listings endpoint; không gán GET product detail cho task này. |  |  | done
BE-FR-SEL-01-01 | W1 ¦ Seller quản lý sản phẩm vật lý | SEL | Physical product/variant/media create transaction | BE1 – An | products, product_media, product_variants, storefronts, audit_logs | BE-FR-STR-01-01, BE-FR-ACC-05-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Draft hợp lệ lưu đủ variant; SKU trùng báo field error; seller B không gán sản phẩm vào Storefront A. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-SEL-03-01 | W1 ¦ Seller quản lý sản phẩm vật lý | SEL | Price và stock total/reserved/available invariants | BE1 – An | products, product_media, product_variants, storefronts, audit_logs | BE-FR-SEL-01-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Hai checkout tranh một sản phẩm chỉ một bên giữ được; Seller không giảm stock xuống dưới lượng đã giữ. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-SEL-04-01 | W1 ¦ Seller quản lý sản phẩm vật lý | SEL | Submit moderation/unpublish/archive listing | BE1 – An | products, product_media, product_variants, storefronts, audit_logs | BE-FR-SEL-01-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Reject có reason; unpublish khiến cart item unavailable; đơn đã tạo vẫn truy xuất được dữ liệu snapshot. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-MOD-01-01 | W1 ¦ Kiểm duyệt listing và Report | MOD | Hybrid moderation adapter và revision evidence | BE1 – An | products, reports, audit_logs, notifications | BE-FR-SEL-04-01, BE-FR-ACC-05-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Listing nghi vấn vào manual review; outage không làm mất draft; sửa ảnh sau check buộc kiểm tra revision mới. | Chưa tìm thấy implementation trong workspace. | products có moderation_reason/status nhưng chưa có moderation job/revision/provider evidence normalized. | products có moderation_reason/status nhưng chưa có moderation job/revision/provider evidence normalized. |  | Chưa bắt đầu
BE-FR-SEL-02-01 | W1 ¦ Seller quản lý sản phẩm vật lý | SEL | Listing update/revision và moderation invalidation | BE1 – An | products, product_media, product_variants, storefronts, audit_logs | BE-FR-SEL-01-01, BE-FR-MOD-01-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Sửa giá không đổi tiền đơn đã tạo; nội dung thay đổi không bỏ qua review; sửa resource khác seller bị chặn. | Chưa tìm thấy implementation trong workspace. | products chưa có revision/optimistic lock marker; chốt revision persistence trước async moderation. | products chưa có revision/optimistic lock marker; chốt revision persistence trước async moderation. |  | Chưa bắt đầu
BE-FR-MOD-01-02 | W1 ¦ Kiểm duyệt listing và Report | MOD | Moderation async scan/result correlation | BE1 – An | products, reports, audit_logs, notifications | BE-FR-SEL-04-01, BE-FR-ACC-05-01, BE-FR-MOD-01-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Old scan không approve revision mới; AI không xác minh copyright; demo/outage vẫn giữ draft. | Chưa tìm thấy implementation trong workspace. | Chưa có revision marker+scan correlation persistence; audit không thay hoàn toàn moderation jobs. | Chưa có revision marker+scan correlation persistence; audit không thay hoàn toàn moderation jobs. |  | Chưa bắt đầu
BE-FR-MOD-02-01 | W1 ¦ Kiểm duyệt listing và Report | MOD | Manual moderation decision transaction | BE1 – An | products, reports, audit_logs, notifications | BE-FR-MOD-01-01, BE-FR-OPS-04-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Staff thiếu permission không duyệt được; listing đã thay revision không được approve bằng màn hình cũ. | Chưa tìm thấy implementation trong workspace. | Cần revision concurrency guard/self-review policy; v2 chưa có moderation revision entity. | Cần revision concurrency guard/self-review policy; v2 chưa có moderation revision entity. |  | Chưa bắt đầu
BE-FR-MOD-03-01 | W1 ¦ Kiểm duyệt listing và Report | MOD | Report/evidence/investigation/sanction APIs | BE1 – An | products, reports, audit_logs, notifications | BE-FR-ACC-05-01, BE-FR-OPS-04-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Report trùng không gây sanction lặp; hide listing chặn mua mới nhưng giữ order/case history. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-LIB-01-01 | W1 ¦ Project thư viện model và file version | LIB | Project/model library CRUD và source ownership | BE2 – Khang | models_3d, model_versions, model_files | BE-FR-ACC-05-01 | High | In-progress | Một phần | GET /api/models/my GET /api/models/getId/{modelId} | Done: AI model và upload model xuất hiện cùng library, có origin; User khác không đọc model private. | Own list/detail và upload tạo model private. | Chưa đủ update/delete/visibility CRUD, quyền commercial/current owner theo schema và chặn tài nguyên đang được tham chiếu. |  |  | in_process
BE-FR-LIB-02-01 | W1 ¦ Project thư viện model và file version | LIB | File validation/storage/metadata và permission APIs | BE2 – Khang | models_3d, model_versions, model_files | BE-FR-LIB-01-01 | High | Done | Đã triển khai | POST /api/models/uploads GET /api/models/{modelId}/files/{fileId}/download | Done: Upload GLB hợp lệ tạo version/file; đổi đuôi file sai không pass validation; lỗi upload không tạo version usable giả. | Upload file validation/storage/hash/metadata/size + own authorized download; unit/controller tests có trong repo. |  |  | Local private storage; không đồng nhất Cloudinary avatar với storage file 3D. | done
BE-FR-LIB-02-02 | W1 ¦ Project thư viện model và file version | LIB | Secure object/file transfer and orphan cleanup | BE2 – Khang | models_3d, model_versions, model_files | BE-FR-LIB-01-01, BE-FR-LIB-02-01 | High | In-progress | Một phần | POST /api/models/uploads GET /api/models/{modelId}/files/{fileId}/download | Done: Extension giả không pass; failed metadata không model usable; private access rechecked. | Secure local path, authorized streaming, cleanup upload rollback và giữ file khi commit outcome unknown. | Chưa có durable orphan reconciliation scanner/retry khi cleanup thất bại; cập nhật fixtures PostgreSQL shared users theo v2. |  |  | done
BE-FR-LIB-03-01 | W1 ¦ Project thư viện model và file version | LIB | Immutable version/save/restore và reference guards | BE2 – Khang | models_3d, model_versions, model_files | BE-FR-LIB-02-01 | High | Done | Đã triển khai | GET /api/models/getId/{modelId}/versions GET /api/models/{modelId}/versions/{versionId} POST /api/models/{modelId}/versions/save POST /api/models/{modelId}/versions/{versionId}/restore | Done: Save sau quote không sửa file quote; restore v1 tạo v3 thay vì xóa v2. | Immutable new versions, head lock/stale-base conflict, restore thành version mới, history và safe metadata APIs. |  |  | Core own Model versions đã code/test; không bao gồm POD-specific file/spec version workflow. | in_process
BE-FR-VIW-01-01 | W1 ¦ Hiển thị và kiểm tra model 3D trên web | VIW | Preview metadata và authorized file access contract | BE2 – Khang | models_3d, model_versions, model_files | BE-FR-LIB-02-01, BE-FR-ACC-05-01 | High | In-progress | Một phần | GET /api/models/{modelId}/versions/{versionId} GET /api/models/{modelId}/files/{fileId}/download | Done: GLB và STL hỗ trợ hiển thị đúng; private file gọi bằng account khác bị chặn; file lỗi có retry/thông báo. | Authorized file metadata/download path. | Preview/viewable representation contract và entitlement cho renter/shared project chưa hoàn chỉnh. |  |  | in_process
BE-FR-CAT-03-01 | W1 ¦ Landing Page và khám phá Marketplace | CAT | Physical detail, variant availability và Buy Now eligibility | BE1 – An | products, product_media, product_variants, storefronts | BE-FR-CAT-02-01, BE-FR-VIW-01-01 | High | In-progress | Một phần | GET /api/catalog/{productId} | Done: Đổi variant cập nhật đúng giá; giá detail chỉ current price; product bị gỡ trong khi xem không checkout được. | Product summary/media/variant current price và stock/reserved/available. | Detail còn thiếu description/specifications/shipping/seller/reviews, buy-now eligibility per actor và hết hạn store trả lý do rõ. |  | Đây là product detail, không phải CAT-04-01 public storefront. | Chưa bắt đầu
BE-FR-VIW-01-02 | W1 ¦ Hiển thị và kiểm tra model 3D trên web | VIW | Preview representation và units/capabilities metadata | BE2 – Khang | models_3d, model_versions, model_files | BE-FR-LIB-02-01, BE-FR-ACC-05-01, BE-FR-VIW-01-01 | High | In-progress | Một phần | GET /api/models/getId/{modelId} GET /api/models/{modelId}/versions/{versionId} | Done: Public preview không lộ raw source URL; STL unknown unit ghi rõ; quyền revoked chặn access mới. | File format/hash/size và version metadata. | Units/dimensions/render capability/preview conversion chưa có đầy đủ. |  |  | in_process
BE-FR-AIG-03-01 | W1 ¦ AI tạo model 3D | AIG | Credit policy/read/admin grant và demo quota | BE2 – Khang | users, ai_requests, models_3d, model_versions, model_files, audit_logs | BE-FR-OPS-04-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Balance/cost không trộn Wallet; unauthorized user không grant; read/adapter demo làm độc lập với schema ledger thật; không claim credit phục hồi khi outcome còn unknown. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-AIG-03-02 | W1 ¦ AI tạo model 3D | AIG | Credit operation ledger reserve/consume/restore | BE2 – Khang | users, ai_requests, models_3d, model_versions, model_files, audit_logs | BE-FR-OPS-04-01, BE-FR-AIG-03-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Concurrent jobs không dùng quá balance; late callback không consume và restore cùng credit; operation replay không double refund. | Chưa tìm thấy implementation trong workspace. | Có balance và credits_used nhưng không có credit operation ledger/reservation idempotency; phải chốt persistence trước triển khai. | Có balance và credits_used nhưng không có credit operation ledger/reservation idempotency; phải chốt persistence trước triển khai. |  | Blocked
BE-FR-OPS-02-01 | W1 ¦ Notification dashboard cấu hình và audit | OPS | Business notification event/read/deep link permissions | BE2 – Khang | notifications | BE-FR-ACC-05-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Click quote notification mở đúng quote; User bị revoke project không đọc file từ notification cũ. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-OPS-02-02 | W1 ¦ Notification dashboard cấu hình và audit | OPS | Notification worker/deduplication và delivery log | BE2 – Khang | notifications | BE-FR-ACC-05-01, BE-FR-OPS-02-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Duplicate event không spam; notification không cấp resource rights; tài chính không gửi user khác. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-CRT-01-01 | W2 ¦ Giỏ hàng Marketplace | CRT | Cart item mutation và ownership validation | BE1 – An | carts, cart_items, products, product_variants, storefronts | BE-FR-CAT-03-01 | High | Done | Đã triển khai | GET /api/cart POST /api/cart/items PATCH /api/cart/items/{itemId} DELETE /api/cart/items/{itemId} | Done: Cùng variant thêm hai lần gộp quantity; khác variant tách item; rental/POD payload bị từ chối. | Cart 1/user, add merge variant, update/remove own item, lock user, check stock/self-buy; không reserve; lưu price_at_added. |  |  |  | done
BE-FR-CRT-02-01 | W2 ¦ Giỏ hàng Marketplace | CRT | Cart revalidation và changed/unavailable responses | BE1 – An | carts, cart_items, products, product_variants, storefronts | BE-FR-CRT-01-01, BE-FR-STR-03-01 | High | Done | Đã triển khai | GET /api/cart POST /api/cart/revalidate POST /api/cart/items/{itemId}/acknowledge-price | Done: Seller đổi giá thì Cart có old/new; Storefront hết hạn item còn trong Cart nhưng không checkout. | Current/previous price và priceChanged; storefront expiry/variant/stock revalidation; unavailable item giữ lại; checkout bắt acknowledge giá. |  |  | Cart total hiện tổng tất cả item available; FE quản lý selection, checkout revalidate selected IDs. | done
BE-FR-CHK-01-01 | W2 ¦ Checkout và giữ tồn kho | CHK | Checkout child order splitting và source separation | BE1 – An | carts, cart_items, products, product_variants, storefronts, user_addresses, physical_orders, physical_order_items, order_status_history | BE-FR-CRT-02-01, BE-FR-PAY-01-01 | High | Done | Đã triển khai | POST /api/orders/checkout | Done: Cart hai Seller tạo hai Physical orders; Buyer thấy đơn paid/pending riêng, không tưởng tất cả đã trả. | Physical checkout tách theo storefront; group UUID, per-order total/status; idempotency replay trả cùng orders. |  |  | Physical/Gateway implementation. Wallet/COD/Digital methods là phần mở rộng chưa Done. | done
BE-FR-CHK-02-01 | W2 ¦ Checkout và giữ tồn kho | CHK | Atomic stock reservation, consume và cancel release | BE1 – An | carts, cart_items, products, product_variants, storefronts, user_addresses, physical_orders, physical_order_items, order_status_history | BE-FR-CHK-01-01, BE-FR-SEL-03-01 | High | In-progress | Một phần | POST /api/orders/checkout PATCH /api/orders/{orderId}/status | Done: Hai người mua last unit chỉ một order reserve được; duplicate confirm trả cùng kết quả theo idempotency key. | Lock variants theo ID, reserve, processing consume một lần, persisted reservation state. | Chưa buyer cancel/review, restock sau consume và refund compensation; test concurrent last-unit thực sự chưa có trong suite v2 hiện tại. |  |  | done
BE-FR-CHK-02-02 | W2 ¦ Checkout và giữ tồn kho | CHK | Reservation expiry + late paid reconciliation job | BE1 – An | carts, cart_items, products, product_variants, storefronts, user_addresses, physical_orders, physical_order_items, order_status_history | BE-FR-CHK-01-01, BE-FR-SEL-03-01, BE-FR-CHK-02-01 | High | Done | Đã triển khai | Worker nội bộ; không có endpoint riêng | Done: Hai job không release twice; paid after timeout không oversell và không giả confirmed. | Expiry persisted mỗi order; worker lock/recheck, release repeat-safe; late paid đánh fulfillment RECONCILIATION_REQUIRED. |  |  | Không có REST riêng. Manual reconciliation/refund execution còn ở PAY/CAS, không tự hồi sinh order hết hạn. | done
BE-FR-CHK-03-01 | W2 ¦ Checkout và giữ tồn kho | CHK | Order/item money và policy snapshots | BE1 – An | carts, cart_items, products, product_variants, storefronts, user_addresses, physical_orders, physical_order_items, order_status_history | BE-FR-CHK-02-01 | High | In-progress | Một phần | POST /api/orders/checkout | Done: Sửa amount từ client không giảm tiền; đổi phí policy sau order không thay rate/window của order đó. | Decimal subtotal, SKU/title/variant/address snapshot; commission/refund/auto-confirm policy snapshot; fee flat từ cấu hình. | Chưa packaging/carrier shipping quote và subscription context snapshot; hoàn thiện breakdown theo v2 packaging. |  | Không đánh Done toàn task khi chỉ có snapshot giá/địa chỉ. V2-CHK-POLICY-01 ghi nhận phần đã xong. | done
BE-FR-ORD-01-01 | W2 ¦ Đơn hàng vật lý giao hàng và COD | ORD | Buyer/Seller order read và guarded fulfillment transitions | BE1 – An | physical_orders, physical_order_items, order_status_history, shipments, audit_logs | BE-FR-CHK-03-01, BE-FR-ACC-05-01 | High | In-progress | Một phần | GET /api/orders/mine GET /api/orders/seller PATCH /api/orders/{orderId}/status | Done: Seller cập nhật packed từ confirmed hợp lệ; gọi shipping trực tiếp từ cancelled bị chặn. | Own buyer/seller lists; PAID->PROCESSING có guard/consume; seller không tự PAID; append order history. | Chưa packed/handover contract, status filters/paging/detail timeline/payment/tracking và COD policy hoàn chỉnh. |  |  | Chưa bắt đầu
BE-FR-ORD-03-01 | W2 ¦ Đơn hàng vật lý giao hàng và COD | ORD | Shipment events và delivery/failed/return facts | BE1 – An | physical_orders, physical_order_items, order_status_history, shipments, audit_logs | BE-FR-ORD-01-01, BE-FR-OPS-04-01 | High | Done | Đã triển khai | POST /api/orders/{orderId}/shipment GET /api/orders/{orderId}/shipments GET /api/seller/orders/{orderId}/shipments PATCH /api/shipments/{shipmentId}/event | Done: Delivered chưa làm commission recognized; delivery failed COD uncollected có revenue/commission bằng 0. | Physical shipment PROCESSING+CONSUMED; shipped/delivered/failed/returned; owner check; audit actor/reference/time; không tự received/settlement. |  |  | POD dispatch vẫn BE-INT-03 / POD-06-01; chưa hỗ trợ create shipment POD ở route hiện tại. | done
BE-FR-ORD-03-02 | W2 ¦ Đơn hàng vật lý giao hàng và COD | ORD | Shipping provider/demo event adapter | BE1 – An | physical_orders, physical_order_items, order_status_history, shipments, audit_logs | BE-FR-ORD-01-01, BE-FR-OPS-04-01, BE-FR-ORD-03-01 | High | Done | Đã triển khai | POST /api/orders/{orderId}/shipment PATCH /api/shipments/{shipmentId}/event | Done: Duplicate delivery không tạo received/settlement; demo lưu actor/reference/time. | DemoShippingProvider, tracking DEMO; order lock, same-state event no-op, regression guard, history/audit. |  |  | Done demo adapter; không phải tích hợp carrier thật hoặc callback ký từ hãng vận chuyển. | done
BE-FR-PAY-03-01 | W2 ¦ Thanh toán và payment attempts | PAY | Wallet spend atomic và COD method guard | BE2 – Khang | transactions, transaction_attempts | BE-FR-PAY-01-01, BE-FR-WAL-01-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Hai payment đồng thời không tiêu vượt Available; chọn COD cho POD bị backend từ chối. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-WAL-02-01 | W2 ¦ Wallet doanh thu commission và payout | WAL | Seller earning Pending và commission snapshot | BE2 – Khang | wallets, wallet_ledgers, seller_earnings, transactions, transaction_attempts | BE-FR-PAY-02-01, BE-FR-CHK-03-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Payment Physical success thấy pending và release reason; COD collected chưa settled không thấy pending. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-LIB-04-01 | W2 ¦ Project thư viện model và file version | LIB | Project VIEW/EDIT grant/revoke authorization | BE2 – Khang | models_3d, model_versions, model_files | BE-FR-LIB-03-01, BE-FR-ACC-05-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Member bị revoke không mở private file bằng link cũ; hai saves cùng base được xử lý conflict. | Chưa tìm thấy implementation trong workspace. | 48 bảng chưa có project membership/access grants VIEW/EDIT; ownership users không thay thế membership. | 48 bảng chưa có project membership/access grants VIEW/EDIT; ownership users không thay thế membership. |  | Chưa bắt đầu
BE-FR-EDT-04-01 | W2 ¦ Editor 3D cơ bản trên web | EDT | Editor source access/import metadata contract | BE2 – Khang | models_3d, model_versions, model_files | BE-FR-LIB-02-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: GLB AI output mở, scale và đổi màu được; model thuê allow_edit=false bị chặn khi W5 triển khai. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-EDT-05-01 | W2 ¦ Editor 3D cơ bản trên web | EDT | Persist scene state + model files và new version transaction | BE2 – Khang | models_3d, model_versions, model_files | BE-FR-LIB-03-01 | High | In-progress | Một phần | POST /api/models/{modelId}/versions/save | Done: Save/reopen giữ vị trí object; STL đã bake scale; refresh sau save không tạo version trùng do retry. | Save source file thành version mới với stale-base check. | Persist editable scene state cùng file-role contract; không coi save SOURCE_MODEL là đã đủ Editor scene. |  |  | Chưa bắt đầu
BE-FR-EDT-05-02 | W2 ¦ Editor 3D cơ bản trên web | EDT | Editor export/version conflict contract | BE2 – Khang | models_3d, model_versions, model_files | BE-FR-LIB-03-01, BE-FR-EDT-05-01 | High | In-progress | Một phần | POST /api/models/{modelId}/versions/save | Done: Retry trả cùng version; exported file source refs ổn định; quote/print version không bị overwrite. | Stale base version conflict đã xử lý. | Export format/render pipeline và scene export contract chưa đủ. |  |  | Chưa bắt đầu
BE-FR-AIG-01-01 | W2 ¦ AI tạo model 3D | AIG | Text-to-3D request và async provider submit | BE2 – Khang | users, ai_requests, models_3d, model_versions, model_files, audit_logs | BE-FR-AIG-03-01, BE-FR-ACC-05-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Prompt hợp lệ tạo đúng một request; job chạy tiếp khi rời trang; thiếu credits không gọi provider. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-AIG-02-01 | W2 ¦ AI tạo model 3D | AIG | Image input validation/private storage và async submit | BE2 – Khang | users, ai_requests, models_3d, model_versions, model_files, audit_logs | BE-FR-AIG-01-01, BE-FR-AIG-03-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Ảnh hợp lệ tạo image request; upload fail không trừ credits; request B không đọc ảnh private A. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-AIG-04-01 | W2 ¦ AI tạo model 3D | AIG | Normalize result/status, ingest output và save Model idempotent | BE2 – Khang | users, ai_requests, models_3d, model_versions, model_files, audit_logs | BE-FR-AIG-01-01, BE-FR-LIB-02-01, BE-FR-VIW-01-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Refresh history còn trạng thái job; save hai lần không tạo hai MODEL3D từ cùng AI_RESULT; model có provenance AI. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-AIG-04-02 | W2 ¦ AI tạo model 3D | AIG | AI output ingest/storage + result-to-model transaction | BE2 – Khang | users, ai_requests, models_3d, model_versions, model_files, audit_logs | BE-FR-AIG-01-01, BE-FR-LIB-02-01, BE-FR-VIW-01-01, BE-FR-AIG-04-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Expired provider link không mất saved result; invalid output không succeeded; save cùng result không model duplicate. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-AIG-05-01 | W2 ¦ AI tạo model 3D | AIG | Generation history/regenerate lineage và fresh charge | BE2 – Khang | users, ai_requests, models_3d, model_versions, model_files, audit_logs | BE-FR-AIG-03-01, BE-FR-AIG-04-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Regenerate có cost mới; bản cũ đã save vẫn tồn tại; retry kỹ thuật của một job không tự charge mới. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-AIG-06-01 | W2 ¦ AI tạo model 3D | AIG | Provider adapter, timeout/unknown và demo scenarios | BE2 – Khang | users, ai_requests, models_3d, model_versions, model_files, audit_logs | BE-FR-AIG-04-01, BE-FR-PAY-02-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Mock output mở được Viewer/Editor; callback muộn không consume và restore cùng credit; provider outage giữ request history. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-AIG-06-02 | W2 ¦ AI tạo model 3D | AIG | AI polling/webhook/timeout reconciliation worker | BE2 – Khang | users, ai_requests, models_3d, model_versions, model_files, audit_logs | BE-FR-AIG-04-01, BE-FR-PAY-02-01, BE-FR-AIG-06-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Provider outage giữ history; callback muộn không double consume/restore; mock tạo GLB/STL render được. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-CAS-01-01 | W2 ¦ Refund Dispute và Review | CAS | Case eligibility/evidence và earning hold atomic | BE1 – An | refund_requests, refund_request_items, transactions, transaction_attempts, physical_orders, physical_order_items, seller_earnings, wallets, wallet_ledgers, audit_logs | BE-FR-ORD-03-01, BE-FR-WAL-02-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Case gửi trong hạn giữ earning; quá deadline không auto-approved và chuyển exceptional policy nếu có; User khác không mở case của đơn. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-CAS-02-01 | W2 ¦ Refund Dispute và Review | CAS | Case actions/refund execution và close-after-confirmation | BE1 – An | refund_requests, refund_request_items, transactions, transaction_attempts, physical_orders, physical_order_items, seller_earnings, wallets, wallet_ledgers, audit_logs | BE-FR-CAS-01-01, BE-FR-PAY-02-01, BE-FR-WAL-02-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Refund callback lặp không tăng Buyer Wallet hai lần; rejected case bỏ hold rồi đánh giá release lại; failed refund còn pending action. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-ORD-02-01 | W2 ¦ Đơn hàng vật lý giao hàng và COD | ORD | Cancel review, inventory reversal và refund initiation | BE1 – An | physical_orders, physical_order_items, order_status_history, shipments, audit_logs | BE-FR-ORD-01-01, BE-FR-CAS-02-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Cancel unpaid hoàn đúng stock; paid cancel còn refund pending đến khi refund success; repeat action không double refund. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-CAS-02-02 | W2 ¦ Refund Dispute và Review | CAS | Refund adapter và ledger/hold reconciliation | BE1 – An | refund_requests, refund_request_items, transactions, transaction_attempts, physical_orders, physical_order_items, seller_earnings, wallets, wallet_ledgers, audit_logs | BE-FR-CAS-01-01, BE-FR-PAY-02-01, BE-FR-WAL-02-01, BE-FR-CAS-02-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: COD refund Available đúng một lần; failed/unknown giữ case/refund pending; full pre-completion commission=0. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-ORD-04-01 | W3 ¦ Đơn hàng vật lý giao hàng và COD | ORD | Confirm received một lần và refund deadline | BE1 – An | physical_orders, physical_order_items, order_status_history, shipments, audit_logs | BE-FR-ORD-03-01, BE-FR-CAS-01-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Buyer confirm sớm làm deadline bắt đầu đúng received_at; job chạy lặp không dịch deadline. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-ORD-04-02 | W3 ¦ Đơn hàng vật lý giao hàng và COD | ORD | Auto-received scheduler và open-case race | BE1 – An | physical_orders, physical_order_items, order_status_history, shipments, audit_logs | BE-FR-ORD-03-01, BE-FR-CAS-01-01, BE-FR-ORD-04-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Timer/click lặp không kéo dài deadline; case hợp lệ giữ completion; trước delivered không auto receive. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-ORD-05-01 | W3 ¦ Đơn hàng vật lý giao hàng và COD | ORD | COD collection/settlement và earning reconciliation | BE1 – An | physical_orders, physical_order_items, order_status_history, shipments, audit_logs | BE-FR-ORD-03-01, BE-FR-WAL-02-01, BE-FR-PAY-03-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Delivered mà chưa settlement không Available; cùng settlement submit hai lần chỉ một ledger entry. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-ORD-05-02 | W3 ¦ Đơn hàng vật lý giao hàng và COD | ORD | COD settlement amount reconciliation | BE1 – An | physical_orders, physical_order_items, order_status_history, shipments, audit_logs | BE-FR-ORD-03-01, BE-FR-WAL-02-01, BE-FR-PAY-03-01, BE-FR-ORD-05-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Collected không credit; duplicate reference không tăng money; unsettled giữ Pending/earning state. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-PAY-04-01 | W3 ¦ Thanh toán và payment attempts | PAY | Attempt history/retry và reconciliation | BE2 – Khang | transactions, transaction_attempts | BE-FR-PAY-02-01, BE-FR-OPS-04-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Refresh giữ kết quả; payment unknown chỉ tạo tác động tiền sau verified success; manual override có audit. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-WAL-03-01 | W3 ¦ Wallet doanh thu commission và payout | WAL | Atomic financial finalization/commission/release | BE2 – Khang | wallets, wallet_ledgers, seller_earnings, transactions, transaction_attempts | BE-FR-ORD-04-01, BE-FR-ORD-05-01, BE-FR-CAS-02-01, BE-FR-WAL-02-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Job lặp không release lần hai; case mở hợp lệ ngay trước deadline giữ earning; completed amount khớp snapshot. | Chưa tìm thấy implementation trong workspace. | seller_earnings hiện chỉ physical_order_id NOT NULL UNIQUE; thu nhập Digital/Rental cần persistence riêng hoặc schema mở rộng. | seller_earnings hiện chỉ physical_order_id NOT NULL UNIQUE; thu nhập Digital/Rental cần persistence riêng hoặc schema mở rộng. |  | Chưa bắt đầu
BE-FR-WAL-03-02 | W3 ¦ Wallet doanh thu commission và payout | WAL | Financial deadline/release scheduler | BE2 – Khang | wallets, wallet_ledgers, seller_earnings, transactions, transaction_attempts | BE-FR-ORD-04-01, BE-FR-ORD-05-01, BE-FR-CAS-02-01, BE-FR-WAL-02-01, BE-FR-WAL-03-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: COD tới muộn không release sớm; case trước deadline thắng race; job replay một release. | Chưa tìm thấy implementation trong workspace. | Scheduler Digital/Rental earnings bị giới hạn seller_earnings physical-only; cần chốt revenue/settlement policy. | Scheduler Digital/Rental earnings bị giới hạn seller_earnings physical-only; cần chốt revenue/settlement policy. |  | Chưa bắt đầu
BE-FR-WAL-04-01 | W3 ¦ Wallet doanh thu commission và payout | WAL | Payout request và Available hold atomic | BE2 – Khang | wallets, wallet_ledgers, seller_earnings, transactions, transaction_attempts | BE-FR-WAL-01-01, BE-FR-ACC-03-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Available 500k, hold 300k thì chỉ 200k spendable; gửi payout thứ hai vượt 200k bị chặn. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-WAL-05-01 | W3 ¦ Wallet doanh thu commission và payout | WAL | Admin payout decision và verified transfer result | BE2 – Khang | wallets, wallet_ledgers, seller_earnings, transactions, transaction_attempts | BE-FR-WAL-04-01, BE-FR-OPS-04-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Approve không giảm tiền hai lần; failed trả spendable; repeated transfer success chỉ ghi một lần. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-WAL-05-02 | W3 ¦ Wallet doanh thu commission và payout | WAL | Payout transfer adapter/demo reconciliation | BE2 – Khang | wallets, wallet_ledgers, seller_earnings, transactions, transaction_attempts | BE-FR-WAL-04-01, BE-FR-OPS-04-01, BE-FR-WAL-05-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Approve không success; duplicate transfer callback một debit; spend không dùng tiền held. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-POD-01-01 | W3 ¦ Đặt in 3D theo yêu cầu | POD | Print request/source/version và compatible settings | BE2 – Khang | print_materials, print_requests, print_request_items, print_quotes, print_quote_items, print_request_file_versions, print_request_spec_versions, print_request_status_history, print_request_technical_reviews | BE-FR-LIB-03-01 | High | In-progress | Một phần | POST /api/print/requests/create GET /api/print/requests/getAll GET /api/print/requests/getId/{printRequestId} GET /api/print/requests/getId/{printRequestId}/file GET /api/print/materials/getAll GET /api/print/materials/getId/{materialId} POST /api/print/requests/getId/{printRequestId}/file/correct GET /api/print/requests/getId/{printRequestId}/file/versions GET /api/print/requests/getId/{printRequestId}/file/versions/{version}/download PATCH /api/print/requests/getId/{printRequestId}/specifications GET /api/print/requests/getId/{printRequestId}/specifications/versions | Done: Chọn resin không hiển thị FDM infill không phù hợp; source/version giữ nguyên khi submit. | Existing Draft flow now creates Spec V1 from persisted item values after File V1. Customer Draft spec update/history source implemented; scoped Model/Printing regression passed 278 tests, 0 failures, 8 skips. | Parent remains In-progress: Submit, State/Review/Quote/Payment/production gates and PostgreSQL v2 runtime verification remain. |  | POST create là multipart file + materialId + rightsDeclarationAccepted, không phải JSON spec API. | in_process
BE-FR-POD-02-01 | W3 ¦ Đặt in 3D theo yêu cầu | POD | Staff file review/correction/version transition | BE2 – Khang | print_materials, print_requests, print_request_items, print_quotes, print_quote_items, print_request_file_versions, print_request_spec_versions, print_request_status_history, print_request_technical_reviews | BE-FR-POD-01-01, BE-FR-VIW-01-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Yêu cầu sửa có note; upload v2 giữ v1; Staff quote chỉ từ version đang review hợp lệ. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-POD-03-01 | W3 ¦ Đặt in 3D theo yêu cầu | POD | Quote snapshot và material/labor/deposit/remaining validation | BE2 – Khang | print_materials, print_requests, print_request_items, print_quotes, print_quote_items, print_request_file_versions, print_request_spec_versions, print_request_status_history, print_request_technical_reviews | BE-FR-POD-02-01, BE-FR-OPS-01-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Quote total 1m, deposit 700k, remaining 300k hiển thị nhất quán; thay rate/material sau issue không đổi quote. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-POD-03-02 | W3 ¦ Đặt in 3D theo yêu cầu | POD | Quote validity and obsolete-version guard | BE2 – Khang | print_materials, print_requests, print_request_items, print_quotes, print_quote_items, print_request_file_versions, print_request_spec_versions, print_request_status_history, print_request_technical_reviews | BE-FR-POD-02-01, BE-FR-OPS-01-01, BE-FR-POD-03-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: 24h là quote validity default; late payment vào reconciliation; thay config không sửa quote đã issue. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-POD-04-01 | W3 ¦ Đặt in 3D theo yêu cầu | POD | Accepted quote/order/deposit + atomic production lock | BE2 – Khang | print_materials, print_requests, print_request_items, print_quotes, print_quote_items, print_request_file_versions, print_request_spec_versions, print_request_status_history, print_request_technical_reviews | BE-FR-POD-03-01, BE-FR-PAY-02-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Failed deposit không queued; callback lặp không tạo hai orders; sau queued Customer không đổi file/settings hay cancel đổi ý. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-POD-05-01 | W3 ¦ Đặt in 3D theo yêu cầu | POD | Production runs/post-processing/defect metadata APIs | BE2 – Khang | print_materials, print_requests, print_request_items, print_quotes, print_quote_items, print_request_file_versions, print_request_spec_versions, print_request_status_history, print_request_technical_reviews | BE-FR-POD-04-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Hai lần in lại lưu hai runs; model quote locked không đổi; complete production hiển thị yêu cầu remaining. | Chưa tìm thấy implementation trong workspace. | Có production_status từng item và status history; chưa có print_runs/defects/preview assets/workload normalized. | Có production_status từng item và status history; chưa có print_runs/defects/preview assets/workload normalized. |  | Chưa bắt đầu
BE-FR-POD-05-02 | W3 ¦ Đặt in 3D theo yêu cầu | POD | Workload/ETA theo print technology | BE2 – Khang | print_materials, print_requests, print_request_items, print_quotes, print_quote_items, print_request_file_versions, print_request_spec_versions, print_request_status_history, print_request_technical_reviews | BE-FR-POD-04-01, BE-FR-POD-05-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Không có dữ liệu thì ETA unavailable; estimate có timestamp/technology; không sửa locked quote khi workload đổi. | Chưa tìm thấy implementation trong workspace. | Chưa có schema workload/capacity/technology queues để tính ETA đáng tin cậy. | Chưa có schema workload/capacity/technology queues để tính ETA đáng tin cậy. |  | Chưa bắt đầu
BE-FR-POD-06-01 | W3 ¦ Đặt in 3D theo yêu cầu | POD | Remaining payment gate, shipment và service completion | BE2 – Khang | print_materials, print_requests, print_request_items, print_quotes, print_quote_items, print_request_file_versions, print_request_spec_versions, print_request_status_history, print_request_technical_reviews | BE-FR-POD-05-01, BE-FR-PAY-02-01, BE-FR-ORD-03-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Remaining unpaid gọi shipping API bị chặn; trả đủ mới handover; service revenue không credit Seller wallet. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-POD-07-01 | W3 ¦ Đặt in 3D theo yêu cầu | POD | Manufacturing defect/remedy/full refund policy service | BE2 – Khang | print_materials, print_requests, print_request_items, print_quotes, print_quote_items, print_request_file_versions, print_request_spec_versions, print_request_status_history, print_request_technical_reviews | BE-FR-POD-06-01, BE-FR-CAS-02-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Sai kích thước locked được review/reprint; đổi ý sau lock không tự hoàn deposit; full refund gồm deposit và remaining đã paid. | Chưa tìm thấy implementation trong workspace. | refund_requests hỗ trợ evidence/refund; repair/reprint/replacement/remedy lifecycle chưa có bảng chuyên biệt. | refund_requests hỗ trợ evidence/refund; repair/reprint/replacement/remedy lifecycle chưa có bảng chuyên biệt. |  | Chưa bắt đầu
BE-FR-POD-07-02 | W3 ¦ Đặt in 3D theo yêu cầu | POD | POD defect evidence + remediation transaction | BE2 – Khang | print_materials, print_requests, print_request_items, print_quotes, print_quote_items, print_request_file_versions, print_request_spec_versions, print_request_status_history, print_request_technical_reviews | BE-FR-POD-06-01, BE-FR-CAS-02-01, BE-FR-POD-07-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Wrong spec có remedy; change-of-mind đúng spec không defect refund; repeated action không refund hai lần. | Chưa tìm thấy implementation trong workspace. | Thiếu normalized remediation/run references; không nhét toàn bộ vào audit_logs. | Thiếu normalized remediation/run references; không nhét toàn bộ vào audit_logs. |  | Chưa bắt đầu
BE-FR-CAS-03-01 | W3 ¦ Refund Dispute và Review | CAS | Completed-transaction review eligibility và aggregate rating | BE1 – An | reviews, review_merchant_replies, products, physical_orders, physical_order_items, audit_logs | BE-FR-WAL-03-01, BE-FR-MOD-01-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Chưa mua không review; duplicate review bị chặn; sửa review cập nhật rating aggregate chính xác. | Chưa tìm thấy implementation trong workspace. | reviews v2 chỉ FK Physical order/item; review POD/Rental/Design cần mở rộng source contract. | reviews v2 chỉ FK Physical order/item; review POD/Rental/Design cần mở rộng source contract. |  | Chưa bắt đầu
BE-FR-OPS-03-01 | W3 ¦ Notification dashboard cấu hình và audit | OPS | Role-scoped operational/finance dashboard queries | BE2 – Khang | notifications, audit_logs, platform_configs, users, roles, user_roles | BE-FR-WAL-03-01, BE-FR-MOD-02-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: COD collected chưa settled không cộng available; POD revenue không là Seller commission; filters phản ánh đúng queue. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-DES-01-01 | W4 ¦ Dịch vụ thiết kế nội bộ | DES | Internal Design request/review/assignment authorization | BE2 – Khang | users, models_3d, model_versions, transactions | BE-FR-OPS-05-01, BE-FR-ACC-05-01 | Medium | In-progress | Chờ mở rộng schema | Chưa có API cho chức năng này | Done: Admin assignment hiện đúng designer workspace; Customer không tự set assigned_by hay role. | Chưa tìm thấy implementation trong workspace. | Schema 48 bảng chưa có design_requests/assignments/quotes/revisions/deliveries. Không thể đánh Done chỉ bằng users/models/transactions. | Schema 48 bảng chưa có design_requests/assignments/quotes/revisions/deliveries. Không thể đánh Done chỉ bằng users/models/transactions. |  | Chưa bắt đầu
BE-FR-DES-02-01 | W4 ¦ Dịch vụ thiết kế nội bộ | DES | Design quote acceptance/deposit và work gate | BE2 – Khang | users, models_3d, model_versions, transactions | BE-FR-DES-01-01, BE-FR-PAY-02-01 | Medium | In-progress | Chờ mở rộng schema | Chưa có API cho chức năng này | Done: Accept quote lặp không tạo hai orders; Designer chỉ bắt đầu khi deposit paid; failed không work_started. | Chưa tìm thấy implementation trong workspace. | Schema 48 bảng chưa có design_requests/assignments/quotes/revisions/deliveries. Không thể đánh Done chỉ bằng users/models/transactions. | Schema 48 bảng chưa có design_requests/assignments/quotes/revisions/deliveries. Không thể đánh Done chỉ bằng users/models/transactions. |  | Chưa bắt đầu
BE-FR-DES-03-01 | W4 ¦ Dịch vụ thiết kế nội bộ | DES | Preview/revision/allowance/approval + Additional Quote | BE2 – Khang | users, models_3d, model_versions, transactions | BE-FR-DES-02-01, BE-FR-LIB-03-01 | Medium | In-progress | Chờ mở rộng schema | Chưa có API cho chức năng này | Done: Revision count tăng đúng lần; vượt allowance không tự charge; final approval gắn delivery/version cụ thể. | Chưa tìm thấy implementation trong workspace. | Schema 48 bảng chưa có design_requests/assignments/quotes/revisions/deliveries. Không thể đánh Done chỉ bằng users/models/transactions. | Schema 48 bảng chưa có design_requests/assignments/quotes/revisions/deliveries. Không thể đánh Done chỉ bằng users/models/transactions. |  | Chưa bắt đầu
BE-FR-DES-03-02 | W4 ¦ Dịch vụ thiết kế nội bộ | DES | Additional Design Quote linkage guard | BE2 – Khang | users, models_3d, model_versions, transactions | BE-FR-DES-02-01, BE-FR-LIB-03-01, BE-FR-DES-03-01 | Medium | In-progress | Chờ mở rộng schema | Chưa có API cho chức năng này | Done: Unaccepted additional scope không bắt paid work; quote/payment một linkage rõ; original quote retained. | Chưa tìm thấy implementation trong workspace. | Schema 48 bảng chưa có design_requests/assignments/quotes/revisions/deliveries. Không thể đánh Done chỉ bằng users/models/transactions. | Schema 48 bảng chưa có design_requests/assignments/quotes/revisions/deliveries. Không thể đánh Done chỉ bằng users/models/transactions. |  | Blocked
BE-FR-DES-04-01 | W4 ¦ Dịch vụ thiết kế nội bộ | DES | Remaining paid final access + ownership handover transaction | BE2 – Khang | users, models_3d, model_versions, transactions | BE-FR-DES-03-01, BE-FR-PAY-02-01, BE-FR-LIB-03-01 | Medium | In-progress | Chờ mở rộng schema | Chưa có API cho chức năng này | Done: Thanh toán đủ mới tải final; retry grant/handover không chuyển owner hai lần; Customer thấy final trong Library. | Chưa tìm thấy implementation trong workspace. | Schema 48 bảng chưa có design_requests/assignments/quotes/revisions/deliveries. Không thể đánh Done chỉ bằng users/models/transactions. | Schema 48 bảng chưa có design_requests/assignments/quotes/revisions/deliveries. Không thể đánh Done chỉ bằng users/models/transactions. |  | Chưa bắt đầu
BE-FR-CHT-01-01 | W4 ¦ Chat theo ngữ cảnh | CHT | Context conversation participant/message APIs (Optional) | BE2 – Khang | notifications, users | BE-FR-ACC-05-01, BE-FR-DES-01-01, BE-FR-POD-01-01 | Medium | In-progress | Chờ mở rộng schema | Chưa có API cho chức năng này | Done: User không trong conversation gọi trực tiếp bị chặn; Support không cần FK POD/Design; gửi message lưu sender/time. | Chưa tìm thấy implementation trong workspace. | Optional: không có conversations/participants/messages; notifications.conversation_id không có FK và không phải hệ thống chat. | Optional: không có conversations/participants/messages; notifications.conversation_id không có FK và không phải hệ thống chat. |  | Optional
BE-FR-DIG-01-01 | W5 ¦ Digital Sale và chuyển current ownership | DIG | Current-owner listing và SALE/RENTAL active exclusion | BE2 – Khang | models_3d, model_versions, rental_offers, rental_contracts, transactions | BE-FR-SEL-04-01, BE-FR-MOD-01-01, BE-FR-LIB-03-01 | Low | In-progress | Chờ mở rộng schema | Chưa có API cho chức năng này | Done: Renter không publish asset; same asset mở offer SALE khi RENTAL active bị chặn. | Chưa tìm thấy implementation trong workspace. | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. |  | Chưa bắt đầu
BE-FR-DIG-02-01 | W5 ¦ Digital Sale và chuyển current ownership | DIG | Digital checkout reservation/concurrent payment protection | BE2 – Khang | models_3d, model_versions, rental_offers, rental_contracts, transactions | BE-FR-DIG-01-01, BE-FR-CHK-01-01, BE-FR-PAY-02-01 | Low | In-progress | Chờ mở rộng schema | Chưa có API cho chức năng này | Done: Hai buyers cùng asset chỉ một transfer thành công; Buyer thấy payment status riêng từng digital order. | Chưa tìm thấy implementation trong workspace. | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. |  | Blocked
BE-FR-DIG-02-02 | W5 ¦ Digital Sale và chuyển current ownership | DIG | Exclusive sale concurrency/reservation mechanism | BE2 – Khang | models_3d, model_versions, rental_offers, rental_contracts, transactions | BE-FR-DIG-01-01, BE-FR-CHK-01-01, BE-FR-PAY-02-01, BE-FR-DIG-02-01 | Low | In-progress | Chờ mở rộng schema | Chưa có API cho chức năng này | Done: Hai buyers không có hai transfers; paid loser có outcome/reconciliation rõ; no active rentals. | Chưa tìm thấy implementation trong workspace. | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. |  | Blocked
BE-FR-DIG-03-01 | W5 ¦ Digital Sale và chuyển current ownership | DIG | Ownership transfer + access grant exactly once | BE2 – Khang | models_3d, model_versions, rental_offers, rental_contracts, transactions | BE-FR-DIG-02-01, BE-FR-LIB-04-01 | Low | In-progress | Chờ mở rộng schema | Chưa có API cho chức năng này | Done: Seller cũ mất quyền commercialize và quyền project không còn hợp lệ; Buyer mới có access; callback lặp không có hai transfers. | Chưa tìm thấy implementation trong workspace. | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. |  | Blocked
BE-FR-DIG-03-02 | W5 ¦ Digital Sale và chuyển current ownership | DIG | Ownership entitlement retry/compensation worker | BE2 – Khang | models_3d, model_versions, rental_offers, rental_contracts, transactions | BE-FR-DIG-02-01, BE-FR-LIB-04-01, BE-FR-DIG-03-01 | Low | In-progress | Chờ mở rộng schema | Chưa có API cho chức năng này | Done: Payment mà access fail chưa completed; replay một transfer; không rewind lịch sử sau resale. | Chưa tìm thấy implementation trong workspace. | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. |  | Blocked
BE-FR-DIG-04-01 | W5 ¦ Digital Sale và chuyển current ownership | DIG | Provenance/resale eligibility và digital completion | BE2 – Khang | models_3d, model_versions, rental_offers, rental_contracts, transactions | BE-FR-DIG-03-01, BE-FR-WAL-03-01 | Low | In-progress | Chờ mở rộng schema | Chưa có API cho chức năng này | Done: Buyer đã nhận asset và có Storefront tạo resale được; Buyer chưa verification không publish; transfer pending giữ earning. | Chưa tìm thấy implementation trong workspace. | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. |  | Chưa bắt đầu
BE-FR-DIG-05-01 | W5 ¦ Digital Sale và chuyển current ownership | DIG | Exceptional digital case/ownership compensation guard | BE2 – Khang | models_3d, model_versions, rental_offers, rental_contracts, transactions | BE-FR-DIG-03-01, BE-FR-CAS-01-01 | Low | In-progress | Chờ mở rộng schema | Chưa có API cho chức năng này | Done: File inaccessible tạo case và giữ completion; change-of-mind không auto-refund; resale chain chưa có policy chặn auto reversal. | Chưa tìm thấy implementation trong workspace. | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. |  | Blocked
BE-FR-REN-01-01 | W5 ¦ Digital Rental và hết hạn quyền truy cập | REN | Rental payment/contract/entitlement activation | BE2 – Khang | rental_offers, rental_plans, rental_contracts, model_versions, transactions | BE-FR-DIG-01-01, BE-FR-PAY-02-01, BE-FR-ACC-05-01 | Low | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Payment failed không access; rental allow_edit=false không mở editable source; owner không đổi khi rent. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-FR-REN-02-01 | W5 ¦ Digital Rental và hết hạn quyền truy cập | REN | Access deadline guard và rental completion hold | BE2 – Khang | rental_offers, rental_plans, rental_contracts, model_versions, transactions | BE-FR-REN-01-01, BE-FR-WAL-03-01 | Low | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: URL tải mới sau expiry bị chặn dù job trễ; job lặp không release hai lần; model owner giữ nguyên. | Chưa tìm thấy implementation trong workspace. | Rental contract/expiry có bảng, entitlement granularity và income completion cần chốt; seller_earnings physical-only. | Rental contract/expiry có bảng, entitlement granularity và income completion cần chốt; seller_earnings physical-only. |  | Chưa bắt đầu
BE-FR-REN-02-02 | W5 ¦ Digital Rental và hết hạn quyền truy cập | REN | Rental expiry/release job và request-time access guard | BE2 – Khang | rental_offers, rental_plans, rental_contracts, model_versions, transactions | BE-FR-REN-01-01, BE-FR-WAL-03-01, BE-FR-REN-02-01 | Low | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Job chậm vẫn chặn URL mới; active case giữ earning; owner không đổi. | Chưa tìm thấy implementation trong workspace. | Rental contract/expiry có bảng, entitlement granularity và income completion cần chốt; seller_earnings physical-only. | Rental contract/expiry có bảng, entitlement granularity và income completion cần chốt; seller_earnings physical-only. |  | Chưa bắt đầu
BE-FR-REN-03-01 | W5 ¦ Digital Rental và hết hạn quyền truy cập | REN | Stop rental/current contracts và commercial mode transition | BE2 – Khang | rental_offers, rental_plans, rental_contracts, model_versions, transactions | BE-FR-REN-02-01, BE-FR-DIG-01-01 | Low | In-progress | Chưa có code | Chưa có API cho chức năng này | Done: Stop giữa kỳ không cắt access; thử chuyển SALE khi còn renter bị chặn; hết hợp đồng cuối mới chuyển được. | Chưa tìm thấy implementation trong workspace. | Chưa có API/service nghiệp vụ tương ứng; triển khai theo acceptance v2 và dependency. |  |  | Chưa bắt đầu
BE-V2-ACC-AVATAR-01 | W0 | ACC | Upload avatar Cloudinary + date of birth | BE1 – An | users | BE-FR-ACC-02-01 | High | Done | Đã triển khai | POST /api/users/me/avatar PATCH /api/users/me | Chỉ user hiện tại; PNG/JPEG hợp lệ; storage fail không thay URL; avatar_public_id dùng cleanup. | AvatarService/ImageValidator/CloudinaryStorage; tests ảnh; date_of_birth đã map/profile. |  |  |  | Task v2 mới
BE-V2-ACC-GOOGLE-01 | Future | ACC | Google identity sign-in (tùy chọn) | BE1 – An | users, roles, user_roles | BE-FR-ACC-02-01 | Low | In-progress | Chưa có code | Chưa có API cho chức năng này | Validate Google identity server-side, link theo verified identity không tin google_id client. | Chưa có implementation. | Validate Google identity server-side, link theo verified identity không tin google_id client. |  | Chỉ có google_id Entity. Optional, không ép mở scope nếu nhóm không chọn Google Login. | Task v2 mới
BE-V2-CRT-PRICE-01 | W2 | CRT | Snapshot và acknowledge giá cart | BE1 – An | cart_items, product_variants | BE-FR-CRT-01-01 | High | Done | Đã triển khai | POST /api/cart/items/{itemId}/acknowledge-price GET /api/cart POST /api/orders/checkout | Giá cũ/mới rõ; không silent charge; checkout chặn giá chưa được chấp nhận. | price_at_added/price_acknowledged_at, priceChanged và guard checkout; PG test có kiểm tra changed price. |  |  |  | Task v2 mới
BE-V2-CHK-IDEMP-01 | W2 | CHK | Checkout replay + fingerprint theo buyer/seller | BE1 – An | physical_orders, physical_order_items, carts, cart_items | BE-FR-CRT-02-01 | High | Done | Đã triển khai | POST /api/orders/checkout | Cùng key/payload trả cùng child orders; khác payload bị từ chối; UNIQUE buyer+key+storefront. | Lock user, fingerprint sorted cart IDs/address; PG replay test. |  |  |  | Task v2 mới
BE-V2-CHK-POLICY-01 | W2 | CHK | Snapshot địa chỉ và policy hiện có | BE1 – An | physical_orders, physical_order_items, user_addresses | BE-FR-CHK-01-01 | High | Done | Đã triển khai | POST /api/orders/checkout | Địa chỉ owned đọc từ DB; commission/refund/auto-confirm/expiry snapshot không đổi theo config mới. | Order initializeCheckout + JSON address và title/SKU/price; PG address independence test. |  |  | Flat fee từ config; chưa có packaging calculator hoặc platform_configs versioned. | Task v2 mới
BE-V2-CHK-RES-01 | W2 | CHK | Reservation expiry/state per order | BE1 – An | physical_orders, physical_order_items, product_variants | BE-FR-CHK-01-01 | High | Done | Đã triển khai | POST /api/orders/checkout PATCH /api/orders/{orderId}/status | Lock order trước release; repeated worker không release lại; processing consume một lần. | RESERVED/CONSUMED/RELEASED timestamps và worker; repeat release/consume PG tests. |  |  |  | Task v2 mới
BE-V2-ORD-HISTORY-01 | W2 | ORD | Append order history cho luồng đã code | BE1 – An | order_status_history, physical_orders | BE-FR-CHK-01-01 | High | Done | Đã triển khai | POST /api/orders/checkout GET /api/orders/mine GET /api/orders/seller PATCH /api/orders/{orderId}/status PATCH /api/shipments/{shipmentId}/event | Checkout/paid/processing/expired/shipping append actor/reason/time, không update history. | OrderStatusHistory Entity/Repository và các service hiện có. |  |  | Chưa có dedicated timeline API và chưa bao phủ cancellation chưa triển khai. | Task v2 mới
BE-V2-ORD-PAY-01 | W2 | PAY | Verified Physical payment -> PAID / late exception | BE1 – An | transactions, transaction_attempts, physical_orders, order_status_history | BE-FR-PAY-02-01 | High | Done | Đã triển khai | POST /api/payments/zalopay/callback | Valid reservation+amount thì PAID; expired/cancelled giữ reconciliation, không resurrect order. | OrderPaymentService; repeat verified payment + processing PG test. |  |  | Sub-feature Physical only; không đồng nghĩa toàn bộ callback/Wallet/POD/Rental đã Done. | Task v2 mới
BE-V2-AUDIT-JSON-01 | W0 | OPS | Audit JSONB compatibility | BE1 – An | audit_logs | BE-FR-ACC-05-01 | High | Done | Đã triển khai | Worker nội bộ; không có endpoint riêng | Metadata JSON hợp lệ được giữ, plain legacy text bọc detail; không log secrets. | JdbcTypeCode JSON + JsonValues normalizeMetadata; PG JSON insert test và unit tests cũ không đổi JSON formatting. |  |  |  | Task v2 mới
BE-V2-PKG-01 | W1 | SHP | Packaging profile administration | BE1 – An | packaging_profiles, audit_logs | BE-FR-ACC-05-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Validate dimensions/weight/cost/groups/fragile và active; profile code unique; audit thay đổi. | Chưa có implementation. | Validate dimensions/weight/cost/groups/fragile và active; profile code unique; audit thay đổi. |  |  | Task v2 mới
BE-V2-PKG-02 | W2 | SHP | Packing calculator và shipping quote | BE1 – An | packaging_profiles, products, product_variants | BE-V2-PKG-01, BE-FR-SEL-01-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Tính kiện theo size/weight/group/fragile; fee deterministic; không tin package cost FE; chốt chính sách carrier. | Chưa có implementation. | Tính kiện theo size/weight/group/fragile; fee deterministic; không tin package cost FE; chốt chính sách carrier. |  |  | Task v2 mới
BE-V2-PKG-03 | W2 | SHP | Persist order package/item snapshots | BE1 – An | order_shipping_packages, order_shipping_package_items, physical_orders, physical_order_items | BE-V2-PKG-02, BE-FR-CHK-01-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Package/item cùng order; tổng allocation=order quantity; profile bị sửa không đổi kiện đơn cũ. | Chưa có implementation. | Package/item cùng order; tổng allocation=order quantity; profile bị sửa không đổi kiện đơn cũ. |  |  | Task v2 mới
BE-V2-REV-01 | W3 | CAS | Physical review eligibility + aggregate | BE1 – An | reviews, products, physical_orders, physical_order_items | BE-FR-CAS-03-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Mỗi completed item một review; user=buyer; moderation status quyết định aggregate; không review self. | Chưa có implementation. | Mỗi completed item một review; user=buyer; moderation status quyết định aggregate; không review self. |  |  | Task v2 mới
BE-V2-REV-02 | W3 | CAS | Merchant reply và moderation review | BE1 – An | review_merchant_replies, reviews, products, storefronts, audit_logs | BE-V2-REV-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Một reply/review; đúng seller; content validate; audit edit/hide; không lộ hidden review. | Chưa có implementation. | Một reply/review; đúng seller; content validate; audit edit/hide; không lộ hidden review. |  |  | Task v2 mới
BE-V2-REF-01 | W3 | CAS | Refund request và item evidence | BE1 – An | refund_requests, refund_request_items, transactions, physical_order_items | BE-FR-CAS-01-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Validate actor/source/time/item qty/refundable amount; evidence JSON; request idempotency; chưa refund lúc submit. | Chưa có implementation. | Validate actor/source/time/item qty/refundable amount; evidence JSON; request idempotency; chưa refund lúc submit. |  |  | Task v2 mới
BE-V2-REF-02 | W3 | CAS | Refund review/return received decision | BE1 – An | refund_requests, refund_request_items, audit_logs | BE-V2-REF-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Reviewer có quyền, decision reason/reference/time; returned_received_at không có nghĩa refund settled. | Chưa có implementation. | Reviewer có quyền, decision reason/reference/time; returned_received_at không có nghĩa refund settled. |  |  | Task v2 mới
BE-V2-REF-03 | W3 | PAY | Approved refund execution + exactly-once settlement | BE1 – An | refund_requests, transactions, transaction_attempts, wallets, wallet_ledgers, seller_earnings | BE-V2-REF-02, BE-FR-PAY-02-01, BE-V2-WAL-HANDLER-01 | High | In-progress | Một phần | POST /api/payments/{transactionId}/refund | Persist REFUND obligation+provider reference; tổng refund<=paid; unknown còn processing; verified mới ledger/close. | Legacy refund route tồn tại nhưng chủ động trả HTTP 409, provider refund adapter còn code. | Chưa dùng được; implement approved request/locking/cumulative limit/retry ledger và query refund outcome. |  | Không mô tả endpoint này là refund đã hoạt động. | Task v2 mới
BE-V2-PAY-PERSIST-01 | W0 | PAY | Provider metadata v2 + durable reconciliation | BE1 – An | transactions, transaction_attempts | BE-FR-PAY-01-01 | High | In-progress | Một phần | POST /api/payments/zalopay POST /api/payments/zalopay/callback | Dedicated provider_transaction_id, URL/expiry/app/time/event; recover unknown và retry không tạo charge trùng. | Entity/provider metadata và REQUESTED query worker đã có. | Durable unknown event, per-attempt transactions/batch backoff, failure matrix và real sandbox UAT. |  |  | Task v2 mới
BE-V2-WAL-HANDLER-01 | W0 | WAL | Verified topup -> available ledger handler (BE2 owner) | BE2 – Khang | wallets, wallet_ledgers, seller_earnings, transactions | BE-FR-PAY-02-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Financial obligation lock và wallet lock; unique ledger idempotency; no credit fail/unknown; trả existing result. | Chưa có implementation. | Financial obligation lock và wallet lock; unique ledger idempotency; no credit fail/unknown; trả existing result. |  | BE1 sở hữu callback/payment; BE2 sở hữu mutation wallet/ledger. BE-FR-WAL-01-01 của BE1 phải gọi handler này qua service contract. | Task v2 mới
BE-V2-POD-MAT-01 | W1 | POD | Admin material catalog và compatible technology/unit | BE2 – Khang | print_materials, audit_logs | BE-FR-ACC-05-01 | High | Done | Đã triển khai | GET /api/print/materials/getAll GET /api/print/materials/getId/{materialId} GET /api/admin/print/materials/getAll POST /api/admin/print/materials/create PATCH /api/admin/print/materials/update/{materialId} PATCH /api/admin/print/materials/updateStatus/{materialId} | Admin create/cost/active, canonical identity duplicate guard, lock & audit; user read active only. | AdminPrintMaterialService + PrintMaterialService + controller/unit tests hiện có. |  |  |  | Task v2 mới
BE-V2-POD-FILE-01 | W3 | POD | POD file version records/current pointer | BE2 – Khang | print_request_file_versions, print_requests, model_versions, model_files | BE-FR-POD-01-01, BE-FR-LIB-02-01 | High | In-progress | Một phần | POST /api/print/requests/create GET /api/print/requests/getId/{printRequestId}/file POST /api/print/requests/getId/{printRequestId}/file/correct GET /api/print/requests/getId/{printRequestId}/file/versions GET /api/print/requests/getId/{printRequestId}/file/versions/{version}/download | Mỗi file mới tăng version/request dưới lock; owned source; immutable old versions; cleanup rollback; pointer cùng request. | V1 record + current pointer on Draft; Draft-only correction under request row lock; immutable history and authorized download routes. 272 Model/Printing tests passed; 7 skipped. | In-progress: verify deployed mapping/transactions on isolated PostgreSQL, concurrent correction and live HTTP/OpenAPI. Legacy Drafts with null pointer return 409 for correction until reviewed backfill. |  |  | Task v2 mới
BE-V2-POD-SPEC-01 | W3 | POD | POD specification versions/current pointer | BE2 – Khang | print_request_spec_versions, print_requests, print_request_items | BE-V2-POD-FILE-01 | High | In-progress | Một phần | PATCH /api/print/requests/getId/{printRequestId}/specifications GET /api/print/requests/getId/{printRequestId}/specifications/versions | Specification JSON object hợp lệ, material compatibility, version/request unique, immutable khi locked/deposit. | Spec V1 snapshot, Draft-only PATCH with owner row lock/expected version, material validation and immutable history implemented. Existing service/MVC tests passed; 278 scoped regression tests passed, 8 skipped. | In-progress: isolated PostgreSQL JSONB/UNIQUE/same-request FK and rollback not run; generated OpenAPI/live HTTP not verified. Legacy Drafts with NULL spec pointer need reviewed backfill. |  |  | Task v2 mới
BE-V2-POD-REVIEW-01 | W3 | POD | Technical review và handler assignment | BE2 – Khang | print_request_technical_reviews, print_requests, audit_logs | BE-FR-POD-02-01 | High | In-progress | Một phần | Chưa có API cho chức năng này | Staff/Admin có quyền; review_data object; handled_by/time; không thay đổi locked file/spec sau deposit. | Technical Review Entity/Repository foundation mapped from exported metadata; no review service or API. | Staff/Admin có quyền; review_data object; handled_by/time; không thay đổi locked file/spec sau deposit. |  |  | Task v2 mới
BE-V2-POD-STATE-01 | W3 | POD | POD submit/cancel/history và confirmation flags | BE2 – Khang | print_requests, print_request_status_history | BE-V2-POD-FILE-01, BE-V2-POD-SPEC-01 | High | In-progress | Một phần | Chưa có API cho chức năng này | Submit cần rights+preview/spec; actor/reason/events; cancel trước lock theo policy; histories append-only. | Status History Entity/Repository foundation mapped from exported metadata; no submit/cancel/history workflow or API. | Service/DTO/controller workflow chưa dùng những field này; quyền và transition cần triển khai. |  |  | Task v2 mới
BE-V2-POD-QUOTE-01 | W3 | POD | Quote current pointer + immutable file/spec snapshot | BE2 – Khang | print_quotes, print_quote_items, print_requests, print_request_file_versions, print_request_spec_versions | BE-V2-POD-REVIEW-01, BE-FR-OPS-01-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Quote snapshot đúng request/version; old quote không accept sau spec/file đổi; total=deposit+remaining; expiry explicit. | Chưa có implementation. | Quote snapshot đúng request/version; old quote không accept sau spec/file đổi; total=deposit+remaining; expiry explicit. |  |  | Task v2 mới
BE-V2-POD-TEST-01 | W0 | POD | Update v2 entity mapping tests và PostgreSQL fixtures | BE2 – Khang | print_requests, users | BE-DB-24 | High | In-progress | Một phần | Chưa có API cho chức năng này | PrintRequestMappingTest biết 20 field và JSONB; old PG fixtures/shared users cập nhật schema; regression tests giữ nguyên nghiệp vụ. | Spec V1/V2 and route tests added to existing classes; scoped Model/Printing suite 278 run, 0 failed, 8 skipped. Focused Spec V1 rollback test passed 3/3. | In-progress: deployed metadata confirms schema; isolated PostgreSQL v2 runtime mapping/JSONB/FK tests remain pending. |  |  | Task v2 mới
BE-V2-NOTIF-01 | W3 | OPS | Notification dedupe/expiry/source event | BE2 – Khang | notifications | BE-FR-OPS-02-01 | High | In-progress | Chưa có code | Chưa có API cho chức năng này | Dedupe theo recipient+key; idempotent worker; scoped read/readAt; expire không leak deep link; conversation_id chưa có chat. | Chưa có implementation. | Dedupe theo recipient+key; idempotent worker; scoped read/readAt; expire không leak deep link; conversation_id chưa có chat. |  |  | Task v2 mới

## API Swagger
Swagger API inventory — code hiện tại
Chỉ liệt kê endpoint có Controller mapping. Các task worker/handler không có endpoint riêng. Đây là source inventory, không phải xác nhận server/Supabase/provider đang chạy thành công.
HTTP | Path | Controller | Feature owner | BE-FR / BE-V2 tasks | Summary | Authentication/authorization | Input type | Giới hạn/contract hiện tại | Source
POST | /api/auth/register | AuthController | BE1 – An | BE-FR-ACC-01-01 | Register a customer account | Public / Guest | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/auth/controller/AuthController.java
POST | /api/auth/login | AuthController | BE1 – An | BE-FR-ACC-02-01 | Login and receive a JWT access token | Public / Guest | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/auth/controller/AuthController.java
POST | /api/auth/logout | AuthController | BE1 – An | BE-FR-ACC-02-01 | Logout and revoke the current JWT session | isAuthenticated() | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/auth/controller/AuthController.java
GET | /api/auth/me | AuthController | BE1 – An | BE-FR-ACC-02-01 BE-FR-ACC-03-01 BE-FR-ACC-05-01 | Get the current account | isAuthenticated() | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/auth/controller/AuthController.java
POST | /api/auth/verify-email | EmailAuthController | BE1 – An | BE-FR-ACC-01-01 | Verify email using the one-time token from the email link | Public / Guest | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/auth/controller/EmailAuthController.java
POST | /api/auth/resend-verification | EmailAuthController | BE1 – An | BE-FR-ACC-01-02 | Request a new verification link; the old token becomes invalid | Public / Guest | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/auth/controller/EmailAuthController.java
POST | /api/auth/forgot-password | EmailAuthController | BE1 – An | BE-FR-ACC-01-02 BE-FR-ACC-02-02 | Request a password reset link without exposing account existence | Public / Guest | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/auth/controller/EmailAuthController.java
POST | /api/auth/reset-password | EmailAuthController | BE1 – An | BE-FR-ACC-02-02 | Set a new password using the one-time reset token | Public / Guest | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/auth/controller/EmailAuthController.java
GET | /api/cart | CartController | BE1 – An | BE-FR-CRT-01-01 BE-FR-CRT-02-01 BE-V2-CRT-PRICE-01 | Get cart | isAuthenticated() | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/cart/controller/CartController.java
POST | /api/cart/items | CartController | BE1 – An | BE-FR-CRT-01-01 | Add cart item | isAuthenticated() | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/cart/controller/CartController.java
PATCH | /api/cart/items/{itemId} | CartController | BE1 – An | BE-FR-CRT-01-01 | Update cart quantity | isAuthenticated() | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/cart/controller/CartController.java
DELETE | /api/cart/items/{itemId} | CartController | BE1 – An | BE-FR-CRT-01-01 | Remove cart item | isAuthenticated() | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/cart/controller/CartController.java
POST | /api/cart/revalidate | CartController | BE1 – An | BE-FR-CRT-02-01 | Revalidate cart | isAuthenticated() | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/cart/controller/CartController.java
POST | /api/cart/items/{itemId}/acknowledge-price | CartController | BE1 – An | BE-FR-CRT-02-01 BE-V2-CRT-PRICE-01 | Accept current item price | isAuthenticated() | JSON | Chấp nhận current price; không reserve stock; caller phải owner cart item. | src/main/java/com/project/w_3d_world/features/cart/controller/CartController.java
GET | /api/catalog | CatalogController | BE1 – An | BE-FR-CAT-01-01 BE-FR-CAT-02-01 | Search public catalog | Public / Guest | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/catalog/controller/CatalogController.java
GET | /api/catalog/{productId} | CatalogController | BE1 – An | BE-FR-CAT-03-01 | Get product detail | Public / Guest | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/catalog/controller/CatalogController.java
GET | /api/models/{modelId}/files/{fileId}/download | ModelDownloadController | BE2 – Khang | BE-FR-LIB-02-01 BE-FR-LIB-02-02 BE-FR-VIW-01-01 | Download an authorized model file | Authenticated + service ownership | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/model/controller/ModelDownloadController.java
GET | /api/models/my | ModelLibraryController | BE2 – Khang | BE-FR-LIB-01-01 | Retrieve the authenticated user's model library | Authenticated + service ownership | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/model/controller/ModelLibraryController.java
GET | /api/models/getId/{modelId} | ModelLibraryController | BE2 – Khang | BE-FR-LIB-01-01 BE-FR-VIW-01-02 | Retrieve one owned model and its latest version | Authenticated + service ownership | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/model/controller/ModelLibraryController.java
POST | /api/models/uploads | ModelUploadController | BE2 – Khang | BE-FR-LIB-02-01 BE-FR-LIB-02-02 | Upload a new private model | Authenticated + service ownership | multipart/form-data | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/model/controller/ModelUploadController.java
GET | /api/models/getId/{modelId}/versions | ModelVersionHistoryController | BE2 – Khang | BE-FR-LIB-03-01 | Retrieve the version history of an owned model | Authenticated + service ownership | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/model/controller/ModelVersionHistoryController.java
GET | /api/models/{modelId}/versions/{versionId} | ModelVersionHistoryController | BE2 – Khang | BE-FR-LIB-03-01 BE-FR-VIW-01-01 BE-FR-VIW-01-02 | Retrieve version details and safe file metadata | Authenticated + service ownership | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/model/controller/ModelVersionHistoryController.java
POST | /api/models/{modelId}/versions/{versionId}/restore | ModelVersionRestoreController | BE2 – Khang | BE-FR-LIB-03-01 | Restore an earlier version as a new version of an owned model | Authenticated + service ownership | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/model/controller/ModelVersionRestoreController.java
POST | /api/models/{modelId}/versions/save | ModelVersionSaveController | BE2 – Khang | BE-FR-LIB-03-01 BE-FR-EDT-05-01 BE-FR-EDT-05-02 | Save a new version of an owned model | Authenticated + service ownership | multipart/form-data | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/model/controller/ModelVersionSaveController.java
POST | /api/orders/checkout | OrderController | BE1 – An | BE-FR-CHK-01-01 BE-FR-CHK-02-01 BE-FR-CHK-03-01 BE-V2-CRT-PRICE-01 BE-V2-CHK-IDEMP-01 BE-V2-CHK-POLICY-01 BE-V2-CHK-RES-01 BE-V2-ORD-HISTORY-01 | Checkout selected cart items | isAuthenticated() | JSON | cartItemIds + shippingAddressId + idempotencyKey; client address snapshot bị bỏ qua; price cần acknowledge. | src/main/java/com/project/w_3d_world/features/order/controller/OrderController.java
GET | /api/orders/mine | OrderController | BE1 – An | BE-FR-ORD-01-01 BE-V2-ORD-HISTORY-01 | List buyer orders | isAuthenticated() | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/order/controller/OrderController.java
GET | /api/orders/seller | OrderController | BE1 – An | BE-FR-ORD-01-01 BE-V2-ORD-HISTORY-01 | List seller orders | isAuthenticated() | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/order/controller/OrderController.java
PATCH | /api/orders/{orderId}/status | OrderController | BE1 – An | BE-FR-CHK-02-01 BE-FR-ORD-01-01 BE-V2-CHK-RES-01 BE-V2-ORD-HISTORY-01 | Update order status | isAuthenticated() | JSON | Seller chỉ PAID -> PROCESSING; consume reserved stock. Không cho client set PAID/DELIVERED. | src/main/java/com/project/w_3d_world/features/order/controller/OrderController.java
POST | /api/payments/zalopay | PaymentController | BE1 – An | BE-FR-PAY-01-01 BE-FR-PAY-01-02 BE-V2-PAY-PERSIST-01 | Create a ZaloPay payment | isAuthenticated() | JSON | Topup yêu cầu idempotencyKey; payment success chưa đồng nghĩa Wallet credit/POD production/Rental access. | src/main/java/com/project/w_3d_world/features/payment/controller/PaymentController.java
POST | /api/payments/{transactionId}/refund | PaymentController | BE1 – An | BE-FR-PAY-01-02 BE-V2-REF-03 | Request a ZaloPay refund | isAuthenticated() | JSON | Route có nhưng HTTP 409; KHÔNG có refund execution hoạt động. | src/main/java/com/project/w_3d_world/features/payment/controller/PaymentController.java
POST | /api/payments/zalopay/callback | PaymentController | BE1 – An | BE-FR-PAY-02-01 BE-V2-ORD-PAY-01 BE-V2-PAY-PERSIST-01 | Receive ZaloPay callback | Provider callback: HMAC KEY2, no login | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/payment/controller/PaymentController.java
GET | /api/admin/print/materials/getAll | AdminPrintMaterialController | BE2 – Khang | BE-V2-POD-MAT-01 | List all print materials for administrators | hasRole('ADMIN') | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/printing/controller/AdminPrintMaterialController.java
POST | /api/admin/print/materials/create | AdminPrintMaterialController | BE2 – Khang | BE-V2-POD-MAT-01 | Create a print material | hasRole('ADMIN') | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/printing/controller/AdminPrintMaterialController.java
PATCH | /api/admin/print/materials/update/{materialId} | AdminPrintMaterialController | BE2 – Khang | BE-V2-POD-MAT-01 | Update a material's estimated cost | hasRole('ADMIN') | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/printing/controller/AdminPrintMaterialController.java
PATCH | /api/admin/print/materials/updateStatus/{materialId} | AdminPrintMaterialController | BE2 – Khang | BE-V2-POD-MAT-01 | Activate or deactivate a print material | hasRole('ADMIN') | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/printing/controller/AdminPrintMaterialController.java
GET | /api/print/materials/getAll | PrintMaterialController | BE2 – Khang | BE-FR-POD-01-01 BE-V2-POD-MAT-01 | list | Authenticated + service ownership | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/printing/controller/PrintMaterialController.java
GET | /api/print/materials/getId/{materialId} | PrintMaterialController | BE2 – Khang | BE-FR-POD-01-01 BE-V2-POD-MAT-01 | detail | Authenticated + service ownership | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/printing/controller/PrintMaterialController.java
POST | /api/print/requests/create | PrintRequestController | BE2 – Khang | BE-FR-POD-01-01 BE-V2-POD-FILE-01 | create | hasRole('CUSTOMER') | multipart/form-data | Multipart file + materialId + rightsDeclarationAccepted; tạo DRAFT qua private Model storage; chưa v2 file/spec versions. | src/main/java/com/project/w_3d_world/features/printing/controller/PrintRequestController.java
GET | /api/print/requests/getAll | PrintRequestController | BE2 – Khang | BE-FR-POD-01-01 | getAll | hasRole('CUSTOMER') | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/printing/controller/PrintRequestController.java
GET | /api/print/requests/getId/{printRequestId} | PrintRequestController | BE2 – Khang | BE-FR-POD-01-01 | getById | hasRole('CUSTOMER') | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/printing/controller/PrintRequestController.java
GET | /api/print/requests/getId/{printRequestId}/file | PrintRequestController | BE2 – Khang | BE-FR-POD-01-01 BE-V2-POD-FILE-01 | downloadFile | hasRole('CUSTOMER') | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/printing/controller/PrintRequestController.java
POST | /api/orders/{orderId}/shipment | ShipmentController | BE1 – An | BE-FR-ORD-03-01 BE-FR-ORD-03-02 | Create shipment | isAuthenticated() | JSON | Chỉ Physical order PROCESSING + CONSUMED. Đây là demo shipment, chưa dispatch POD. | src/main/java/com/project/w_3d_world/features/shipping/controller/ShipmentController.java
GET | /api/orders/{orderId}/shipments | ShipmentController | BE1 – An | BE-FR-ORD-03-01 | Track order shipments | isAuthenticated() | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/shipping/controller/ShipmentController.java
GET | /api/seller/orders/{orderId}/shipments | ShipmentController | BE1 – An | BE-FR-ORD-03-01 | List seller shipment events | isAuthenticated() | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/shipping/controller/ShipmentController.java
PATCH | /api/shipments/{shipmentId}/event | ShipmentController | BE1 – An | BE-FR-ORD-03-01 BE-FR-ORD-03-02 BE-V2-ORD-HISTORY-01 | Apply shipment event | isAuthenticated() | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/shipping/controller/ShipmentController.java
PATCH | /api/admin/bank-accounts/{id}/verification | BankReviewController | BE1 – An | BE-FR-ACC-03-04 | Review bank account | hasRole('ADMIN') | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/user/controller/BankReviewController.java
POST | /api/users/me/avatar | UserProfileController | BE1 – An | BE-FR-ACC-03-01 BE-V2-ACC-AVATAR-01 | Upload avatar | isAuthenticated() | multipart/form-data | Multipart file JPEG/PNG <=5MB; Cloudinary folder Avatar; không dùng cho file model/POD. | src/main/java/com/project/w_3d_world/features/user/controller/UserProfileController.java
PATCH | /api/users/me | UserProfileController | BE1 – An | BE-FR-ACC-03-01 BE-V2-ACC-AVATAR-01 | Update profile | isAuthenticated() | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/user/controller/UserProfileController.java
GET | /api/users/me/addresses | UserProfileController | BE1 – An | BE-FR-ACC-03-02 | List addresses | isAuthenticated() | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/user/controller/UserProfileController.java
POST | /api/users/me/addresses | UserProfileController | BE1 – An | BE-FR-ACC-03-02 | Add address | isAuthenticated() | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/user/controller/UserProfileController.java
PATCH | /api/users/me/addresses/{id} | UserProfileController | BE1 – An | BE-FR-ACC-03-02 | Update address | isAuthenticated() | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/user/controller/UserProfileController.java
DELETE | /api/users/me/addresses/{id} | UserProfileController | BE1 – An | BE-FR-ACC-03-02 | Delete address | isAuthenticated() | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/user/controller/UserProfileController.java
POST | /api/users/me/addresses/{id}/default | UserProfileController | BE1 – An | BE-FR-ACC-03-02 | Set default address | isAuthenticated() | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/user/controller/UserProfileController.java
GET | /api/users/me/bank-accounts | UserProfileController | BE1 – An | BE-FR-ACC-03-03 BE-FR-ACC-03-04 | List bank accounts | isAuthenticated() | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/user/controller/UserProfileController.java
POST | /api/users/me/bank-accounts | UserProfileController | BE1 – An | BE-FR-ACC-03-03 | Add bank account | isAuthenticated() | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/user/controller/UserProfileController.java
PATCH | /api/users/me/bank-accounts/{id} | UserProfileController | BE1 – An | BE-FR-ACC-03-03 | Update bank account | isAuthenticated() | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/user/controller/UserProfileController.java
DELETE | /api/users/me/bank-accounts/{id} | UserProfileController | BE1 – An | BE-FR-ACC-03-03 | Deactivate bank account | isAuthenticated() | query/path | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/user/controller/UserProfileController.java
POST | /api/users/me/bank-accounts/{id}/default | UserProfileController | BE1 – An | BE-FR-ACC-03-03 | Set default bank account | isAuthenticated() | JSON | Hiện có trong source; cần Authorize trừ API public/callback. | src/main/java/com/project/w_3d_world/features/user/controller/UserProfileController.java
POST | /api/print/requests/getId/{printRequestId}/file/correct | PrintRequestController | BE2 – Khang | BE-V2-POD-FILE-01 BE-FR-POD-01-01 | Create corrected Draft file version | hasRole('CUSTOMER') + owner check | multipart/form-data | SOURCE MAPPED; MVC TEST PASSED; OpenAPI/runtime/PostgreSQL NOT VERIFIED | src/main/java/com/project/w_3d_world/features/printing/controller/PrintRequestController.java
GET | /api/print/requests/getId/{printRequestId}/file/versions | PrintRequestController | BE2 – Khang | BE-V2-POD-FILE-01 | List owned immutable file versions | hasRole('CUSTOMER') + owner check | path | SOURCE MAPPED; MVC TEST PASSED; OpenAPI/runtime/PostgreSQL NOT VERIFIED | src/main/java/com/project/w_3d_world/features/printing/controller/PrintRequestController.java
GET | /api/print/requests/getId/{printRequestId}/file/versions/{version}/download | PrintRequestController | BE2 – Khang | BE-V2-POD-FILE-01 | Download owned historical file | hasRole('CUSTOMER') + owner/Model check | path | SOURCE MAPPED; MVC TEST PASSED; OpenAPI/runtime/PostgreSQL NOT VERIFIED | src/main/java/com/project/w_3d_world/features/printing/controller/PrintRequestController.java
PATCH | /api/print/requests/getId/{printRequestId}/specifications | PrintRequestController | BE2 – Khang | BE-V2-POD-SPEC-01 BE-FR-POD-01-01 | Create a new Draft specification version | hasRole('CUSTOMER') + owner check | JSON | SOURCE MAPPED; MVC/SERVICE TEST PASSED; OpenAPI/runtime/PostgreSQL NOT VERIFIED | src/main/java/com/project/w_3d_world/features/printing/controller/PrintRequestController.java
GET | /api/print/requests/getId/{printRequestId}/specifications/versions | PrintRequestController | BE2 – Khang | BE-V2-POD-SPEC-01 | List owned immutable specification versions | hasRole('CUSTOMER') + owner check | path | SOURCE MAPPED; MVC/SERVICE TEST PASSED; OpenAPI/runtime/PostgreSQL NOT VERIFIED | src/main/java/com/project/w_3d_world/features/printing/controller/PrintRequestController.java

## DB48
48 tables — mapping & ownership
Một bảng có một owner Entity/Repository. Owner chức năng khác có thể dùng service contract. Đây là đề xuất ownership v2, giữ cột Owner cũ để review thay đổi; không yêu cầu chia đều số bảng.
DB Task ID | Table | Feature | Table Owner v2 | Owner file (3) | Loại bảng | Số cột | Status mapping | Code hiện có | Entity source | Repository source | FK tới bảng | Task chức năng liên quan | Việc còn thiếu / scope | Lý do phân công
BE-DB-01 | users | Account & Authorization | BE1 – An | BE1 – An | Baseline + v2 fields | 15 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/user/entity/User.java | src/main/java/com/project/w_3d_world/features/user/repository/UserRepository.java |  | BE-FR-ACC-01-01, BE-FR-ACC-01-02, BE-FR-ACC-02-01, BE-FR-ACC-02-02, BE-FR-ACC-03-01, BE-FR-ACC-03-02, BE-FR-ACC-03-03, BE-FR-ACC-03-04, BE-FR-ACC-05-01, BE-FR-OPS-05-01, BE-FR-ACC-04-01, BE-FR-STR-01-01, BE-FR-STR-02-01, BE-FR-STR-03-01, BE-FR-STR-03-02, BE-FR-AIG-03-01, BE-FR-AIG-03-02, BE-FR-AIG-01-01, BE-FR-AIG-02-01, BE-FR-AIG-04-01, BE-FR-AIG-04-02, BE-FR-AIG-05-01, BE-FR-AIG-06-01, BE-FR-AIG-06-02, BE-FR-OPS-03-01, BE-FR-DES-01-01, BE-FR-DES-02-01, BE-FR-DES-03-01, BE-FR-DES-03-02, BE-FR-DES-04-01, BE-FR-CHT-01-01, BE-V2-ACC-AVATAR-01, BE-V2-ACC-GOOGLE-01, BE-V2-POD-TEST-01 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-02 | roles | Account & Authorization | BE1 – An | BE1 – An | Baseline + v2 fields | 5 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/auth/entity/Role.java | src/main/java/com/project/w_3d_world/features/auth/repository/RoleRepository.java |  | BE-FR-ACC-01-01, BE-FR-ACC-02-01, BE-FR-ACC-05-01, BE-FR-OPS-05-01, BE-FR-OPS-03-01, BE-V2-ACC-GOOGLE-01 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-03 | user_roles | Account & Authorization | BE1 – An | BE1 – An | Baseline + v2 fields | 6 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/auth/entity/UserRole.java | src/main/java/com/project/w_3d_world/features/auth/repository/UserRoleRepository.java | roles, users | BE-FR-ACC-01-01, BE-FR-ACC-02-01, BE-FR-ACC-05-01, BE-FR-OPS-05-01, BE-FR-ACC-04-01, BE-FR-OPS-03-01, BE-V2-ACC-GOOGLE-01 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-04 | user_addresses | Account & Authorization | BE1 – An | BE1 – An | Baseline + v2 fields | 12 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/user/entity/UserAddress.java | src/main/java/com/project/w_3d_world/features/user/repository/UserAddressRepository.java | users | BE-FR-ACC-03-02, BE-FR-CHK-01-01, BE-FR-CHK-02-01, BE-FR-CHK-02-02, BE-FR-CHK-03-01, BE-V2-CHK-POLICY-01 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-05 | user_bank_accounts | Account & Authorization | BE1 – An | BE1 – An | Baseline + v2 fields | 14 | In-progress | Entity + Repository | src/main/java/com/project/w_3d_world/features/user/entity/UserBankAccount.java | src/main/java/com/project/w_3d_world/features/user/repository/UserBankAccountRepository.java | users | BE-FR-ACC-03-01, BE-FR-ACC-03-03, BE-FR-ACC-03-04, BE-FR-ACC-04-01 | Rà các cột chưa map/constraint, thêm persistence roundtrip tests. user_bank_accounts còn thiếu updated_at. | Giữ owner domain cũ.
BE-DB-06 | storefronts | Storefront & Subscription | BE1 – An | BE1 – An | Baseline + v2 fields | 9 | In-progress | Entity + Repository | src/main/java/com/project/w_3d_world/features/storefront/entity/Storefront.java | src/main/java/com/project/w_3d_world/features/storefront/repository/StorefrontRepository.java | users | BE-FR-ACC-02-01, BE-FR-ACC-05-01, BE-FR-ACC-04-01, BE-FR-STR-01-01, BE-FR-STR-02-01, BE-FR-STR-03-01, BE-FR-STR-03-02, BE-FR-CAT-01-01, BE-FR-CAT-02-01, BE-FR-CAT-04-01, BE-FR-SEL-01-01, BE-FR-SEL-03-01, BE-FR-SEL-04-01, BE-FR-SEL-02-01, BE-FR-CAT-03-01, BE-FR-CRT-01-01, BE-FR-CRT-02-01, BE-FR-CHK-01-01, BE-FR-CHK-02-01, BE-FR-CHK-02-02, BE-FR-CHK-03-01, BE-V2-REV-02 | Rà các cột chưa map/constraint, thêm persistence roundtrip tests. storefronts còn thiếu description/verified_at/created_at. | Giữ owner domain cũ.
BE-DB-07 | storefront_subscriptions | Storefront & Subscription | BE1 – An | BE1 – An | Baseline + v2 fields | 8 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | storefronts | BE-FR-STR-01-01, BE-FR-STR-02-01, BE-FR-STR-03-01, BE-FR-STR-03-02 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Giữ owner domain cũ.
BE-DB-08 | models_3d | Model Library & Versions | BE2 – Khang | BE2 – Khang | Baseline + v2 fields | 10 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/model/entity/Model3D.java | src/main/java/com/project/w_3d_world/features/model/repository/Model3DRepository.java | users | BE-FR-LIB-01-01, BE-FR-LIB-02-01, BE-FR-LIB-02-02, BE-FR-LIB-03-01, BE-FR-VIW-01-01, BE-FR-VIW-01-02, BE-FR-AIG-03-01, BE-FR-AIG-03-02, BE-FR-LIB-04-01, BE-FR-EDT-04-01, BE-FR-EDT-05-01, BE-FR-EDT-05-02, BE-FR-AIG-01-01, BE-FR-AIG-02-01, BE-FR-AIG-04-01, BE-FR-AIG-04-02, BE-FR-AIG-05-01, BE-FR-AIG-06-01, BE-FR-AIG-06-02, BE-FR-DES-01-01, BE-FR-DES-02-01, BE-FR-DES-03-01, BE-FR-DES-03-02, BE-FR-DES-04-01, BE-FR-DIG-01-01, BE-FR-DIG-02-01, BE-FR-DIG-02-02, BE-FR-DIG-03-01, BE-FR-DIG-03-02, BE-FR-DIG-04-01, BE-FR-DIG-05-01 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-09 | model_versions | Model Library & Versions | BE2 – Khang | BE2 – Khang | Baseline + v2 fields | 9 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/model/entity/ModelVersion.java | src/main/java/com/project/w_3d_world/features/model/repository/ModelVersionRepository.java | ai_requests, model_versions, models_3d, users | BE-FR-LIB-01-01, BE-FR-LIB-02-01, BE-FR-LIB-02-02, BE-FR-LIB-03-01, BE-FR-VIW-01-01, BE-FR-VIW-01-02, BE-FR-AIG-03-01, BE-FR-AIG-03-02, BE-FR-LIB-04-01, BE-FR-EDT-04-01, BE-FR-EDT-05-01, BE-FR-EDT-05-02, BE-FR-AIG-01-01, BE-FR-AIG-02-01, BE-FR-AIG-04-01, BE-FR-AIG-04-02, BE-FR-AIG-05-01, BE-FR-AIG-06-01, BE-FR-AIG-06-02, BE-FR-DES-01-01, BE-FR-DES-02-01, BE-FR-DES-03-01, BE-FR-DES-03-02, BE-FR-DES-04-01, BE-FR-DIG-01-01, BE-FR-DIG-02-01, BE-FR-DIG-02-02, BE-FR-DIG-03-01, BE-FR-DIG-03-02, BE-FR-DIG-04-01, BE-FR-DIG-05-01, BE-FR-REN-01-01, BE-FR-REN-02-01, BE-FR-REN-02-02, BE-FR-REN-03-01, BE-V2-POD-FILE-01 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-10 | model_files | Model Library & Versions | BE2 – Khang | BE2 – Khang | Baseline + v2 fields | 10 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/model/entity/ModelFile.java | src/main/java/com/project/w_3d_world/features/model/repository/ModelFileRepository.java | model_versions | BE-FR-LIB-01-01, BE-FR-LIB-02-01, BE-FR-LIB-02-02, BE-FR-LIB-03-01, BE-FR-VIW-01-01, BE-FR-VIW-01-02, BE-FR-AIG-03-01, BE-FR-AIG-03-02, BE-FR-LIB-04-01, BE-FR-EDT-04-01, BE-FR-EDT-05-01, BE-FR-EDT-05-02, BE-FR-AIG-01-01, BE-FR-AIG-02-01, BE-FR-AIG-04-01, BE-FR-AIG-04-02, BE-FR-AIG-05-01, BE-FR-AIG-06-01, BE-FR-AIG-06-02, BE-V2-POD-FILE-01 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-11 | ai_requests | AI Generation | BE2 – Khang | BE2 – Khang | Baseline + v2 fields | 15 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | model_versions, models_3d, users | BE-FR-AIG-03-01, BE-FR-AIG-03-02, BE-FR-AIG-01-01, BE-FR-AIG-02-01, BE-FR-AIG-04-01, BE-FR-AIG-04-02, BE-FR-AIG-05-01, BE-FR-AIG-06-01, BE-FR-AIG-06-02 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Giữ owner domain cũ.
BE-DB-12 | products | Physical Catalog | BE1 – An | BE1 – An | Baseline + v2 fields | 18 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/catalog/entity/Product.java | src/main/java/com/project/w_3d_world/features/catalog/repository/ProductRepository.java | storefronts, users | BE-FR-CAT-01-01, BE-FR-CAT-02-01, BE-FR-CAT-04-01, BE-FR-SEL-01-01, BE-FR-SEL-03-01, BE-FR-SEL-04-01, BE-FR-MOD-01-01, BE-FR-SEL-02-01, BE-FR-MOD-01-02, BE-FR-MOD-02-01, BE-FR-MOD-03-01, BE-FR-CAT-03-01, BE-FR-CRT-01-01, BE-FR-CRT-02-01, BE-FR-CHK-01-01, BE-FR-CHK-02-01, BE-FR-CHK-02-02, BE-FR-CHK-03-01, BE-FR-CAS-03-01, BE-V2-PKG-02, BE-V2-REV-01, BE-V2-REV-02 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-13 | product_media | Physical Catalog | BE1 – An | BE1 – An | Baseline + v2 fields | 7 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/catalog/entity/ProductMedia.java | src/main/java/com/project/w_3d_world/features/catalog/repository/ProductMediaRepository.java | product_variants, products | BE-FR-CAT-01-01, BE-FR-CAT-02-01, BE-FR-CAT-04-01, BE-FR-SEL-01-01, BE-FR-SEL-03-01, BE-FR-SEL-04-01, BE-FR-SEL-02-01, BE-FR-CAT-03-01 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-14 | product_variants | Physical Catalog | BE1 – An | BE1 – An | Baseline + v2 fields | 16 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/catalog/entity/ProductVariant.java | src/main/java/com/project/w_3d_world/features/catalog/repository/ProductVariantRepository.java | products | BE-FR-CAT-01-01, BE-FR-CAT-02-01, BE-FR-CAT-04-01, BE-FR-SEL-01-01, BE-FR-SEL-03-01, BE-FR-SEL-04-01, BE-FR-SEL-02-01, BE-FR-CAT-03-01, BE-FR-CRT-01-01, BE-FR-CRT-02-01, BE-FR-CHK-01-01, BE-FR-CHK-02-01, BE-FR-CHK-02-02, BE-FR-CHK-03-01, BE-V2-CRT-PRICE-01, BE-V2-CHK-RES-01, BE-V2-PKG-02 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-15 | carts | Cart | BE1 – An | BE1 – An | Baseline + v2 fields | 4 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/cart/entity/Cart.java | src/main/java/com/project/w_3d_world/features/cart/repository/CartRepository.java | users | BE-FR-CRT-01-01, BE-FR-CRT-02-01, BE-FR-CHK-01-01, BE-FR-CHK-02-01, BE-FR-CHK-02-02, BE-FR-CHK-03-01, BE-V2-CHK-IDEMP-01 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-16 | cart_items | Cart | BE1 – An | BE1 – An | Baseline + v2 fields | 8 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/cart/entity/CartItem.java | src/main/java/com/project/w_3d_world/features/cart/repository/CartItemRepository.java | carts, product_variants | BE-FR-CRT-01-01, BE-FR-CRT-02-01, BE-FR-CHK-01-01, BE-FR-CHK-02-01, BE-FR-CHK-02-02, BE-FR-CHK-03-01, BE-V2-CRT-PRICE-01, BE-V2-CHK-IDEMP-01 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-17 | physical_orders | Physical Orders | BE1 – An | BE1 – An | Baseline + v2 fields | 38 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/order/entity/PhysicalOrder.java | src/main/java/com/project/w_3d_world/features/order/repository/PhysicalOrderRepository.java | storefronts, user_addresses, users | BE-FR-ACC-03-02, BE-FR-OPS-01-01, BE-FR-CHK-01-01, BE-FR-CHK-02-01, BE-FR-CHK-02-02, BE-FR-CHK-03-01, BE-FR-ORD-01-01, BE-FR-ORD-03-01, BE-FR-ORD-03-02, BE-FR-CAS-01-01, BE-FR-CAS-02-01, BE-FR-ORD-02-01, BE-FR-CAS-02-02, BE-FR-ORD-04-01, BE-FR-ORD-04-02, BE-FR-ORD-05-01, BE-FR-ORD-05-02, BE-FR-CAS-03-01, BE-V2-CHK-IDEMP-01, BE-V2-CHK-POLICY-01, BE-V2-CHK-RES-01, BE-V2-ORD-HISTORY-01, BE-V2-ORD-PAY-01, BE-V2-PKG-03, BE-V2-REV-01 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-18 | physical_order_items | Physical Orders | BE1 – An | BE1 – An | Baseline + v2 fields | 9 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/order/entity/PhysicalOrderItem.java | src/main/java/com/project/w_3d_world/features/order/repository/PhysicalOrderItemRepository.java | physical_orders, product_variants | BE-FR-CHK-01-01, BE-FR-CHK-02-01, BE-FR-CHK-02-02, BE-FR-CHK-03-01, BE-FR-ORD-01-01, BE-FR-ORD-03-01, BE-FR-ORD-03-02, BE-FR-CAS-01-01, BE-FR-CAS-02-01, BE-FR-ORD-02-01, BE-FR-CAS-02-02, BE-FR-ORD-04-01, BE-FR-ORD-04-02, BE-FR-ORD-05-01, BE-FR-ORD-05-02, BE-FR-CAS-03-01, BE-V2-CHK-IDEMP-01, BE-V2-CHK-POLICY-01, BE-V2-CHK-RES-01, BE-V2-PKG-03, BE-V2-REV-01, BE-V2-REF-01 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-19 | shipments | Shipment (Physical + POD) | BE1 – An | BE1 – An | Baseline + v2 fields | 10 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/shipping/entity/Shipment.java | src/main/java/com/project/w_3d_world/features/shipping/repository/ShipmentRepository.java | physical_orders, print_requests | BE-FR-ORD-01-01, BE-FR-ORD-03-01, BE-FR-ORD-03-02, BE-FR-ORD-02-01, BE-FR-ORD-04-01, BE-FR-ORD-04-02, BE-FR-ORD-05-01, BE-FR-ORD-05-02 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-20 | rental_offers | Rental | BE2 – Khang | BE2 – Khang | Baseline + v2 fields | 9 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | model_versions, storefronts | BE-FR-DIG-01-01, BE-FR-DIG-02-01, BE-FR-DIG-02-02, BE-FR-DIG-03-01, BE-FR-DIG-03-02, BE-FR-DIG-04-01, BE-FR-DIG-05-01, BE-FR-REN-01-01, BE-FR-REN-02-01, BE-FR-REN-02-02, BE-FR-REN-03-01 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Giữ owner domain cũ.
BE-DB-21 | rental_plans | Rental | BE2 – Khang | BE2 – Khang | Baseline + v2 fields | 10 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | rental_offers | BE-FR-REN-01-01, BE-FR-REN-02-01, BE-FR-REN-02-02, BE-FR-REN-03-01 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Giữ owner domain cũ.
BE-DB-22 | rental_contracts | Rental | BE2 – Khang | BE2 – Khang | Baseline + v2 fields | 17 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | model_versions, rental_offers, rental_plans, users | BE-FR-DIG-01-01, BE-FR-DIG-02-01, BE-FR-DIG-02-02, BE-FR-DIG-03-01, BE-FR-DIG-03-02, BE-FR-DIG-04-01, BE-FR-DIG-05-01, BE-FR-REN-01-01, BE-FR-REN-02-01, BE-FR-REN-02-02, BE-FR-REN-03-01 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Giữ owner domain cũ.
BE-DB-23 | print_materials | Print On Demand | BE2 – Khang | BE2 – Khang | Baseline + v2 fields | 6 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/printing/entity/PrintMaterial.java | src/main/java/com/project/w_3d_world/features/printing/repository/PrintMaterialRepository.java |  | BE-FR-POD-01-01, BE-FR-POD-02-01, BE-FR-POD-03-01, BE-FR-POD-03-02, BE-FR-POD-04-01, BE-FR-POD-05-01, BE-FR-POD-05-02, BE-FR-POD-06-01, BE-FR-POD-07-01, BE-FR-POD-07-02, BE-V2-POD-MAT-01 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-24 | print_requests | Print On Demand | BE2 – Khang | BE2 – Khang | Baseline + v2 fields | 20 | In-progress | Entity only | src/main/java/com/project/w_3d_world/features/printing/entity/PrintRequest.java | Chưa có | print_quotes, print_request_file_versions, print_request_spec_versions, user_addresses, users | BE-FR-POD-01-01, BE-FR-POD-02-01, BE-FR-POD-03-01, BE-FR-POD-03-02, BE-FR-POD-04-01, BE-FR-POD-05-01, BE-FR-POD-05-02, BE-FR-POD-06-01, BE-FR-POD-07-01, BE-FR-POD-07-02, BE-V2-POD-FILE-01, BE-V2-POD-SPEC-01, BE-V2-POD-REVIEW-01, BE-V2-POD-STATE-01, BE-V2-POD-QUOTE-01, BE-V2-POD-TEST-01 | Entity đã có 20 field/JSONB; BE2 cập nhật mapping test + fixtures cũ trước khi Done DB task. | Giữ owner domain cũ.
BE-DB-25 | print_request_items | Print On Demand | BE2 – Khang | BE2 – Khang | Baseline + v2 fields | 14 | In-progress | Entity only | src/main/java/com/project/w_3d_world/features/printing/entity/PrintRequestItem.java | Chưa có | model_versions, print_materials, print_requests | BE-FR-POD-01-01, BE-FR-POD-02-01, BE-FR-POD-03-01, BE-FR-POD-03-02, BE-FR-POD-04-01, BE-FR-POD-05-01, BE-FR-POD-05-02, BE-FR-POD-06-01, BE-FR-POD-07-01, BE-FR-POD-07-02, BE-V2-POD-SPEC-01 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Giữ owner domain cũ.
BE-DB-26 | print_quotes | Print On Demand | BE2 – Khang | BE2 – Khang | Baseline + v2 fields | 14 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | print_request_file_versions, print_request_spec_versions, print_requests, users | BE-FR-POD-01-01, BE-FR-POD-02-01, BE-FR-POD-03-01, BE-FR-POD-03-02, BE-FR-POD-04-01, BE-FR-POD-05-01, BE-FR-POD-05-02, BE-FR-POD-06-01, BE-FR-POD-07-01, BE-FR-POD-07-02, BE-V2-POD-QUOTE-01 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Giữ owner domain cũ.
BE-DB-27 | print_quote_items | Print On Demand | BE2 – Khang | BE2 – Khang | Baseline + v2 fields | 12 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | print_quotes, print_request_items | BE-FR-POD-01-01, BE-FR-POD-02-01, BE-FR-POD-03-01, BE-FR-POD-03-02, BE-FR-POD-04-01, BE-FR-POD-05-01, BE-FR-POD-05-02, BE-FR-POD-06-01, BE-FR-POD-07-01, BE-FR-POD-07-02, BE-V2-POD-QUOTE-01 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Giữ owner domain cũ.
BE-DB-28 | transactions | Payment & Provider Attempts | BE1 – An | BE2 – Khang | Baseline + v2 fields | 28 | In-progress | Entity + Repository | src/main/java/com/project/w_3d_world/features/payment/entity/PaymentTransaction.java | src/main/java/com/project/w_3d_world/features/payment/repository/PaymentTransactionRepository.java | physical_orders, print_quotes, print_requests, rental_contracts, storefront_subscriptions, transactions, user_bank_accounts, users, wallets | BE-FR-PAY-01-01, BE-FR-PAY-01-02, BE-FR-PAY-02-01, BE-FR-PAY-02-02, BE-FR-WAL-01-01, BE-FR-WAL-01-02, BE-FR-OPS-01-01, BE-FR-STR-01-01, BE-FR-STR-02-01, BE-FR-STR-03-01, BE-FR-STR-03-02, BE-FR-PAY-03-01, BE-FR-WAL-02-01, BE-FR-CAS-01-01, BE-FR-CAS-02-01, BE-FR-CAS-02-02, BE-FR-PAY-04-01, BE-FR-WAL-03-01, BE-FR-WAL-03-02, BE-FR-WAL-04-01, BE-FR-WAL-05-01, BE-FR-WAL-05-02, BE-FR-DES-01-01, BE-FR-DES-02-01, BE-FR-DES-03-01, BE-FR-DES-03-02, BE-FR-DES-04-01, BE-FR-DIG-01-01, BE-FR-DIG-02-01, BE-FR-DIG-02-02, BE-FR-DIG-03-01, BE-FR-DIG-03-02, BE-FR-DIG-04-01, BE-FR-DIG-05-01, BE-FR-REN-01-01, BE-FR-REN-02-01, BE-FR-REN-02-02, BE-FR-REN-03-01, BE-V2-ORD-PAY-01, BE-V2-REF-01, BE-V2-REF-03, BE-V2-PAY-PERSIST-01, BE-V2-WAL-HANDLER-01 | Rà các cột chưa map/constraint, thêm persistence roundtrip tests. PaymentTransaction/Attempt mới map phần đang dùng, chưa hết baseline columns. | Đề xuất đổi owner để khớp feature: Payment/Platform config BE1; Wallet/Ledger/Earnings BE2. Cần nhóm xác nhận phân công.
BE-DB-29 | transaction_attempts | Payment & Provider Attempts | BE1 – An | BE2 – Khang | Baseline + v2 fields | 31 | In-progress | Entity + Repository | src/main/java/com/project/w_3d_world/features/payment/entity/PaymentAttempt.java | src/main/java/com/project/w_3d_world/features/payment/repository/PaymentAttemptRepository.java | transactions, users | BE-FR-PAY-01-01, BE-FR-PAY-01-02, BE-FR-PAY-02-01, BE-FR-PAY-02-02, BE-FR-WAL-01-01, BE-FR-WAL-01-02, BE-FR-PAY-03-01, BE-FR-WAL-02-01, BE-FR-CAS-01-01, BE-FR-CAS-02-01, BE-FR-CAS-02-02, BE-FR-PAY-04-01, BE-FR-WAL-03-01, BE-FR-WAL-03-02, BE-FR-WAL-04-01, BE-FR-WAL-05-01, BE-FR-WAL-05-02, BE-V2-ORD-PAY-01, BE-V2-REF-03, BE-V2-PAY-PERSIST-01 | Rà các cột chưa map/constraint, thêm persistence roundtrip tests. PaymentTransaction/Attempt mới map phần đang dùng, chưa hết baseline columns. | Đề xuất đổi owner để khớp feature: Payment/Platform config BE1; Wallet/Ledger/Earnings BE2. Cần nhóm xác nhận phân công.
BE-DB-30 | wallets | Wallet & Earnings | BE2 – Khang | BE2 – Khang | Baseline + v2 fields | 7 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | users | BE-FR-WAL-01-01, BE-FR-WAL-01-02, BE-FR-WAL-02-01, BE-FR-CAS-01-01, BE-FR-CAS-02-01, BE-FR-CAS-02-02, BE-FR-WAL-03-01, BE-FR-WAL-03-02, BE-FR-WAL-04-01, BE-FR-WAL-05-01, BE-FR-WAL-05-02, BE-V2-REF-03, BE-V2-WAL-HANDLER-01 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Giữ owner domain cũ.
BE-DB-31 | wallet_ledgers | Wallet & Earnings | BE2 – Khang | BE2 – Khang | Baseline + v2 fields | 10 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | seller_earnings, transactions, wallets | BE-FR-WAL-01-01, BE-FR-WAL-01-02, BE-FR-WAL-02-01, BE-FR-CAS-01-01, BE-FR-CAS-02-01, BE-FR-CAS-02-02, BE-FR-WAL-03-01, BE-FR-WAL-03-02, BE-FR-WAL-04-01, BE-FR-WAL-05-01, BE-FR-WAL-05-02, BE-V2-REF-03, BE-V2-WAL-HANDLER-01 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Giữ owner domain cũ.
BE-DB-32 | seller_earnings | Wallet & Earnings | BE2 – Khang | BE2 – Khang | Baseline + v2 fields | 15 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | physical_orders, users, wallets | BE-FR-WAL-01-01, BE-FR-WAL-01-02, BE-FR-WAL-02-01, BE-FR-CAS-01-01, BE-FR-CAS-02-01, BE-FR-CAS-02-02, BE-FR-WAL-03-01, BE-FR-WAL-03-02, BE-FR-WAL-04-01, BE-FR-WAL-05-01, BE-FR-WAL-05-02, BE-V2-REF-03, BE-V2-WAL-HANDLER-01 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Giữ owner domain cũ.
BE-DB-33 | reports | Governance & Operations | BE1 – An | BE1 – An | Baseline + v2 fields | 13 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | products, rental_offers, users | BE-FR-MOD-01-01, BE-FR-MOD-01-02, BE-FR-MOD-02-01, BE-FR-MOD-03-01 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Giữ owner domain cũ.
BE-DB-34 | notifications | Governance & Operations | BE2 – Khang | BE1 – An | Baseline + v2 fields | 15 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | users | BE-FR-MOD-01-01, BE-FR-MOD-01-02, BE-FR-MOD-02-01, BE-FR-MOD-03-01, BE-FR-OPS-02-01, BE-FR-OPS-02-02, BE-FR-OPS-03-01, BE-FR-CHT-01-01, BE-V2-NOTIF-01 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Đề xuất đổi owner để khớp feature: Payment/Platform config BE1; Wallet/Ledger/Earnings BE2. Cần nhóm xác nhận phân công.
BE-DB-35 | audit_logs | Governance & Operations | BE1 – An | BE1 – An | Baseline + v2 fields | 11 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/audit/entity/AuditLog.java | src/main/java/com/project/w_3d_world/features/audit/repository/AuditLogRepository.java | users | BE-FR-ACC-03-01, BE-FR-ACC-03-03, BE-FR-ACC-03-04, BE-FR-OPS-01-01, BE-FR-OPS-04-01, BE-FR-OPS-05-01, BE-FR-ACC-04-01, BE-FR-SEL-01-01, BE-FR-SEL-03-01, BE-FR-SEL-04-01, BE-FR-MOD-01-01, BE-FR-SEL-02-01, BE-FR-MOD-01-02, BE-FR-MOD-02-01, BE-FR-MOD-03-01, BE-FR-AIG-03-01, BE-FR-AIG-03-02, BE-FR-ORD-01-01, BE-FR-ORD-03-01, BE-FR-ORD-03-02, BE-FR-AIG-01-01, BE-FR-AIG-02-01, BE-FR-AIG-04-01, BE-FR-AIG-04-02, BE-FR-AIG-05-01, BE-FR-AIG-06-01, BE-FR-AIG-06-02, BE-FR-CAS-01-01, BE-FR-CAS-02-01, BE-FR-ORD-02-01, BE-FR-CAS-02-02, BE-FR-ORD-04-01, BE-FR-ORD-04-02, BE-FR-ORD-05-01, BE-FR-ORD-05-02, BE-FR-CAS-03-01, BE-FR-OPS-03-01, BE-V2-AUDIT-JSON-01, BE-V2-PKG-01, BE-V2-REV-02, BE-V2-REF-02, BE-V2-POD-MAT-01, BE-V2-POD-REVIEW-01 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Giữ owner domain cũ.
BE-DB-36 | platform_configs | Governance & Operations | BE1 – An | BE2 – Khang | Baseline + v2 fields | 5 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | users | BE-FR-OPS-01-01, BE-FR-OPS-03-01 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Đề xuất đổi owner để khớp feature: Payment/Platform config BE1; Wallet/Ledger/Earnings BE2. Cần nhóm xác nhận phân công.
BE-DB-37 | packaging_profiles | Packaging & Shipping Cost | BE1 – An | Bảng mới v2 | v2 mới | 17 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có |  | BE-V2-PKG-01, BE-V2-PKG-02 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Bảng v2 mới; giao cho owner của feature tương ứng, phối hợp khi FK crossing.
BE-DB-38 | reviews | Reviews & Merchant Replies | BE1 – An | Bảng mới v2 | v2 mới | 11 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | physical_order_items, physical_orders, products, users | BE-FR-CAS-03-01, BE-V2-REV-01, BE-V2-REV-02 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Bảng v2 mới; giao cho owner của feature tương ứng, phối hợp khi FK crossing.
BE-DB-39 | review_merchant_replies | Reviews & Merchant Replies | BE1 – An | Bảng mới v2 | v2 mới | 6 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | reviews, users | BE-FR-CAS-03-01, BE-V2-REV-02 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Bảng v2 mới; giao cho owner của feature tương ứng, phối hợp khi FK crossing.
BE-DB-40 | order_status_history | Physical Orders | BE1 – An | Bảng mới v2 | v2 mới | 8 | Done | Entity + Repository | src/main/java/com/project/w_3d_world/features/order/entity/OrderStatusHistory.java | src/main/java/com/project/w_3d_world/features/order/repository/OrderStatusHistoryRepository.java | physical_orders, users | BE-FR-OPS-04-01, BE-FR-CHK-01-01, BE-FR-CHK-02-01, BE-FR-CHK-02-02, BE-FR-CHK-03-01, BE-FR-ORD-01-01, BE-FR-ORD-03-01, BE-FR-ORD-03-02, BE-FR-ORD-02-01, BE-FR-ORD-04-01, BE-FR-ORD-04-02, BE-FR-ORD-05-01, BE-FR-ORD-05-02, BE-V2-ORD-HISTORY-01, BE-V2-ORD-PAY-01 | Đã map cho scope hiện có; nghiệp vụ và API xem Tasks v2, không suy ra business Done từ mapping. | Bảng v2 mới; giao cho owner của feature tương ứng, phối hợp khi FK crossing.
BE-DB-41 | order_shipping_packages | Packaging & Shipping Cost | BE1 – An | Bảng mới v2 | v2 mới | 20 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | packaging_profiles, physical_orders | BE-V2-PKG-03 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Bảng v2 mới; giao cho owner của feature tương ứng, phối hợp khi FK crossing.
BE-DB-42 | order_shipping_package_items | Packaging & Shipping Cost | BE1 – An | Bảng mới v2 | v2 mới | 11 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | order_shipping_packages, physical_order_items, physical_orders, product_variants, products | BE-V2-PKG-03 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Bảng v2 mới; giao cho owner của feature tương ứng, phối hợp khi FK crossing.
BE-DB-43 | refund_requests | Refund Requests | BE1 – An | Bảng mới v2 | v2 mới | 24 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | transactions, users | BE-FR-CAS-01-01, BE-FR-CAS-02-01, BE-FR-CAS-02-02, BE-V2-REF-01, BE-V2-REF-02, BE-V2-REF-03 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Bảng v2 mới; giao cho owner của feature tương ứng, phối hợp khi FK crossing.
BE-DB-44 | refund_request_items | Refund Requests | BE1 – An | Bảng mới v2 | v2 mới | 8 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | physical_order_items, products, refund_requests | BE-FR-CAS-01-01, BE-FR-CAS-02-01, BE-FR-CAS-02-02, BE-V2-REF-01, BE-V2-REF-02 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Bảng v2 mới; giao cho owner của feature tương ứng, phối hợp khi FK crossing.
BE-DB-45 | print_request_file_versions | Print On Demand | BE2 – Khang | Bảng mới v2 | v2 mới | 9 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | print_requests, users | BE-FR-POD-01-01, BE-FR-POD-02-01, BE-FR-POD-03-01, BE-FR-POD-03-02, BE-FR-POD-04-01, BE-FR-POD-05-01, BE-FR-POD-05-02, BE-FR-POD-06-01, BE-FR-POD-07-01, BE-FR-POD-07-02, BE-V2-POD-FILE-01, BE-V2-POD-QUOTE-01 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Bảng v2 mới; giao cho owner của feature tương ứng, phối hợp khi FK crossing.
BE-DB-46 | print_request_spec_versions | Print On Demand | BE2 – Khang | Bảng mới v2 | v2 mới | 6 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | print_requests, users | BE-FR-POD-01-01, BE-FR-POD-02-01, BE-FR-POD-03-01, BE-FR-POD-03-02, BE-FR-POD-04-01, BE-FR-POD-05-01, BE-FR-POD-05-02, BE-FR-POD-06-01, BE-FR-POD-07-01, BE-FR-POD-07-02, BE-V2-POD-SPEC-01, BE-V2-POD-QUOTE-01 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Bảng v2 mới; giao cho owner của feature tương ứng, phối hợp khi FK crossing.
BE-DB-47 | print_request_status_history | Print On Demand | BE2 – Khang | Bảng mới v2 | v2 mới | 8 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | print_requests, users | BE-FR-OPS-04-01, BE-FR-POD-01-01, BE-FR-POD-02-01, BE-FR-POD-03-01, BE-FR-POD-03-02, BE-FR-POD-04-01, BE-FR-POD-05-01, BE-FR-POD-05-02, BE-FR-POD-06-01, BE-FR-POD-07-01, BE-FR-POD-07-02, BE-V2-POD-STATE-01 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Bảng v2 mới; giao cho owner của feature tương ứng, phối hợp khi FK crossing.
BE-DB-48 | print_request_technical_reviews | Print On Demand | BE2 – Khang | Bảng mới v2 | v2 mới | 6 | In-progress | Chưa có Entity/Repository | Chưa có | Chưa có | print_requests, users | BE-FR-POD-01-01, BE-FR-POD-02-01, BE-FR-POD-03-01, BE-FR-POD-03-02, BE-FR-POD-04-01, BE-FR-POD-05-01, BE-FR-POD-05-02, BE-FR-POD-06-01, BE-FR-POD-07-01, BE-FR-POD-07-02, BE-V2-POD-REVIEW-01 | Triển khai Entity/Repository khi nhận task feature; PK/FK/UNIQUE/CHECK/JSONB phải khớp schema, không tạo bảng trùng. | Bảng v2 mới; giao cho owner của feature tương ứng, phối hợp khi FK crossing.

## Relationships
Foreign-key relationships — schema v2
Quan hệ lấy trực tiếp từ PostgreSQL v2 đã validate, gồm composite FK. N:1 là quan hệ của từng FK, không mô tả toàn bộ business ownership. Partial unique indexes xem Constraints.
ID | Bảng nguồn | Cột nguồn | Bảng đích | Cột đích | Cardinality FK | Nullable | Owner nguồn | Owner đích | Boundary | Constraint | DDL relationship | Business/contract guard
FK-001 | ai_requests | model_id, base_version_id | model_versions | model_id, model_version_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_ai_requests_base_same_model | FOREIGN KEY (model_id, base_version_id) REFERENCES model_versions(model_id, model_version_id) ON DELETE RESTRICT | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-002 | ai_requests | base_version_id | model_versions | model_version_id | N : 1 | Có thể NULL | BE2 – Khang | BE2 – Khang | Cùng owner | fk_ai_requests_base_version_id | FOREIGN KEY (base_version_id) REFERENCES model_versions(model_version_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-003 | ai_requests | model_id | models_3d | model_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_ai_requests_model_id | FOREIGN KEY (model_id) REFERENCES models_3d(model_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-004 | ai_requests | user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE1 – An | Cross-owner | fk_ai_requests_user_id | FOREIGN KEY (user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-005 | audit_logs | actor_user_id | users | user_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_audit_logs_actor_user_id | FOREIGN KEY (actor_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-006 | cart_items | cart_id | carts | cart_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_cart_items_cart | FOREIGN KEY (cart_id) REFERENCES carts(cart_id) ON DELETE CASCADE | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-007 | cart_items | variant_id | product_variants | variant_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_cart_items_variant | FOREIGN KEY (variant_id) REFERENCES product_variants(variant_id) ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-008 | carts | user_id | users | user_id | 1 : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_carts_user | FOREIGN KEY (user_id) REFERENCES users(user_id) ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-009 | model_files | model_version_id | model_versions | model_version_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_model_files_model_version_id | FOREIGN KEY (model_version_id) REFERENCES model_versions(model_version_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-010 | model_versions | ai_request_id | ai_requests | ai_request_id | 0..1 : 1 | Có thể NULL | BE2 – Khang | BE2 – Khang | Cùng owner | fk_model_versions_ai_request_id | FOREIGN KEY (ai_request_id) REFERENCES ai_requests(ai_request_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-011 | model_versions | model_id, ai_request_id | ai_requests | model_id, ai_request_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_model_versions_ai_same_model | FOREIGN KEY (model_id, ai_request_id) REFERENCES ai_requests(model_id, ai_request_id) ON DELETE RESTRICT | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-012 | model_versions | created_by_user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE1 – An | Cross-owner | fk_model_versions_created_by_user_id | FOREIGN KEY (created_by_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-013 | model_versions | model_id | models_3d | model_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_model_versions_model_id | FOREIGN KEY (model_id) REFERENCES models_3d(model_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-014 | model_versions | model_id, parent_version_id | model_versions | model_id, model_version_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_model_versions_parent_same_model | FOREIGN KEY (model_id, parent_version_id) REFERENCES model_versions(model_id, model_version_id) ON DELETE RESTRICT | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-015 | model_versions | parent_version_id | model_versions | model_version_id | N : 1 | Có thể NULL | BE2 – Khang | BE2 – Khang | Cùng owner | fk_model_versions_parent_version_id | FOREIGN KEY (parent_version_id) REFERENCES model_versions(model_version_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-016 | models_3d | owner_user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE1 – An | Cross-owner | fk_models_3d_owner_user_id | FOREIGN KEY (owner_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-017 | notifications | recipient_user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE1 – An | Cross-owner | fk_notifications_recipient_user_id | FOREIGN KEY (recipient_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-018 | order_shipping_package_items | physical_order_id | physical_orders | physical_order_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | order_shipping_package_items_physical_order_id_fkey | FOREIGN KEY (physical_order_id) REFERENCES physical_orders(physical_order_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-019 | order_shipping_package_items | physical_order_id, physical_order_item_id | physical_order_items | physical_order_id, physical_order_item_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | order_shipping_package_items_physical_order_id_physical_or_fkey | FOREIGN KEY (physical_order_id, physical_order_item_id) REFERENCES physical_order_items(physical_order_id, physical_order_item_id) | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-020 | order_shipping_package_items | physical_order_id, shipping_package_id | order_shipping_packages | physical_order_id, shipping_package_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | order_shipping_package_items_physical_order_id_shipping_pa_fkey | FOREIGN KEY (physical_order_id, shipping_package_id) REFERENCES order_shipping_packages(physical_order_id, shipping_package_id) | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-021 | order_shipping_package_items | physical_order_item_id | physical_order_items | physical_order_item_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | order_shipping_package_items_physical_order_item_id_fkey | FOREIGN KEY (physical_order_item_id) REFERENCES physical_order_items(physical_order_item_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-022 | order_shipping_package_items | product_id | products | product_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | order_shipping_package_items_product_id_fkey | FOREIGN KEY (product_id) REFERENCES products(product_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-023 | order_shipping_package_items | product_id, variant_id | product_variants | product_id, variant_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | order_shipping_package_items_product_id_variant_id_fkey | FOREIGN KEY (product_id, variant_id) REFERENCES product_variants(product_id, variant_id) | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-024 | order_shipping_package_items | shipping_package_id | order_shipping_packages | shipping_package_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | order_shipping_package_items_shipping_package_id_fkey | FOREIGN KEY (shipping_package_id) REFERENCES order_shipping_packages(shipping_package_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-025 | order_shipping_package_items | variant_id | product_variants | variant_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | order_shipping_package_items_variant_id_fkey | FOREIGN KEY (variant_id) REFERENCES product_variants(variant_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-026 | order_shipping_packages | packaging_profile_id | packaging_profiles | packaging_profile_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | order_shipping_packages_packaging_profile_id_fkey | FOREIGN KEY (packaging_profile_id) REFERENCES packaging_profiles(packaging_profile_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-027 | order_shipping_packages | physical_order_id | physical_orders | physical_order_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | order_shipping_packages_physical_order_id_fkey | FOREIGN KEY (physical_order_id) REFERENCES physical_orders(physical_order_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-028 | order_status_history | changed_by_user_id | users | user_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | order_status_history_changed_by_user_id_fkey | FOREIGN KEY (changed_by_user_id) REFERENCES users(user_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-029 | order_status_history | physical_order_id | physical_orders | physical_order_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | order_status_history_physical_order_id_fkey | FOREIGN KEY (physical_order_id) REFERENCES physical_orders(physical_order_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-030 | physical_order_items | physical_order_id | physical_orders | physical_order_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_physical_orders_item_physical_order_id | FOREIGN KEY (physical_order_id) REFERENCES physical_orders(physical_order_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-031 | physical_order_items | variant_id | product_variants | variant_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_physical_orders_item_variant_id | FOREIGN KEY (variant_id) REFERENCES product_variants(variant_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-032 | physical_orders | buyer_user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_physical_orders_buyer_user_id | FOREIGN KEY (buyer_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-033 | physical_orders | shipping_address_id | user_addresses | address_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_physical_orders_shipping_address_id | FOREIGN KEY (shipping_address_id) REFERENCES user_addresses(address_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-034 | physical_orders | storefront_id | storefronts | storefront_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_physical_orders_storefront_id | FOREIGN KEY (storefront_id) REFERENCES storefronts(storefront_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-035 | platform_configs | updated_by_user_id | users | user_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_platform_configs_updated_by_user_id | FOREIGN KEY (updated_by_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-036 | print_quote_items | print_quote_id | print_quotes | print_quote_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_print_quotes_item_print_quote_id | FOREIGN KEY (print_quote_id) REFERENCES print_quotes(print_quote_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-037 | print_quote_items | print_request_item_id | print_request_items | print_request_item_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_print_quotes_item_print_request_item_id | FOREIGN KEY (print_request_item_id) REFERENCES print_request_items(print_request_item_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-038 | print_quotes | print_request_id | print_requests | print_request_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_print_quotes_print_request_id | FOREIGN KEY (print_request_id) REFERENCES print_requests(print_request_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-039 | print_quotes | quoted_by_user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE1 – An | Cross-owner | fk_print_quotes_quoted_by_user_id | FOREIGN KEY (quoted_by_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-040 | print_quotes | print_request_id, file_version_snapshot | print_request_file_versions | print_request_id, version | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_quote_file_version | FOREIGN KEY (print_request_id, file_version_snapshot) REFERENCES print_request_file_versions(print_request_id, version) | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-041 | print_quotes | print_request_id, specification_version_snapshot | print_request_spec_versions | print_request_id, version | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_quote_spec_version | FOREIGN KEY (print_request_id, specification_version_snapshot) REFERENCES print_request_spec_versions(print_request_id, version) | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-042 | print_request_file_versions | print_request_id | print_requests | print_request_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | print_request_file_versions_print_request_id_fkey | FOREIGN KEY (print_request_id) REFERENCES print_requests(print_request_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-043 | print_request_file_versions | uploaded_by_user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE1 – An | Cross-owner | print_request_file_versions_uploaded_by_user_id_fkey | FOREIGN KEY (uploaded_by_user_id) REFERENCES users(user_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-044 | print_request_items | material_id | print_materials | material_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_print_requests_item_material_id | FOREIGN KEY (material_id) REFERENCES print_materials(material_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-045 | print_request_items | model_version_id | model_versions | model_version_id | N : 1 | Có thể NULL | BE2 – Khang | BE2 – Khang | Cùng owner | fk_print_requests_item_model_version_id | FOREIGN KEY (model_version_id) REFERENCES model_versions(model_version_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-046 | print_request_items | print_request_id | print_requests | print_request_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_print_requests_item_print_request_id | FOREIGN KEY (print_request_id) REFERENCES print_requests(print_request_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-047 | print_request_spec_versions | created_by_user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE1 – An | Cross-owner | print_request_spec_versions_created_by_user_id_fkey | FOREIGN KEY (created_by_user_id) REFERENCES users(user_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-048 | print_request_spec_versions | print_request_id | print_requests | print_request_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | print_request_spec_versions_print_request_id_fkey | FOREIGN KEY (print_request_id) REFERENCES print_requests(print_request_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-049 | print_request_status_history | changed_by_user_id | users | user_id | N : 1 | Có thể NULL | BE2 – Khang | BE1 – An | Cross-owner | print_request_status_history_changed_by_user_id_fkey | FOREIGN KEY (changed_by_user_id) REFERENCES users(user_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-050 | print_request_status_history | print_request_id | print_requests | print_request_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | print_request_status_history_print_request_id_fkey | FOREIGN KEY (print_request_id) REFERENCES print_requests(print_request_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-051 | print_request_technical_reviews | print_request_id | print_requests | print_request_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | print_request_technical_reviews_print_request_id_fkey | FOREIGN KEY (print_request_id) REFERENCES print_requests(print_request_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-052 | print_request_technical_reviews | reviewer_user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE1 – An | Cross-owner | print_request_technical_reviews_reviewer_user_id_fkey | FOREIGN KEY (reviewer_user_id) REFERENCES users(user_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-053 | print_requests | print_request_id, current_file_version | print_request_file_versions | print_request_id, version | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_current_file_version | FOREIGN KEY (print_request_id, current_file_version) REFERENCES print_request_file_versions(print_request_id, version) | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-054 | print_requests | print_request_id, current_quote_id | print_quotes | print_request_id, print_quote_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_current_quote_same_request | FOREIGN KEY (print_request_id, current_quote_id) REFERENCES print_quotes(print_request_id, print_quote_id) | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-055 | print_requests | print_request_id, current_spec_version | print_request_spec_versions | print_request_id, version | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_current_spec_version | FOREIGN KEY (print_request_id, current_spec_version) REFERENCES print_request_spec_versions(print_request_id, version) | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-056 | print_requests | handled_by_user_id | users | user_id | N : 1 | Có thể NULL | BE2 – Khang | BE1 – An | Cross-owner | fk_print_handled_by | FOREIGN KEY (handled_by_user_id) REFERENCES users(user_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-057 | print_requests | customer_user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE1 – An | Cross-owner | fk_print_requests_customer_user_id | FOREIGN KEY (customer_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-058 | print_requests | shipping_address_id | user_addresses | address_id | N : 1 | Có thể NULL | BE2 – Khang | BE1 – An | Cross-owner | fk_print_requests_shipping_address_id | FOREIGN KEY (shipping_address_id) REFERENCES user_addresses(address_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-059 | product_media | product_id, variant_id | product_variants | product_id, variant_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_media_variant_same_product | FOREIGN KEY (product_id, variant_id) REFERENCES product_variants(product_id, variant_id) | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-060 | product_media | product_id | products | product_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_products_media_product_id | FOREIGN KEY (product_id) REFERENCES products(product_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-061 | product_variants | product_id | products | product_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_products_variant_product_id | FOREIGN KEY (product_id) REFERENCES products(product_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-062 | products | created_by_user_id | users | user_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_product_created_by | FOREIGN KEY (created_by_user_id) REFERENCES users(user_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-063 | products | storefront_id | storefronts | storefront_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_products_storefront_id | FOREIGN KEY (storefront_id) REFERENCES storefronts(storefront_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-064 | refund_request_items | physical_order_item_id | physical_order_items | physical_order_item_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | refund_request_items_physical_order_item_id_fkey | FOREIGN KEY (physical_order_item_id) REFERENCES physical_order_items(physical_order_item_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Service kiểm tra original paid source + cumulative refunded amount.
FK-065 | refund_request_items | product_id | products | product_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | refund_request_items_product_id_fkey | FOREIGN KEY (product_id) REFERENCES products(product_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Service kiểm tra original paid source + cumulative refunded amount.
FK-066 | refund_request_items | refund_request_id | refund_requests | refund_request_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | refund_request_items_refund_request_id_fkey | FOREIGN KEY (refund_request_id) REFERENCES refund_requests(refund_request_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Service kiểm tra original paid source + cumulative refunded amount.
FK-067 | refund_requests | completed_by_user_id | users | user_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | refund_requests_completed_by_user_id_fkey | FOREIGN KEY (completed_by_user_id) REFERENCES users(user_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Service kiểm tra original paid source + cumulative refunded amount.
FK-068 | refund_requests | customer_user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | refund_requests_customer_user_id_fkey | FOREIGN KEY (customer_user_id) REFERENCES users(user_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Service kiểm tra original paid source + cumulative refunded amount.
FK-069 | refund_requests | reviewed_by_user_id | users | user_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | refund_requests_reviewed_by_user_id_fkey | FOREIGN KEY (reviewed_by_user_id) REFERENCES users(user_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Service kiểm tra original paid source + cumulative refunded amount.
FK-070 | refund_requests | transaction_id | transactions | transaction_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | refund_requests_transaction_id_fkey | FOREIGN KEY (transaction_id) REFERENCES transactions(transaction_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Service kiểm tra original paid source + cumulative refunded amount.
FK-071 | rental_contracts | designer_user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE1 – An | Cross-owner | fk_rental_contracts_designer_user_id | FOREIGN KEY (designer_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-072 | rental_contracts | rental_offer_id, model_version_id | rental_offers | rental_offer_id, model_version_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_rental_contracts_model_same_offer | FOREIGN KEY (rental_offer_id, model_version_id) REFERENCES rental_offers(rental_offer_id, model_version_id) ON DELETE RESTRICT | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-073 | rental_contracts | model_version_id | model_versions | model_version_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_rental_contracts_model_version_id | FOREIGN KEY (model_version_id) REFERENCES model_versions(model_version_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-074 | rental_contracts | rental_offer_id, rental_plan_id | rental_plans | rental_offer_id, rental_plan_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_rental_contracts_plan_same_offer | FOREIGN KEY (rental_offer_id, rental_plan_id) REFERENCES rental_plans(rental_offer_id, rental_plan_id) ON DELETE RESTRICT | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-075 | rental_contracts | rental_offer_id | rental_offers | rental_offer_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_rental_contracts_rental_offer_id | FOREIGN KEY (rental_offer_id) REFERENCES rental_offers(rental_offer_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-076 | rental_contracts | rental_plan_id | rental_plans | rental_plan_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_rental_contracts_rental_plan_id | FOREIGN KEY (rental_plan_id) REFERENCES rental_plans(rental_plan_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-077 | rental_contracts | renter_user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE1 – An | Cross-owner | fk_rental_contracts_renter_user_id | FOREIGN KEY (renter_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-078 | rental_offers | model_version_id | model_versions | model_version_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_rental_offers_model_version_id | FOREIGN KEY (model_version_id) REFERENCES model_versions(model_version_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-079 | rental_offers | storefront_id | storefronts | storefront_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE1 – An | Cross-owner | fk_rental_offers_storefront_id | FOREIGN KEY (storefront_id) REFERENCES storefronts(storefront_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-080 | rental_plans | rental_offer_id | rental_offers | rental_offer_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_rental_plans_rental_offer_id | FOREIGN KEY (rental_offer_id) REFERENCES rental_offers(rental_offer_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-081 | reports | handled_by_user_id | users | user_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_reports_handled_by_user_id | FOREIGN KEY (handled_by_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-082 | reports | product_id | products | product_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_reports_product_id | FOREIGN KEY (product_id) REFERENCES products(product_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-083 | reports | rental_offer_id | rental_offers | rental_offer_id | N : 1 | Có thể NULL | BE1 – An | BE2 – Khang | Cross-owner | fk_reports_rental_offer_id | FOREIGN KEY (rental_offer_id) REFERENCES rental_offers(rental_offer_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-084 | reports | reported_user_id | users | user_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_reports_reported_user_id | FOREIGN KEY (reported_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-085 | reports | reporter_user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_reports_reporter_user_id | FOREIGN KEY (reporter_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-086 | review_merchant_replies | replied_by_user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | review_merchant_replies_replied_by_user_id_fkey | FOREIGN KEY (replied_by_user_id) REFERENCES users(user_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-087 | review_merchant_replies | review_id | reviews | review_id | 1 : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | review_merchant_replies_review_id_fkey | FOREIGN KEY (review_id) REFERENCES reviews(review_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-088 | reviews | physical_order_id, physical_order_item_id | physical_order_items | physical_order_id, physical_order_item_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_review_same_order_item | FOREIGN KEY (physical_order_id, physical_order_item_id) REFERENCES physical_order_items(physical_order_id, physical_order_item_id) | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-089 | reviews | physical_order_id | physical_orders | physical_order_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | reviews_physical_order_id_fkey | FOREIGN KEY (physical_order_id) REFERENCES physical_orders(physical_order_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-090 | reviews | physical_order_item_id | physical_order_items | physical_order_item_id | 1 : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | reviews_physical_order_item_id_fkey | FOREIGN KEY (physical_order_item_id) REFERENCES physical_order_items(physical_order_item_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-091 | reviews | product_id | products | product_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | reviews_product_id_fkey | FOREIGN KEY (product_id) REFERENCES products(product_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-092 | reviews | user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | reviews_user_id_fkey | FOREIGN KEY (user_id) REFERENCES users(user_id) | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-093 | seller_earnings | physical_order_id | physical_orders | physical_order_id | 1 : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE1 – An | Cross-owner | fk_seller_earnings_physical_order_id | FOREIGN KEY (physical_order_id) REFERENCES physical_orders(physical_order_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-094 | seller_earnings | seller_user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE1 – An | Cross-owner | fk_seller_earnings_seller_user_id | FOREIGN KEY (seller_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-095 | seller_earnings | wallet_id | wallets | wallet_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_seller_earnings_wallet_id | FOREIGN KEY (wallet_id) REFERENCES wallets(wallet_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-096 | seller_earnings | seller_user_id, wallet_id | wallets | user_id, wallet_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_seller_earnings_wallet_owner | FOREIGN KEY (seller_user_id, wallet_id) REFERENCES wallets(user_id, wallet_id) ON DELETE RESTRICT | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-097 | shipments | physical_order_id | physical_orders | physical_order_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_shipments_physical_order_id | FOREIGN KEY (physical_order_id) REFERENCES physical_orders(physical_order_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-098 | shipments | print_request_id | print_requests | print_request_id | N : 1 | Có thể NULL | BE1 – An | BE2 – Khang | Cross-owner | fk_shipments_print_request_id | FOREIGN KEY (print_request_id) REFERENCES print_requests(print_request_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-099 | storefront_subscriptions | storefront_id | storefronts | storefront_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_storefronts_subscription_storefront_id | FOREIGN KEY (storefront_id) REFERENCES storefronts(storefront_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-100 | storefronts | owner_user_id | users | user_id | 1 : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_storefronts_owner_user_id | FOREIGN KEY (owner_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-101 | transaction_attempts | transaction_id | transactions | transaction_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_attempt_transaction | FOREIGN KEY (transaction_id) REFERENCES transactions(transaction_id) ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-102 | transaction_attempts | verified_by_user_id | users | user_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_attempt_verified_user | FOREIGN KEY (verified_by_user_id) REFERENCES users(user_id) ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-103 | transactions | original_transaction_id | transactions | transaction_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_transactions_original_transaction_id | FOREIGN KEY (original_transaction_id) REFERENCES transactions(transaction_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-104 | transactions | payee_bank_account_id | user_bank_accounts | bank_account_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_transactions_payee_bank_account_id | FOREIGN KEY (payee_bank_account_id) REFERENCES user_bank_accounts(bank_account_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-105 | transactions | payee_user_id, payee_bank_account_id | user_bank_accounts | user_id, bank_account_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_transactions_payee_bank_owner | FOREIGN KEY (payee_user_id, payee_bank_account_id) REFERENCES user_bank_accounts(user_id, bank_account_id) ON DELETE RESTRICT | Composite FK: giữ đúng cùng model/offer/owner/order/request; không tách thành các FK độc lập.
FK-106 | transactions | payee_user_id | users | user_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_transactions_payee_user_id | FOREIGN KEY (payee_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-107 | transactions | payer_user_id | users | user_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_transactions_payer_user_id | FOREIGN KEY (payer_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-108 | transactions | physical_order_id | physical_orders | physical_order_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_transactions_physical_order_id | FOREIGN KEY (physical_order_id) REFERENCES physical_orders(physical_order_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-109 | transactions | print_quote_id | print_quotes | print_quote_id | N : 1 | Có thể NULL | BE1 – An | BE2 – Khang | Cross-owner | fk_transactions_print_quote_id | FOREIGN KEY (print_quote_id) REFERENCES print_quotes(print_quote_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-110 | transactions | print_request_id | print_requests | print_request_id | N : 1 | Có thể NULL | BE1 – An | BE2 – Khang | Cross-owner | fk_transactions_print_request_id | FOREIGN KEY (print_request_id) REFERENCES print_requests(print_request_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-111 | transactions | rental_contract_id | rental_contracts | rental_contract_id | N : 1 | Có thể NULL | BE1 – An | BE2 – Khang | Cross-owner | fk_transactions_rental_contract_id | FOREIGN KEY (rental_contract_id) REFERENCES rental_contracts(rental_contract_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-112 | transactions | requested_by_user_id | users | user_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_transactions_requested_by_user_id | FOREIGN KEY (requested_by_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-113 | transactions | reviewed_by_user_id | users | user_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_transactions_reviewed_by_user_id | FOREIGN KEY (reviewed_by_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-114 | transactions | storefront_subscription_id | storefront_subscriptions | subscription_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_transactions_storefront_subscription_id | FOREIGN KEY (storefront_subscription_id) REFERENCES storefront_subscriptions(subscription_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-115 | transactions | wallet_id | wallets | wallet_id | N : 1 | Có thể NULL | BE1 – An | BE2 – Khang | Cross-owner | fk_transactions_wallet_id | FOREIGN KEY (wallet_id) REFERENCES wallets(wallet_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-116 | user_addresses | user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_users_address_user_id | FOREIGN KEY (user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-117 | user_bank_accounts | user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_users_bank_account_user_id | FOREIGN KEY (user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-118 | user_roles | granted_by_user_id | users | user_id | N : 1 | Có thể NULL | BE1 – An | BE1 – An | Cùng owner | fk_users_role_granted_by_user_id | FOREIGN KEY (granted_by_user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-119 | user_roles | role_id | roles | role_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_users_role_role_id | FOREIGN KEY (role_id) REFERENCES roles(role_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-120 | user_roles | user_id | users | user_id | N : 1 | Bắt buộc hoặc composite-partial | BE1 – An | BE1 – An | Cùng owner | fk_users_role_user_id | FOREIGN KEY (user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-121 | wallet_ledgers | seller_earning_id | seller_earnings | earning_id | N : 1 | Có thể NULL | BE2 – Khang | BE2 – Khang | Cùng owner | fk_wallets_ledger_seller_earning_id | FOREIGN KEY (seller_earning_id) REFERENCES seller_earnings(earning_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-122 | wallet_ledgers | transaction_id | transactions | transaction_id | N : 1 | Có thể NULL | BE2 – Khang | BE1 – An | Cross-owner | fk_wallets_ledger_transaction_id | FOREIGN KEY (transaction_id) REFERENCES transactions(transaction_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.
FK-123 | wallet_ledgers | wallet_id | wallets | wallet_id | N : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE2 – Khang | Cùng owner | fk_wallets_ledger_wallet_id | FOREIGN KEY (wallet_id) REFERENCES wallets(wallet_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service.
FK-124 | wallets | user_id | users | user_id | 1 : 1 | Bắt buộc hoặc composite-partial | BE2 – Khang | BE1 – An | Cross-owner | fk_wallets_user_id | FOREIGN KEY (user_id) REFERENCES users(user_id) ON UPDATE RESTRICT ON DELETE RESTRICT | Bảo toàn FK; kiểm tra actor/ownership/lifecycle trong service. Gọi service/contract owner đích; không tạo duplicate Entity owner.

## Constraints
PK / UNIQUE / CHECK / indexes
Dùng sheet này khi viết Entity, idempotency và concurrency tests. Constraint không thay được ownership/authorization và workflow guard ở service.
Table | Type | Name | DDL definition | Owner
ai_requests | n | ai_requests_action_type_not_null | NOT NULL action_type | BE2 – Khang
ai_requests | n | ai_requests_ai_request_id_not_null | NOT NULL ai_request_id | BE2 – Khang
ai_requests | n | ai_requests_created_at_not_null | NOT NULL created_at | BE2 – Khang
ai_requests | n | ai_requests_credits_used_not_null | NOT NULL credits_used | BE2 – Khang
ai_requests | n | ai_requests_model_id_not_null | NOT NULL model_id | BE2 – Khang
ai_requests | PRIMARY KEY | ai_requests_pkey | PRIMARY KEY (ai_request_id) | BE2 – Khang
ai_requests | n | ai_requests_request_type_not_null | NOT NULL request_type | BE2 – Khang
ai_requests | n | ai_requests_status_not_null | NOT NULL status | BE2 – Khang
ai_requests | n | ai_requests_user_id_not_null | NOT NULL user_id | BE2 – Khang
ai_requests | CHECK | ck_ai_action | CHECK (((action_type)::text = ANY ((ARRAY['GENERATE'::character varying, 'REGENERATE'::character varying, 'REFINE'::character varying])::text[]))) | BE2 – Khang
ai_requests | CHECK | ck_ai_credit_nonnegative | CHECK ((credits_used >= 0)) | BE2 – Khang
ai_requests | CHECK | ck_ai_status | CHECK (((status)::text = ANY ((ARRAY['PENDING'::character varying, 'PROCESSING'::character varying, 'STORING'::character varying, 'SUCCESS'::character varying, 'FAILED'::character varying])::text[]))) | BE2 – Khang
audit_logs | n | audit_logs_action_type_not_null | NOT NULL action_type | BE1 – An
audit_logs | n | audit_logs_audit_log_id_not_null | NOT NULL audit_log_id | BE1 – An
audit_logs | n | audit_logs_created_at_not_null | NOT NULL created_at | BE1 – An
audit_logs | n | audit_logs_entity_id_not_null | NOT NULL entity_id | BE1 – An
audit_logs | n | audit_logs_entity_type_not_null | NOT NULL entity_type | BE1 – An
audit_logs | PRIMARY KEY | audit_logs_pkey | PRIMARY KEY (audit_log_id) | BE1 – An
cart_items | n | cart_items_added_at_not_null | NOT NULL added_at | BE1 – An
cart_items | n | cart_items_cart_id_not_null | NOT NULL cart_id | BE1 – An
cart_items | n | cart_items_cart_item_id_not_null | NOT NULL cart_item_id | BE1 – An
cart_items | PRIMARY KEY | cart_items_pkey | PRIMARY KEY (cart_item_id) | BE1 – An
cart_items | n | cart_items_quantity_not_null | NOT NULL quantity | BE1 – An
cart_items | n | cart_items_updated_at_not_null | NOT NULL updated_at | BE1 – An
cart_items | n | cart_items_variant_id_not_null | NOT NULL variant_id | BE1 – An
cart_items | CHECK | ck_cart_price | CHECK (((price_at_added IS NULL) OR (price_at_added >= (0)::numeric))) | BE1 – An
cart_items | CHECK | ck_cart_quantity | CHECK ((quantity > 0)) | BE1 – An
cart_items | UNIQUE | uq_cart_variant | UNIQUE (cart_id, variant_id) | BE1 – An
carts | n | carts_cart_id_not_null | NOT NULL cart_id | BE1 – An
carts | n | carts_created_at_not_null | NOT NULL created_at | BE1 – An
carts | PRIMARY KEY | carts_pkey | PRIMARY KEY (cart_id) | BE1 – An
carts | n | carts_updated_at_not_null | NOT NULL updated_at | BE1 – An
carts | UNIQUE | carts_user_id_key | UNIQUE (user_id) | BE1 – An
carts | n | carts_user_id_not_null | NOT NULL user_id | BE1 – An
model_files | CHECK | ck_model_file_role | CHECK (((file_role)::text = ANY ((ARRAY['EDITABLE_SCENE'::character varying, 'VIEWABLE_MODEL'::character varying, 'PRINT_MODEL'::character varying, 'SOURCE_MODEL'::character varying, 'PREVIEW'::character varying])::text[]))) | BE2 – Khang
model_files | CHECK | ck_model_file_size | CHECK (((file_size IS NULL) OR (file_size >= 0))) | BE2 – Khang
model_files | n | model_files_created_at_not_null | NOT NULL created_at | BE2 – Khang
model_files | n | model_files_file_format_not_null | NOT NULL file_format | BE2 – Khang
model_files | n | model_files_file_id_not_null | NOT NULL file_id | BE2 – Khang
model_files | n | model_files_file_role_not_null | NOT NULL file_role | BE2 – Khang
model_files | n | model_files_is_primary_not_null | NOT NULL is_primary | BE2 – Khang
model_files | n | model_files_model_version_id_not_null | NOT NULL model_version_id | BE2 – Khang
model_files | PRIMARY KEY | model_files_pkey | PRIMARY KEY (file_id) | BE2 – Khang
model_files | n | model_files_storage_key_not_null | NOT NULL storage_key | BE2 – Khang
model_versions | CHECK | ck_model_version_not_self_parent | CHECK (((parent_version_id IS NULL) OR (parent_version_id <> model_version_id))) | BE2 – Khang
model_versions | CHECK | ck_model_version_number | CHECK ((version_number > 0)) | BE2 – Khang
model_versions | CHECK | ck_model_version_source | CHECK (((((source_type)::text = 'AI_GENERATED'::text) AND (ai_request_id IS NOT NULL)) OR (((source_type)::text = ANY ((ARRAY['EDITOR_SAVE'::character varying, 'UPLOAD'::character varying])::text[])) AND (ai_request_id IS NULL)))) | BE2 – Khang
model_versions | UNIQUE | model_versions_ai_request_id_key | UNIQUE (ai_request_id) | BE2 – Khang
model_versions | n | model_versions_created_at_not_null | NOT NULL created_at | BE2 – Khang
model_versions | n | model_versions_created_by_user_id_not_null | NOT NULL created_by_user_id | BE2 – Khang
model_versions | n | model_versions_model_id_not_null | NOT NULL model_id | BE2 – Khang
model_versions | n | model_versions_model_version_id_not_null | NOT NULL model_version_id | BE2 – Khang
model_versions | PRIMARY KEY | model_versions_pkey | PRIMARY KEY (model_version_id) | BE2 – Khang
model_versions | n | model_versions_source_type_not_null | NOT NULL source_type | BE2 – Khang
model_versions | n | model_versions_version_number_not_null | NOT NULL version_number | BE2 – Khang
models_3d | CHECK | ck_model_origin | CHECK (((((model_type)::text = 'WEB_EDITOR'::text) AND ((origin_type)::text = ANY ((ARRAY['UPLOAD'::character varying, 'EDITOR'::character varying])::text[]))) OR (((model_type)::text = 'AI_GENERATOR'::text) AND ((origin_type)::text = 'AI'::text)))) | BE2 – Khang
models_3d | CHECK | ck_model_type | CHECK (((model_type)::text = ANY ((ARRAY['WEB_EDITOR'::character varying, 'AI_GENERATOR'::character varying])::text[]))) | BE2 – Khang
models_3d | n | models_3d_created_at_not_null | NOT NULL created_at | BE2 – Khang
models_3d | n | models_3d_model_id_not_null | NOT NULL model_id | BE2 – Khang
models_3d | n | models_3d_model_name_not_null | NOT NULL model_name | BE2 – Khang
models_3d | n | models_3d_model_type_not_null | NOT NULL model_type | BE2 – Khang
models_3d | n | models_3d_origin_type_not_null | NOT NULL origin_type | BE2 – Khang
models_3d | n | models_3d_owner_user_id_not_null | NOT NULL owner_user_id | BE2 – Khang
models_3d | PRIMARY KEY | models_3d_pkey | PRIMARY KEY (model_id) | BE2 – Khang
models_3d | n | models_3d_visibility_not_null | NOT NULL visibility | BE2 – Khang
notifications | n | notifications_created_at_not_null | NOT NULL created_at | BE2 – Khang
notifications | n | notifications_event_type_not_null | NOT NULL event_type | BE2 – Khang
notifications | n | notifications_is_read_not_null | NOT NULL is_read | BE2 – Khang
notifications | n | notifications_notification_id_not_null | NOT NULL notification_id | BE2 – Khang
notifications | PRIMARY KEY | notifications_pkey | PRIMARY KEY (notification_id) | BE2 – Khang
notifications | n | notifications_recipient_user_id_not_null | NOT NULL recipient_user_id | BE2 – Khang
notifications | n | notifications_title_not_null | NOT NULL title | BE2 – Khang
order_shipping_package_items | n | order_shipping_package_items_physical_order_id_not_null | NOT NULL physical_order_id | BE1 – An
order_shipping_package_items | n | order_shipping_package_items_physical_order_item_id_not_null | NOT NULL physical_order_item_id | BE1 – An
order_shipping_package_items | PRIMARY KEY | order_shipping_package_items_pkey | PRIMARY KEY (shipping_package_item_id) | BE1 – An
order_shipping_package_items | CHECK | order_shipping_package_items_product_height_cm_check | CHECK ((product_height_cm > (0)::numeric)) | BE1 – An
order_shipping_package_items | n | order_shipping_package_items_product_id_not_null | NOT NULL product_id | BE1 – An
order_shipping_package_items | CHECK | order_shipping_package_items_product_length_cm_check | CHECK ((product_length_cm > (0)::numeric)) | BE1 – An
order_shipping_package_items | CHECK | order_shipping_package_items_product_width_cm_check | CHECK ((product_width_cm > (0)::numeric)) | BE1 – An
order_shipping_package_items | CHECK | order_shipping_package_items_quantity_check | CHECK ((quantity > 0)) | BE1 – An
order_shipping_package_items | n | order_shipping_package_items_quantity_not_null | NOT NULL quantity | BE1 – An
order_shipping_package_items | n | order_shipping_package_items_shipping_package_id_not_null | NOT NULL shipping_package_id | BE1 – An
order_shipping_package_items | UNIQUE | order_shipping_package_items_shipping_package_id_physical_o_key | UNIQUE (shipping_package_id, physical_order_item_id) | BE1 – An
order_shipping_package_items | n | order_shipping_package_items_shipping_package_item_id_not_null | NOT NULL shipping_package_item_id | BE1 – An
order_shipping_package_items | n | order_shipping_package_items_variant_id_not_null | NOT NULL variant_id | BE1 – An
order_shipping_packages | CHECK | order_shipping_packages_actual_weight_grams_check | CHECK ((actual_weight_grams >= 0)) | BE1 – An
order_shipping_packages | CHECK | order_shipping_packages_box_cost_vnd_check | CHECK ((box_cost_vnd >= (0)::numeric)) | BE1 – An
order_shipping_packages | n | order_shipping_packages_box_cost_vnd_not_null | NOT NULL box_cost_vnd | BE1 – An
order_shipping_packages | n | order_shipping_packages_created_at_not_null | NOT NULL created_at | BE1 – An
order_shipping_packages | CHECK | order_shipping_packages_fragile_padding_applied_grams_check | CHECK ((fragile_padding_applied_grams >= 0)) | BE1 – An
order_shipping_packages | n | order_shipping_packages_fragile_padding_applied_grams_not_null | NOT NULL fragile_padding_applied_grams | BE1 – An
order_shipping_packages | CHECK | order_shipping_packages_fragile_padding_weight_grams_check | CHECK ((fragile_padding_weight_grams >= 0)) | BE1 – An
order_shipping_packages | n | order_shipping_packages_fragile_padding_weight_grams_not_null | NOT NULL fragile_padding_weight_grams | BE1 – An
order_shipping_packages | CHECK | order_shipping_packages_inner_height_cm_check | CHECK ((inner_height_cm > (0)::numeric)) | BE1 – An
order_shipping_packages | n | order_shipping_packages_inner_height_cm_not_null | NOT NULL inner_height_cm | BE1 – An
order_shipping_packages | CHECK | order_shipping_packages_inner_length_cm_check | CHECK ((inner_length_cm > (0)::numeric)) | BE1 – An
order_shipping_packages | n | order_shipping_packages_inner_length_cm_not_null | NOT NULL inner_length_cm | BE1 – An
order_shipping_packages | CHECK | order_shipping_packages_inner_width_cm_check | CHECK ((inner_width_cm > (0)::numeric)) | BE1 – An
order_shipping_packages | n | order_shipping_packages_inner_width_cm_not_null | NOT NULL inner_width_cm | BE1 – An
order_shipping_packages | CHECK | order_shipping_packages_internal_packaging_cost_vnd_check | CHECK ((internal_packaging_cost_vnd >= (0)::numeric)) | BE1 – An
order_shipping_packages | n | order_shipping_packages_internal_packaging_cost_vnd_not_null | NOT NULL internal_packaging_cost_vnd | BE1 – An
order_shipping_packages | CHECK | order_shipping_packages_max_product_weight_grams_check | CHECK ((max_product_weight_grams > 0)) | BE1 – An
order_shipping_packages | n | order_shipping_packages_max_product_weight_grams_not_null | NOT NULL max_product_weight_grams | BE1 – An
order_shipping_packages | UNIQUE | order_shipping_packages_package_code_key | UNIQUE (package_code) | BE1 – An
order_shipping_packages | n | order_shipping_packages_package_code_not_null | NOT NULL package_code | BE1 – An
order_shipping_packages | CHECK | order_shipping_packages_package_index_check | CHECK ((package_index > 0)) | BE1 – An
order_shipping_packages | n | order_shipping_packages_package_index_not_null | NOT NULL package_index | BE1 – An
order_shipping_packages | CHECK | order_shipping_packages_package_weight_grams_check | CHECK ((package_weight_grams >= 0)) | BE1 – An
order_shipping_packages | n | order_shipping_packages_package_weight_grams_not_null | NOT NULL package_weight_grams | BE1 – An
order_shipping_packages | CHECK | order_shipping_packages_packaging_weight_grams_check | CHECK ((packaging_weight_grams >= 0)) | BE1 – An
order_shipping_packages | n | order_shipping_packages_packaging_weight_grams_not_null | NOT NULL packaging_weight_grams | BE1 – An
order_shipping_packages | CHECK | order_shipping_packages_padding_cost_vnd_check | CHECK ((padding_cost_vnd >= (0)::numeric)) | BE1 – An
order_shipping_packages | n | order_shipping_packages_padding_cost_vnd_not_null | NOT NULL padding_cost_vnd | BE1 – An
order_shipping_packages | n | order_shipping_packages_physical_order_id_not_null | NOT NULL physical_order_id | BE1 – An
order_shipping_packages | UNIQUE | order_shipping_packages_physical_order_id_package_index_key | UNIQUE (physical_order_id, package_index) | BE1 – An
order_shipping_packages | UNIQUE | order_shipping_packages_physical_order_id_shipping_package__key | UNIQUE (physical_order_id, shipping_package_id) | BE1 – An
order_shipping_packages | PRIMARY KEY | order_shipping_packages_pkey | PRIMARY KEY (shipping_package_id) | BE1 – An
order_shipping_packages | CHECK | order_shipping_packages_product_weight_grams_check | CHECK ((product_weight_grams >= 0)) | BE1 – An
order_shipping_packages | n | order_shipping_packages_product_weight_grams_not_null | NOT NULL product_weight_grams | BE1 – An
order_shipping_packages | n | order_shipping_packages_profile_code_not_null | NOT NULL profile_code | BE1 – An
order_shipping_packages | n | order_shipping_packages_shipping_package_id_not_null | NOT NULL shipping_package_id | BE1 – An
order_status_history | n | order_status_history_changed_at_not_null | NOT NULL changed_at | BE1 – An
order_status_history | CHECK | order_status_history_check | CHECK (((from_status IS NULL) OR ((from_status)::text <> (to_status)::text))) | BE1 – An
order_status_history | n | order_status_history_order_status_history_id_not_null | NOT NULL order_status_history_id | BE1 – An
order_status_history | n | order_status_history_physical_order_id_not_null | NOT NULL physical_order_id | BE1 – An
order_status_history | PRIMARY KEY | order_status_history_pkey | PRIMARY KEY (order_status_history_id) | BE1 – An
order_status_history | UNIQUE | order_status_history_source_event_id_key | UNIQUE (source_event_id) | BE1 – An
order_status_history | n | order_status_history_to_status_not_null | NOT NULL to_status | BE1 – An
packaging_profiles | CHECK | packaging_profiles_allowed_packing_groups_check | CHECK ((jsonb_typeof(allowed_packing_groups) = 'array'::text)) | BE1 – An
packaging_profiles | n | packaging_profiles_allowed_packing_groups_not_null | NOT NULL allowed_packing_groups | BE1 – An
packaging_profiles | CHECK | packaging_profiles_box_cost_vnd_check | CHECK ((box_cost_vnd >= (0)::numeric)) | BE1 – An
packaging_profiles | n | packaging_profiles_box_cost_vnd_not_null | NOT NULL box_cost_vnd | BE1 – An
packaging_profiles | UNIQUE | packaging_profiles_code_key | UNIQUE (code) | BE1 – An
packaging_profiles | n | packaging_profiles_code_not_null | NOT NULL code | BE1 – An
packaging_profiles | n | packaging_profiles_created_at_not_null | NOT NULL created_at | BE1 – An
packaging_profiles | CHECK | packaging_profiles_fragile_padding_weight_grams_check | CHECK ((fragile_padding_weight_grams >= 0)) | BE1 – An
packaging_profiles | n | packaging_profiles_fragile_padding_weight_grams_not_null | NOT NULL fragile_padding_weight_grams | BE1 – An
packaging_profiles | CHECK | packaging_profiles_inner_height_cm_check | CHECK ((inner_height_cm > (0)::numeric)) | BE1 – An
packaging_profiles | n | packaging_profiles_inner_height_cm_not_null | NOT NULL inner_height_cm | BE1 – An
packaging_profiles | CHECK | packaging_profiles_inner_length_cm_check | CHECK ((inner_length_cm > (0)::numeric)) | BE1 – An
packaging_profiles | n | packaging_profiles_inner_length_cm_not_null | NOT NULL inner_length_cm | BE1 – An
packaging_profiles | CHECK | packaging_profiles_inner_width_cm_check | CHECK ((inner_width_cm > (0)::numeric)) | BE1 – An
packaging_profiles | n | packaging_profiles_inner_width_cm_not_null | NOT NULL inner_width_cm | BE1 – An
packaging_profiles | CHECK | packaging_profiles_max_product_weight_grams_check | CHECK ((max_product_weight_grams > 0)) | BE1 – An
packaging_profiles | n | packaging_profiles_max_product_weight_grams_not_null | NOT NULL max_product_weight_grams | BE1 – An
packaging_profiles | n | packaging_profiles_name_not_null | NOT NULL name | BE1 – An
packaging_profiles | CHECK | packaging_profiles_package_weight_grams_check | CHECK ((package_weight_grams >= 0)) | BE1 – An
packaging_profiles | n | packaging_profiles_package_weight_grams_not_null | NOT NULL package_weight_grams | BE1 – An
packaging_profiles | n | packaging_profiles_packaging_profile_id_not_null | NOT NULL packaging_profile_id | BE1 – An
packaging_profiles | CHECK | packaging_profiles_padding_cost_vnd_check | CHECK ((padding_cost_vnd >= (0)::numeric)) | BE1 – An
packaging_profiles | n | packaging_profiles_padding_cost_vnd_not_null | NOT NULL padding_cost_vnd | BE1 – An
packaging_profiles | PRIMARY KEY | packaging_profiles_pkey | PRIMARY KEY (packaging_profile_id) | BE1 – An
packaging_profiles | n | packaging_profiles_priority_not_null | NOT NULL priority | BE1 – An
packaging_profiles | CHECK | packaging_profiles_status_check | CHECK (((status)::text = ANY ((ARRAY['ACTIVE'::character varying, 'INACTIVE'::character varying])::text[]))) | BE1 – An
packaging_profiles | n | packaging_profiles_status_not_null | NOT NULL status | BE1 – An
packaging_profiles | n | packaging_profiles_supports_fragile_not_null | NOT NULL supports_fragile | BE1 – An
physical_order_items | CHECK | ck_order_item_qty | CHECK (((quantity > 0) AND (unit_price_snapshot >= (0)::numeric) AND (line_total >= (0)::numeric))) | BE1 – An
physical_order_items | n | physical_order_items_line_total_not_null | NOT NULL line_total | BE1 – An
physical_order_items | n | physical_order_items_physical_order_id_not_null | NOT NULL physical_order_id | BE1 – An
physical_order_items | n | physical_order_items_physical_order_item_id_not_null | NOT NULL physical_order_item_id | BE1 – An
physical_order_items | PRIMARY KEY | physical_order_items_pkey | PRIMARY KEY (physical_order_item_id) | BE1 – An
physical_order_items | n | physical_order_items_quantity_not_null | NOT NULL quantity | BE1 – An
physical_order_items | n | physical_order_items_sku_snapshot_not_null | NOT NULL sku_snapshot | BE1 – An
physical_order_items | n | physical_order_items_unit_price_snapshot_not_null | NOT NULL unit_price_snapshot | BE1 – An
physical_order_items | n | physical_order_items_variant_id_not_null | NOT NULL variant_id | BE1 – An
physical_order_items | UNIQUE | uq_order_items_order_item | UNIQUE (physical_order_id, physical_order_item_id) | BE1 – An
physical_orders | CHECK | ck_order_policies | CHECK ((((commission_rate_snapshot IS NULL) OR ((commission_rate_snapshot >= (0)::numeric) AND (commission_rate_snapshot <= (1)::numeric))) AND ((refund_window_hours_snapshot IS NULL) OR (refund_window_hours_snapshot >= 0)) AND ((auto_confirm_hours_snapshot IS NULL) OR (auto_confirm_hours_snapshot >= 0)) AND ((reservation_expires_at IS NULL) OR (reservation_expires_at > created_at)))) | BE1 – An
physical_orders | CHECK | ck_physical_amounts | CHECK (((subtotal >= (0)::numeric) AND (shipping_fee >= (0)::numeric) AND (total_amount >= (0)::numeric) AND (total_amount = (subtotal + shipping_fee)))) | BE1 – An
physical_orders | CHECK | ck_received_after_delivery | CHECK (((received_at IS NULL) OR (delivered_at IS NOT NULL))) | BE1 – An
physical_orders | CHECK | ck_reservation_state | CHECK (((reservation_status)::text = ANY ((ARRAY['NONE'::character varying, 'RESERVED'::character varying, 'CONSUMED'::character varying, 'RELEASED'::character varying, 'RESTOCKED'::character varying])::text[]))) | BE1 – An
physical_orders | CHECK | ck_shipping_snapshot | CHECK ((((shipping_package_count IS NULL) OR (shipping_package_count >= 0)) AND ((shipping_packaging_cost_vnd IS NULL) OR (shipping_packaging_cost_vnd >= (0)::numeric)) AND ((shipping_packaging_weight_grams IS NULL) OR (shipping_packaging_weight_grams >= 0)) AND ((shipping_product_weight_grams IS NULL) OR (shipping_product_weight_grams >= 0)) AND ((shipping_weight_grams IS NULL) OR (shipping_weight_grams >= 0)))) | BE1 – An
physical_orders | n | physical_orders_buyer_user_id_not_null | NOT NULL buyer_user_id | BE1 – An
physical_orders | n | physical_orders_created_at_not_null | NOT NULL created_at | BE1 – An
physical_orders | UNIQUE | physical_orders_order_code_key | UNIQUE (order_code) | BE1 – An
physical_orders | n | physical_orders_order_status_not_null | NOT NULL order_status | BE1 – An
physical_orders | n | physical_orders_physical_order_id_not_null | NOT NULL physical_order_id | BE1 – An
physical_orders | PRIMARY KEY | physical_orders_pkey | PRIMARY KEY (physical_order_id) | BE1 – An
physical_orders | n | physical_orders_reservation_status_not_null | NOT NULL reservation_status | BE1 – An
physical_orders | n | physical_orders_shipping_address_snapshot_not_null | NOT NULL shipping_address_snapshot | BE1 – An
physical_orders | n | physical_orders_shipping_fee_not_null | NOT NULL shipping_fee | BE1 – An
physical_orders | n | physical_orders_storefront_id_not_null | NOT NULL storefront_id | BE1 – An
physical_orders | n | physical_orders_subtotal_not_null | NOT NULL subtotal | BE1 – An
physical_orders | n | physical_orders_total_amount_not_null | NOT NULL total_amount | BE1 – An
platform_configs | n | platform_configs_config_id_not_null | NOT NULL config_id | BE1 – An
platform_configs | UNIQUE | platform_configs_config_key_key | UNIQUE (config_key) | BE1 – An
platform_configs | n | platform_configs_config_key_not_null | NOT NULL config_key | BE1 – An
platform_configs | n | platform_configs_config_value_not_null | NOT NULL config_value | BE1 – An
platform_configs | PRIMARY KEY | platform_configs_pkey | PRIMARY KEY (config_id) | BE1 – An
print_materials | CHECK | ck_material_cost | CHECK (((estimated_unit_cost IS NULL) OR (estimated_unit_cost >= (0)::numeric))) | BE2 – Khang
print_materials | n | print_materials_is_active_not_null | NOT NULL is_active | BE2 – Khang
print_materials | n | print_materials_material_id_not_null | NOT NULL material_id | BE2 – Khang
print_materials | n | print_materials_material_name_not_null | NOT NULL material_name | BE2 – Khang
print_materials | PRIMARY KEY | print_materials_pkey | PRIMARY KEY (material_id) | BE2 – Khang
print_materials | n | print_materials_technology_code_not_null | NOT NULL technology_code | BE2 – Khang
print_quote_items | CHECK | ck_print_quote_line | CHECK (((quantity_snapshot > 0) AND (material_cost_snapshot >= (0)::numeric) AND (labor_cost_snapshot >= (0)::numeric) AND (option_fee_snapshot >= (0)::numeric) AND (line_total >= (0)::numeric))) | BE2 – Khang
print_quote_items | n | print_quote_items_file_reference_snapshot_not_null | NOT NULL file_reference_snapshot | BE2 – Khang
print_quote_items | n | print_quote_items_labor_cost_snapshot_not_null | NOT NULL labor_cost_snapshot | BE2 – Khang
print_quote_items | n | print_quote_items_line_total_not_null | NOT NULL line_total | BE2 – Khang
print_quote_items | n | print_quote_items_material_cost_snapshot_not_null | NOT NULL material_cost_snapshot | BE2 – Khang
print_quote_items | n | print_quote_items_option_fee_snapshot_not_null | NOT NULL option_fee_snapshot | BE2 – Khang
print_quote_items | PRIMARY KEY | print_quote_items_pkey | PRIMARY KEY (print_quote_item_id) | BE2 – Khang
print_quote_items | n | print_quote_items_print_quote_id_not_null | NOT NULL print_quote_id | BE2 – Khang
print_quote_items | n | print_quote_items_print_quote_item_id_not_null | NOT NULL print_quote_item_id | BE2 – Khang
print_quote_items | n | print_quote_items_print_request_item_id_not_null | NOT NULL print_request_item_id | BE2 – Khang
print_quote_items | n | print_quote_items_quantity_snapshot_not_null | NOT NULL quantity_snapshot | BE2 – Khang
print_quote_items | n | print_quote_items_specification_snapshot_not_null | NOT NULL specification_snapshot | BE2 – Khang
print_quotes | CHECK | ck_print_quote_amounts | CHECK (((total_amount >= (0)::numeric) AND (deposit_amount >= (0)::numeric) AND (remaining_amount >= (0)::numeric) AND (total_amount = (deposit_amount + remaining_amount)))) | BE2 – Khang
print_quotes | CHECK | ck_print_quote_version | CHECK ((version_number > 0)) | BE2 – Khang
print_quotes | n | print_quotes_deposit_amount_not_null | NOT NULL deposit_amount | BE2 – Khang
print_quotes | n | print_quotes_expires_at_not_null | NOT NULL expires_at | BE2 – Khang
print_quotes | PRIMARY KEY | print_quotes_pkey | PRIMARY KEY (print_quote_id) | BE2 – Khang
print_quotes | n | print_quotes_print_quote_id_not_null | NOT NULL print_quote_id | BE2 – Khang
print_quotes | n | print_quotes_print_request_id_not_null | NOT NULL print_request_id | BE2 – Khang
print_quotes | n | print_quotes_quote_status_not_null | NOT NULL quote_status | BE2 – Khang
print_quotes | n | print_quotes_quoted_by_user_id_not_null | NOT NULL quoted_by_user_id | BE2 – Khang
print_quotes | n | print_quotes_remaining_amount_not_null | NOT NULL remaining_amount | BE2 – Khang
print_quotes | n | print_quotes_total_amount_not_null | NOT NULL total_amount | BE2 – Khang
print_quotes | n | print_quotes_version_number_not_null | NOT NULL version_number | BE2 – Khang
print_quotes | UNIQUE | uq_quote_request_quote | UNIQUE (print_request_id, print_quote_id) | BE2 – Khang
print_request_file_versions | n | print_request_file_versions_file_name_not_null | NOT NULL file_name | BE2 – Khang
print_request_file_versions | CHECK | print_request_file_versions_file_size_check | CHECK ((file_size >= 0)) | BE2 – Khang
print_request_file_versions | n | print_request_file_versions_file_size_not_null | NOT NULL file_size | BE2 – Khang
print_request_file_versions | n | print_request_file_versions_file_type_not_null | NOT NULL file_type | BE2 – Khang
print_request_file_versions | n | print_request_file_versions_file_url_not_null | NOT NULL file_url | BE2 – Khang
print_request_file_versions | n | print_request_file_versions_file_version_id_not_null | NOT NULL file_version_id | BE2 – Khang
print_request_file_versions | PRIMARY KEY | print_request_file_versions_pkey | PRIMARY KEY (file_version_id) | BE2 – Khang
print_request_file_versions | n | print_request_file_versions_print_request_id_not_null | NOT NULL print_request_id | BE2 – Khang
print_request_file_versions | UNIQUE | print_request_file_versions_print_request_id_version_key | UNIQUE (print_request_id, version) | BE2 – Khang
print_request_file_versions | n | print_request_file_versions_uploaded_at_not_null | NOT NULL uploaded_at | BE2 – Khang
print_request_file_versions | n | print_request_file_versions_uploaded_by_user_id_not_null | NOT NULL uploaded_by_user_id | BE2 – Khang
print_request_file_versions | CHECK | print_request_file_versions_version_check | CHECK ((version > 0)) | BE2 – Khang
print_request_file_versions | n | print_request_file_versions_version_not_null | NOT NULL version | BE2 – Khang
print_request_items | CHECK | ck_pod_dims | CHECK ((((width_mm IS NULL) OR (width_mm > (0)::numeric)) AND ((height_mm IS NULL) OR (height_mm > (0)::numeric)) AND ((depth_mm IS NULL) OR (depth_mm > (0)::numeric)))) | BE2 – Khang
print_request_items | CHECK | ck_pod_infill | CHECK (((infill_percent IS NULL) OR ((infill_percent >= 0) AND (infill_percent <= 100)))) | BE2 – Khang
print_request_items | CHECK | ck_pod_quantity | CHECK ((quantity > 0)) | BE2 – Khang
print_request_items | CHECK | ck_pod_source_xor | CHECK ((num_nonnulls(model_version_id, uploaded_file_key) = 1)) | BE2 – Khang
print_request_items | n | print_request_items_material_id_not_null | NOT NULL material_id | BE2 – Khang
print_request_items | PRIMARY KEY | print_request_items_pkey | PRIMARY KEY (print_request_item_id) | BE2 – Khang
print_request_items | n | print_request_items_print_request_id_not_null | NOT NULL print_request_id | BE2 – Khang
print_request_items | n | print_request_items_print_request_item_id_not_null | NOT NULL print_request_item_id | BE2 – Khang
print_request_items | n | print_request_items_production_status_not_null | NOT NULL production_status | BE2 – Khang
print_request_items | n | print_request_items_quantity_not_null | NOT NULL quantity | BE2 – Khang
print_request_spec_versions | n | print_request_spec_versions_created_at_not_null | NOT NULL created_at | BE2 – Khang
print_request_spec_versions | n | print_request_spec_versions_created_by_user_id_not_null | NOT NULL created_by_user_id | BE2 – Khang
print_request_spec_versions | PRIMARY KEY | print_request_spec_versions_pkey | PRIMARY KEY (spec_version_id) | BE2 – Khang
print_request_spec_versions | n | print_request_spec_versions_print_request_id_not_null | NOT NULL print_request_id | BE2 – Khang
print_request_spec_versions | UNIQUE | print_request_spec_versions_print_request_id_version_key | UNIQUE (print_request_id, version) | BE2 – Khang
print_request_spec_versions | n | print_request_spec_versions_spec_version_id_not_null | NOT NULL spec_version_id | BE2 – Khang
print_request_spec_versions | CHECK | print_request_spec_versions_specification_data_check | CHECK ((jsonb_typeof(specification_data) = 'object'::text)) | BE2 – Khang
print_request_spec_versions | n | print_request_spec_versions_specification_data_not_null | NOT NULL specification_data | BE2 – Khang
print_request_spec_versions | CHECK | print_request_spec_versions_version_check | CHECK ((version > 0)) | BE2 – Khang
print_request_spec_versions | n | print_request_spec_versions_version_not_null | NOT NULL version | BE2 – Khang
print_request_status_history | n | print_request_status_history_changed_at_not_null | NOT NULL changed_at | BE2 – Khang
print_request_status_history | CHECK | print_request_status_history_check | CHECK (((from_status IS NULL) OR ((from_status)::text <> (to_status)::text))) | BE2 – Khang
print_request_status_history | PRIMARY KEY | print_request_status_history_pkey | PRIMARY KEY (print_status_history_id) | BE2 – Khang
print_request_status_history | n | print_request_status_history_print_request_id_not_null | NOT NULL print_request_id | BE2 – Khang
print_request_status_history | n | print_request_status_history_print_status_history_id_not_null | NOT NULL print_status_history_id | BE2 – Khang
print_request_status_history | UNIQUE | print_request_status_history_source_event_id_key | UNIQUE (source_event_id) | BE2 – Khang
print_request_status_history | n | print_request_status_history_to_status_not_null | NOT NULL to_status | BE2 – Khang
print_request_technical_reviews | n | print_request_technical_reviews_created_at_not_null | NOT NULL created_at | BE2 – Khang
print_request_technical_reviews | PRIMARY KEY | print_request_technical_reviews_pkey | PRIMARY KEY (technical_review_id) | BE2 – Khang
print_request_technical_reviews | n | print_request_technical_reviews_print_request_id_not_null | NOT NULL print_request_id | BE2 – Khang
print_request_technical_reviews | CHECK | print_request_technical_reviews_review_data_check | CHECK ((jsonb_typeof(review_data) = 'object'::text)) | BE2 – Khang
print_request_technical_reviews | n | print_request_technical_reviews_review_data_not_null | NOT NULL review_data | BE2 – Khang
print_request_technical_reviews | n | print_request_technical_reviews_reviewer_user_id_not_null | NOT NULL reviewer_user_id | BE2 – Khang
print_request_technical_reviews | n | print_request_technical_reviews_technical_review_id_not_null | NOT NULL technical_review_id | BE2 – Khang
print_requests | n | print_requests_copyright_confirmed_not_null | NOT NULL copyright_confirmed | BE2 – Khang
print_requests | n | print_requests_created_at_not_null | NOT NULL created_at | BE2 – Khang
print_requests | n | print_requests_customer_user_id_not_null | NOT NULL customer_user_id | BE2 – Khang
print_requests | PRIMARY KEY | print_requests_pkey | PRIMARY KEY (print_request_id) | BE2 – Khang
print_requests | n | print_requests_preview_confirmed_not_null | NOT NULL preview_confirmed | BE2 – Khang
print_requests | n | print_requests_print_request_id_not_null | NOT NULL print_request_id | BE2 – Khang
print_requests | n | print_requests_status_not_null | NOT NULL status | BE2 – Khang
product_media | n | product_media_created_at_not_null | NOT NULL created_at | BE1 – An
product_media | n | product_media_media_id_not_null | NOT NULL media_id | BE1 – An
product_media | n | product_media_media_url_not_null | NOT NULL media_url | BE1 – An
product_media | PRIMARY KEY | product_media_pkey | PRIMARY KEY (media_id) | BE1 – An
product_media | n | product_media_product_id_not_null | NOT NULL product_id | BE1 – An
product_media | n | product_media_sort_order_not_null | NOT NULL sort_order | BE1 – An
product_variants | CHECK | ck_variant_positive_price | CHECK ((unit_price >= (0)::numeric)) | BE1 – An
product_variants | CHECK | ck_variant_shipping | CHECK (((low_stock_threshold >= 0) AND ((product_weight_grams IS NULL) OR (product_weight_grams > 0)) AND ((product_length_cm IS NULL) OR (product_length_cm > (0)::numeric)) AND ((product_width_cm IS NULL) OR (product_width_cm > (0)::numeric)) AND ((product_height_cm IS NULL) OR (product_height_cm > (0)::numeric)))) | BE1 – An
product_variants | CHECK | ck_variant_stock | CHECK (((stock_quantity >= 0) AND (reserved_quantity >= 0) AND (reserved_quantity <= stock_quantity))) | BE1 – An
product_variants | n | product_variants_fragile_not_null | NOT NULL fragile | BE1 – An
product_variants | n | product_variants_is_active_not_null | NOT NULL is_active | BE1 – An
product_variants | n | product_variants_low_stock_threshold_not_null | NOT NULL low_stock_threshold | BE1 – An
product_variants | PRIMARY KEY | product_variants_pkey | PRIMARY KEY (variant_id) | BE1 – An
product_variants | n | product_variants_product_id_not_null | NOT NULL product_id | BE1 – An
product_variants | n | product_variants_reserved_quantity_not_null | NOT NULL reserved_quantity | BE1 – An
product_variants | UNIQUE | product_variants_sku_key | UNIQUE (sku) | BE1 – An
product_variants | n | product_variants_sku_not_null | NOT NULL sku | BE1 – An
product_variants | n | product_variants_status_not_null | NOT NULL status | BE1 – An
product_variants | n | product_variants_stock_quantity_not_null | NOT NULL stock_quantity | BE1 – An
product_variants | n | product_variants_unit_price_not_null | NOT NULL unit_price | BE1 – An
product_variants | n | product_variants_variant_id_not_null | NOT NULL variant_id | BE1 – An
product_variants | UNIQUE | uq_variants_product_variant | UNIQUE (product_id, variant_id) | BE1 – An
products | CHECK | ck_product_stats | CHECK ((((base_price IS NULL) OR (base_price >= (0)::numeric)) AND ((average_rating >= (0)::numeric) AND (average_rating <= (5)::numeric)) AND (review_count >= 0) AND (sales_count >= 0))) | BE1 – An
products | n | products_average_rating_not_null | NOT NULL average_rating | BE1 – An
products | n | products_created_at_not_null | NOT NULL created_at | BE1 – An
products | PRIMARY KEY | products_pkey | PRIMARY KEY (product_id) | BE1 – An
products | n | products_product_id_not_null | NOT NULL product_id | BE1 – An
products | n | products_review_count_not_null | NOT NULL review_count | BE1 – An
products | n | products_sales_count_not_null | NOT NULL sales_count | BE1 – An
products | n | products_status_not_null | NOT NULL status | BE1 – An
products | n | products_storefront_id_not_null | NOT NULL storefront_id | BE1 – An
products | n | products_title_not_null | NOT NULL title | BE1 – An
refund_request_items | CHECK | refund_request_items_check | CHECK ((defective_quantity <= quantity)) | BE1 – An
refund_request_items | CHECK | refund_request_items_defective_quantity_check | CHECK ((defective_quantity >= 0)) | BE1 – An
refund_request_items | n | refund_request_items_defective_quantity_not_null | NOT NULL defective_quantity | BE1 – An
refund_request_items | n | refund_request_items_physical_order_item_id_not_null | NOT NULL physical_order_item_id | BE1 – An
refund_request_items | PRIMARY KEY | refund_request_items_pkey | PRIMARY KEY (refund_request_item_id) | BE1 – An
refund_request_items | n | refund_request_items_product_id_not_null | NOT NULL product_id | BE1 – An
refund_request_items | CHECK | refund_request_items_quantity_check | CHECK ((quantity > 0)) | BE1 – An
refund_request_items | n | refund_request_items_quantity_not_null | NOT NULL quantity | BE1 – An
refund_request_items | CHECK | refund_request_items_refund_price_check | CHECK ((refund_price >= (0)::numeric)) | BE1 – An
refund_request_items | n | refund_request_items_refund_price_not_null | NOT NULL refund_price | BE1 – An
refund_request_items | n | refund_request_items_refund_request_id_not_null | NOT NULL refund_request_id | BE1 – An
refund_request_items | UNIQUE | refund_request_items_refund_request_id_physical_order_item__key | UNIQUE (refund_request_id, physical_order_item_id) | BE1 – An
refund_request_items | n | refund_request_items_refund_request_item_id_not_null | NOT NULL refund_request_item_id | BE1 – An
refund_request_items | n | refund_request_items_sku_not_null | NOT NULL sku | BE1 – An
refund_requests | CHECK | refund_requests_check | CHECK ((((status)::text <> 'REJECTED'::text) OR (NULLIF(btrim(decision_reason), ''::text) IS NOT NULL))) | BE1 – An
refund_requests | n | refund_requests_created_at_not_null | NOT NULL created_at | BE1 – An
refund_requests | n | refund_requests_customer_user_id_not_null | NOT NULL customer_user_id | BE1 – An
refund_requests | CHECK | refund_requests_evidence_check | CHECK ((jsonb_typeof(evidence) = 'array'::text)) | BE1 – An
refund_requests | n | refund_requests_evidence_not_null | NOT NULL evidence | BE1 – An
refund_requests | UNIQUE | refund_requests_idempotency_key_key | UNIQUE (idempotency_key) | BE1 – An
refund_requests | n | refund_requests_idempotency_key_not_null | NOT NULL idempotency_key | BE1 – An
refund_requests | PRIMARY KEY | refund_requests_pkey | PRIMARY KEY (refund_request_id) | BE1 – An
refund_requests | n | refund_requests_reason_not_null | NOT NULL reason | BE1 – An
refund_requests | CHECK | refund_requests_refund_amount_check | CHECK ((refund_amount > (0)::numeric)) | BE1 – An
refund_requests | n | refund_requests_refund_amount_not_null | NOT NULL refund_amount | BE1 – An
refund_requests | n | refund_requests_refund_request_id_not_null | NOT NULL refund_request_id | BE1 – An
refund_requests | CHECK | refund_requests_source_id_check | CHECK ((source_id > 0)) | BE1 – An
refund_requests | n | refund_requests_source_id_not_null | NOT NULL source_id | BE1 – An
refund_requests | CHECK | refund_requests_source_type_check | CHECK (((source_type)::text = ANY ((ARRAY['PHYSICAL_ORDER'::character varying, 'POD'::character varying, 'RENTAL'::character varying, 'SUBSCRIPTION'::character varying])::text[]))) | BE1 – An
refund_requests | n | refund_requests_source_type_not_null | NOT NULL source_type | BE1 – An
refund_requests | CHECK | refund_requests_status_check | CHECK (((status)::text = ANY ((ARRAY['REQUESTED'::character varying, 'REVIEWING'::character varying, 'APPROVED'::character varying, 'REJECTED'::character varying, 'PROCESSING'::character varying, 'SUCCESS'::character varying, 'FAILED'::character varying, 'UNKNOWN'::character varying, 'CANCELLED'::character varying])::text[]))) | BE1 – An
refund_requests | n | refund_requests_status_not_null | NOT NULL status | BE1 – An
refund_requests | n | refund_requests_transaction_id_not_null | NOT NULL transaction_id | BE1 – An
rental_contracts | CHECK | ck_rental_dates | CHECK (((start_at IS NULL) OR (end_at IS NULL) OR (end_at > start_at))) | BE2 – Khang
rental_contracts | CHECK | ck_rental_not_self | CHECK ((renter_user_id <> designer_user_id)) | BE2 – Khang
rental_contracts | CHECK | ck_rental_price | CHECK ((price_snapshot >= (0)::numeric)) | BE2 – Khang
rental_contracts | n | rental_contracts_allow_download_snapshot_not_null | NOT NULL allow_download_snapshot | BE2 – Khang
rental_contracts | n | rental_contracts_allow_print_snapshot_not_null | NOT NULL allow_print_snapshot | BE2 – Khang
rental_contracts | n | rental_contracts_allow_view_snapshot_not_null | NOT NULL allow_view_snapshot | BE2 – Khang
rental_contracts | n | rental_contracts_created_at_not_null | NOT NULL created_at | BE2 – Khang
rental_contracts | n | rental_contracts_designer_user_id_not_null | NOT NULL designer_user_id | BE2 – Khang
rental_contracts | n | rental_contracts_license_accepted_at_not_null | NOT NULL license_accepted_at | BE2 – Khang
rental_contracts | n | rental_contracts_license_terms_snapshot_not_null | NOT NULL license_terms_snapshot | BE2 – Khang
rental_contracts | n | rental_contracts_model_version_id_not_null | NOT NULL model_version_id | BE2 – Khang
rental_contracts | PRIMARY KEY | rental_contracts_pkey | PRIMARY KEY (rental_contract_id) | BE2 – Khang
rental_contracts | n | rental_contracts_price_snapshot_not_null | NOT NULL price_snapshot | BE2 – Khang
rental_contracts | n | rental_contracts_rental_contract_id_not_null | NOT NULL rental_contract_id | BE2 – Khang
rental_contracts | n | rental_contracts_rental_offer_id_not_null | NOT NULL rental_offer_id | BE2 – Khang
rental_contracts | n | rental_contracts_rental_plan_id_not_null | NOT NULL rental_plan_id | BE2 – Khang
rental_contracts | n | rental_contracts_renter_user_id_not_null | NOT NULL renter_user_id | BE2 – Khang
rental_contracts | n | rental_contracts_status_not_null | NOT NULL status | BE2 – Khang
rental_offers | n | rental_offers_created_at_not_null | NOT NULL created_at | BE2 – Khang
rental_offers | n | rental_offers_model_version_id_not_null | NOT NULL model_version_id | BE2 – Khang
rental_offers | PRIMARY KEY | rental_offers_pkey | PRIMARY KEY (rental_offer_id) | BE2 – Khang
rental_offers | n | rental_offers_rental_offer_id_not_null | NOT NULL rental_offer_id | BE2 – Khang
rental_offers | n | rental_offers_status_not_null | NOT NULL status | BE2 – Khang
rental_offers | n | rental_offers_storefront_id_not_null | NOT NULL storefront_id | BE2 – Khang
rental_offers | n | rental_offers_title_not_null | NOT NULL title | BE2 – Khang
rental_plans | CHECK | ck_rental_price_duration | CHECK (((duration_days > 0) AND (price >= (0)::numeric))) | BE2 – Khang
rental_plans | n | rental_plans_allow_download_not_null | NOT NULL allow_download | BE2 – Khang
rental_plans | n | rental_plans_allow_print_not_null | NOT NULL allow_print | BE2 – Khang
rental_plans | n | rental_plans_allow_view_not_null | NOT NULL allow_view | BE2 – Khang
rental_plans | n | rental_plans_duration_days_not_null | NOT NULL duration_days | BE2 – Khang
rental_plans | n | rental_plans_is_active_not_null | NOT NULL is_active | BE2 – Khang
rental_plans | n | rental_plans_license_terms_not_null | NOT NULL license_terms | BE2 – Khang
rental_plans | PRIMARY KEY | rental_plans_pkey | PRIMARY KEY (rental_plan_id) | BE2 – Khang
rental_plans | n | rental_plans_price_not_null | NOT NULL price | BE2 – Khang
rental_plans | n | rental_plans_rental_offer_id_not_null | NOT NULL rental_offer_id | BE2 – Khang
rental_plans | n | rental_plans_rental_plan_id_not_null | NOT NULL rental_plan_id | BE2 – Khang
reports | CHECK | ck_report_has_target | CHECK ((num_nonnulls(product_id, rental_offer_id, reported_user_id) >= 1)) | BE1 – An
reports | n | reports_created_at_not_null | NOT NULL created_at | BE1 – An
reports | PRIMARY KEY | reports_pkey | PRIMARY KEY (report_id) | BE1 – An
reports | n | reports_report_id_not_null | NOT NULL report_id | BE1 – An
reports | n | reports_report_reason_not_null | NOT NULL report_reason | BE1 – An
reports | n | reports_reporter_user_id_not_null | NOT NULL reporter_user_id | BE1 – An
reports | n | reports_status_not_null | NOT NULL status | BE1 – An
review_merchant_replies | CHECK | review_merchant_replies_content_check | CHECK ((btrim(content) <> ''::text)) | BE1 – An
review_merchant_replies | n | review_merchant_replies_content_not_null | NOT NULL content | BE1 – An
review_merchant_replies | PRIMARY KEY | review_merchant_replies_pkey | PRIMARY KEY (reply_id) | BE1 – An
review_merchant_replies | n | review_merchant_replies_replied_at_not_null | NOT NULL replied_at | BE1 – An
review_merchant_replies | n | review_merchant_replies_replied_by_user_id_not_null | NOT NULL replied_by_user_id | BE1 – An
review_merchant_replies | n | review_merchant_replies_reply_id_not_null | NOT NULL reply_id | BE1 – An
review_merchant_replies | UNIQUE | review_merchant_replies_review_id_key | UNIQUE (review_id) | BE1 – An
review_merchant_replies | n | review_merchant_replies_review_id_not_null | NOT NULL review_id | BE1 – An
reviews | n | reviews_created_at_not_null | NOT NULL created_at | BE1 – An
reviews | CHECK | reviews_images_check | CHECK ((jsonb_typeof(images) = 'array'::text)) | BE1 – An
reviews | n | reviews_images_not_null | NOT NULL images | BE1 – An
reviews | n | reviews_physical_order_id_not_null | NOT NULL physical_order_id | BE1 – An
reviews | UNIQUE | reviews_physical_order_item_id_key | UNIQUE (physical_order_item_id) | BE1 – An
reviews | n | reviews_physical_order_item_id_not_null | NOT NULL physical_order_item_id | BE1 – An
reviews | PRIMARY KEY | reviews_pkey | PRIMARY KEY (review_id) | BE1 – An
reviews | n | reviews_product_id_not_null | NOT NULL product_id | BE1 – An
reviews | CHECK | reviews_rating_check | CHECK (((rating >= 1) AND (rating <= 5))) | BE1 – An
reviews | n | reviews_rating_not_null | NOT NULL rating | BE1 – An
reviews | n | reviews_review_id_not_null | NOT NULL review_id | BE1 – An
reviews | CHECK | reviews_status_check | CHECK (((status)::text = ANY ((ARRAY['PENDING'::character varying, 'PUBLISHED'::character varying, 'HIDDEN'::character varying, 'REJECTED'::character varying])::text[]))) | BE1 – An
reviews | n | reviews_status_not_null | NOT NULL status | BE1 – An
reviews | n | reviews_user_id_not_null | NOT NULL user_id | BE1 – An
roles | CHECK | ck_role_code | CHECK (((role_code)::text = ANY ((ARRAY['CUSTOMER'::character varying, 'SELLER'::character varying, 'DESIGNER'::character varying, 'PRINT_STAFF'::character varying, 'ADMIN'::character varying])::text[]))) | BE1 – An
roles | n | roles_created_at_not_null | NOT NULL created_at | BE1 – An
roles | n | roles_is_internal_not_null | NOT NULL is_internal | BE1 – An
roles | PRIMARY KEY | roles_pkey | PRIMARY KEY (role_id) | BE1 – An
roles | UNIQUE | roles_role_code_key | UNIQUE (role_code) | BE1 – An
roles | n | roles_role_code_not_null | NOT NULL role_code | BE1 – An
roles | n | roles_role_id_not_null | NOT NULL role_id | BE1 – An
roles | n | roles_role_name_not_null | NOT NULL role_name | BE1 – An
seller_earnings | CHECK | ck_earning_amounts | CHECK (((gross_amount >= (0)::numeric) AND (commission_amount >= (0)::numeric) AND (net_amount >= (0)::numeric) AND ((commission_rate_snapshot >= (0)::numeric) AND (commission_rate_snapshot <= (1)::numeric)) AND (commission_amount <= gross_amount) AND (net_amount = (gross_amount - commission_amount)))) | BE2 – Khang
seller_earnings | CHECK | ck_earning_sandbox | CHECK (((environment)::text = 'SANDBOX'::text)) | BE2 – Khang
seller_earnings | CHECK | ck_earning_status | CHECK (((earning_status)::text = ANY ((ARRAY['AWAITING_FUNDS'::character varying, 'PENDING'::character varying, 'HELD'::character varying, 'RELEASED'::character varying, 'VOID'::character varying, 'REFUNDED'::character varying])::text[]))) | BE2 – Khang
seller_earnings | n | seller_earnings_commission_amount_not_null | NOT NULL commission_amount | BE2 – Khang
seller_earnings | n | seller_earnings_commission_rate_snapshot_not_null | NOT NULL commission_rate_snapshot | BE2 – Khang
seller_earnings | n | seller_earnings_created_at_not_null | NOT NULL created_at | BE2 – Khang
seller_earnings | n | seller_earnings_earning_id_not_null | NOT NULL earning_id | BE2 – Khang
seller_earnings | n | seller_earnings_earning_status_not_null | NOT NULL earning_status | BE2 – Khang
seller_earnings | n | seller_earnings_environment_not_null | NOT NULL environment | BE2 – Khang
seller_earnings | n | seller_earnings_gross_amount_not_null | NOT NULL gross_amount | BE2 – Khang
seller_earnings | n | seller_earnings_net_amount_not_null | NOT NULL net_amount | BE2 – Khang
seller_earnings | UNIQUE | seller_earnings_physical_order_id_key | UNIQUE (physical_order_id) | BE2 – Khang
seller_earnings | n | seller_earnings_physical_order_id_not_null | NOT NULL physical_order_id | BE2 – Khang
seller_earnings | PRIMARY KEY | seller_earnings_pkey | PRIMARY KEY (earning_id) | BE2 – Khang
seller_earnings | n | seller_earnings_seller_user_id_not_null | NOT NULL seller_user_id | BE2 – Khang
seller_earnings | n | seller_earnings_wallet_id_not_null | NOT NULL wallet_id | BE2 – Khang
shipments | CHECK | ck_shipment_parent_xor | CHECK ((num_nonnulls(physical_order_id, print_request_id) = 1)) | BE1 – An
shipments | n | shipments_created_at_not_null | NOT NULL created_at | BE1 – An
shipments | PRIMARY KEY | shipments_pkey | PRIMARY KEY (shipment_id) | BE1 – An
shipments | n | shipments_shipment_id_not_null | NOT NULL shipment_id | BE1 – An
shipments | n | shipments_status_not_null | NOT NULL status | BE1 – An
storefront_subscriptions | CHECK | ck_subscription_dates | CHECK (((start_at IS NULL) OR (end_at IS NULL) OR (end_at > start_at))) | BE1 – An
storefront_subscriptions | CHECK | ck_subscription_fee | CHECK ((fee_snapshot >= (0)::numeric)) | BE1 – An
storefront_subscriptions | CHECK | ck_subscription_status | CHECK (((status)::text = ANY ((ARRAY['PENDING_PAYMENT'::character varying, 'ACTIVE'::character varying, 'EXPIRED'::character varying, 'CANCELLED'::character varying])::text[]))) | BE1 – An
storefront_subscriptions | n | storefront_subscriptions_created_at_not_null | NOT NULL created_at | BE1 – An
storefront_subscriptions | n | storefront_subscriptions_fee_snapshot_not_null | NOT NULL fee_snapshot | BE1 – An
storefront_subscriptions | PRIMARY KEY | storefront_subscriptions_pkey | PRIMARY KEY (subscription_id) | BE1 – An
storefront_subscriptions | n | storefront_subscriptions_status_not_null | NOT NULL status | BE1 – An
storefront_subscriptions | n | storefront_subscriptions_storefront_id_not_null | NOT NULL storefront_id | BE1 – An
storefront_subscriptions | n | storefront_subscriptions_subscription_id_not_null | NOT NULL subscription_id | BE1 – An
storefronts | CHECK | ck_storefront_verification | CHECK (((seller_verification_status)::text = ANY ((ARRAY['PENDING'::character varying, 'VERIFIED'::character varying, 'REJECTED'::character varying])::text[]))) | BE1 – An
storefronts | n | storefronts_created_at_not_null | NOT NULL created_at | BE1 – An
storefronts | UNIQUE | storefronts_owner_user_id_key | UNIQUE (owner_user_id) | BE1 – An
storefronts | n | storefronts_owner_user_id_not_null | NOT NULL owner_user_id | BE1 – An
storefronts | PRIMARY KEY | storefronts_pkey | PRIMARY KEY (storefront_id) | BE1 – An
storefronts | n | storefronts_seller_verification_status_not_null | NOT NULL seller_verification_status | BE1 – An
storefronts | n | storefronts_status_not_null | NOT NULL status | BE1 – An
storefronts | n | storefronts_storefront_id_not_null | NOT NULL storefront_id | BE1 – An
storefronts | n | storefronts_storefront_name_not_null | NOT NULL storefront_name | BE1 – An
transaction_attempts | CHECK | ck_attempt_expiry | CHECK (((expires_at IS NULL) OR (expires_at > created_at))) | BE1 – An
transaction_attempts | CHECK | ck_attempt_number | CHECK ((attempt_number > 0)) | BE1 – An
transaction_attempts | CHECK | ck_attempt_status | CHECK (((attempt_status)::text = ANY ((ARRAY['PENDING'::character varying, 'REQUESTED'::character varying, 'REVIEWING'::character varying, 'APPROVED'::character varying, 'PROCESSING'::character varying, 'SUCCESS'::character varying, 'FAILED'::character varying, 'CANCELLED'::character varying, 'REJECTED'::character varying, 'UNKNOWN'::character varying])::text[]))) | BE1 – An
transaction_attempts | n | transaction_attempts_attempt_id_not_null | NOT NULL attempt_id | BE1 – An
transaction_attempts | n | transaction_attempts_attempt_number_not_null | NOT NULL attempt_number | BE1 – An
transaction_attempts | n | transaction_attempts_attempt_status_not_null | NOT NULL attempt_status | BE1 – An
transaction_attempts | n | transaction_attempts_created_at_not_null | NOT NULL created_at | BE1 – An
transaction_attempts | UNIQUE | transaction_attempts_idempotency_key_key | UNIQUE (idempotency_key) | BE1 – An
transaction_attempts | n | transaction_attempts_idempotency_key_not_null | NOT NULL idempotency_key | BE1 – An
transaction_attempts | PRIMARY KEY | transaction_attempts_pkey | PRIMARY KEY (attempt_id) | BE1 – An
transaction_attempts | n | transaction_attempts_provider_name_not_null | NOT NULL provider_name | BE1 – An
transaction_attempts | n | transaction_attempts_transaction_id_not_null | NOT NULL transaction_id | BE1 – An
transaction_attempts | UNIQUE | uq_attempt_external_reference | UNIQUE (provider_name, external_reference) | BE1 – An
transaction_attempts | UNIQUE | uq_attempt_number | UNIQUE (transaction_id, attempt_number) | BE1 – An
transactions | CHECK | ck_tx_amount | CHECK ((amount > (0)::numeric)) | BE1 – An
transactions | CHECK | ck_tx_bank_payee_present | CHECK (((payee_bank_account_id IS NULL) OR (payee_user_id IS NOT NULL))) | BE1 – An
transactions | CHECK | ck_tx_currency | CHECK (((currency)::text = 'VND'::text)) | BE1 – An
transactions | CHECK | ck_tx_direct_rental | CHECK ((((transaction_type)::text <> 'PAYMENT'::text) OR ((purpose)::text <> 'RENTAL'::text) OR ((settlement_mode)::text = 'DIRECT_TO_DESIGNER'::text))) | BE1 – An
transactions | CHECK | ck_tx_environment | CHECK (((environment)::text = 'SANDBOX'::text)) | BE1 – An
transactions | CHECK | ck_tx_no_cod_digital | CHECK ((((settlement_mode)::text <> 'COD'::text) OR ((purpose)::text = 'PHYSICAL_ORDER'::text))) | BE1 – An
transactions | CHECK | ck_tx_no_direct_other | CHECK ((((settlement_mode)::text <> 'DIRECT_TO_DESIGNER'::text) OR (((transaction_type)::text = 'PAYMENT'::text) AND ((purpose)::text = 'RENTAL'::text)))) | BE1 – An
transactions | CHECK | ck_tx_not_self_refund | CHECK (((original_transaction_id IS NULL) OR (original_transaction_id <> transaction_id))) | BE1 – An
transactions | CHECK | ck_tx_payout_bank | CHECK ((((transaction_type)::text <> 'PAYOUT'::text) OR (payee_bank_account_id IS NOT NULL))) | BE1 – An
transactions | CHECK | ck_tx_purpose | CHECK (((purpose)::text = ANY ((ARRAY['PHYSICAL_ORDER'::character varying, 'RENTAL'::character varying, 'POD'::character varying, 'SUBSCRIPTION'::character varying, 'WALLET'::character varying])::text[]))) | BE1 – An
transactions | CHECK | ck_tx_purpose_fk | CHECK ((((transaction_type)::text <> 'PAYMENT'::text) OR (((purpose)::text = 'PHYSICAL_ORDER'::text) AND (physical_order_id IS NOT NULL)) OR (((purpose)::text = 'RENTAL'::text) AND (rental_contract_id IS NOT NULL)) OR (((purpose)::text = 'POD'::text) AND (print_request_id IS NOT NULL)) OR (((purpose)::text = 'SUBSCRIPTION'::text) AND (storefront_subscription_id IS NOT NULL)))) | BE1 – An
transactions | CHECK | ck_tx_refund_reason | CHECK ((((transaction_type)::text <> 'REFUND'::text) OR (refund_reason IS NOT NULL))) | BE1 – An
transactions | CHECK | ck_tx_status | CHECK (((status)::text = ANY ((ARRAY['PENDING'::character varying, 'REQUESTED'::character varying, 'REVIEWING'::character varying, 'APPROVED'::character varying, 'PROCESSING'::character varying, 'SUCCESS'::character varying, 'FAILED'::character varying, 'CANCELLED'::character varying, 'REJECTED'::character varying, 'UNKNOWN'::character varying])::text[]))) | BE1 – An
transactions | CHECK | ck_tx_type | CHECK (((transaction_type)::text = ANY ((ARRAY['PAYMENT'::character varying, 'REFUND'::character varying, 'TOPUP'::character varying, 'PAYOUT'::character varying])::text[]))) | BE1 – An
transactions | CHECK | ck_tx_type_sources | CHECK (((((transaction_type)::text = 'PAYMENT'::text) AND (original_transaction_id IS NULL) AND (num_nonnulls(physical_order_id, rental_contract_id, print_request_id, storefront_subscription_id) = 1) AND ((purpose)::text <> 'WALLET'::text)) OR (((transaction_type)::text = 'REFUND'::text) AND (original_transaction_id IS NOT NULL) AND (num_nonnulls(physical_order_id, rental_contract_id, print_request_id, storefront_subscription_id) = 0)) OR (((transaction_type)::text = ANY ((ARRAY['TOPUP'::character varying, 'PAYOUT'::character varying])::text[])) AND ((purpose)::text = 'WALLET'::text) AND (wallet_id IS NOT NULL) AND (original_transaction_id IS NULL) AND (num_nonnulls(physical_order_id, rental_contract_id, print_request_id, storefront_subscription_id) = 0)))) | BE1 – An
transactions | n | transactions_amount_not_null | NOT NULL amount | BE1 – An
transactions | n | transactions_created_at_not_null | NOT NULL created_at | BE1 – An
transactions | n | transactions_currency_not_null | NOT NULL currency | BE1 – An
transactions | n | transactions_environment_not_null | NOT NULL environment | BE1 – An
transactions | n | transactions_fulfillment_status_not_null | NOT NULL fulfillment_status | BE1 – An
transactions | n | transactions_operation_key_not_null | NOT NULL operation_key | BE1 – An
transactions | PRIMARY KEY | transactions_pkey | PRIMARY KEY (transaction_id) | BE1 – An
transactions | n | transactions_purpose_not_null | NOT NULL purpose | BE1 – An
transactions | n | transactions_settlement_mode_not_null | NOT NULL settlement_mode | BE1 – An
transactions | n | transactions_status_not_null | NOT NULL status | BE1 – An
transactions | n | transactions_transaction_id_not_null | NOT NULL transaction_id | BE1 – An
transactions | n | transactions_transaction_type_not_null | NOT NULL transaction_type | BE1 – An
transactions | UNIQUE | uq_transactions_operation_key | UNIQUE (operation_key) | BE1 – An
user_addresses | n | user_addresses_address_id_not_null | NOT NULL address_id | BE1 – An
user_addresses | n | user_addresses_address_line_not_null | NOT NULL address_line | BE1 – An
user_addresses | n | user_addresses_created_at_not_null | NOT NULL created_at | BE1 – An
user_addresses | n | user_addresses_is_default_not_null | NOT NULL is_default | BE1 – An
user_addresses | PRIMARY KEY | user_addresses_pkey | PRIMARY KEY (address_id) | BE1 – An
user_addresses | n | user_addresses_recipient_name_not_null | NOT NULL recipient_name | BE1 – An
user_addresses | n | user_addresses_user_id_not_null | NOT NULL user_id | BE1 – An
user_bank_accounts | CHECK | ck_bank_sandbox | CHECK (((environment)::text = 'SANDBOX'::text)) | BE1 – An
user_bank_accounts | CHECK | ck_bank_verification | CHECK (((verification_status)::text = ANY ((ARRAY['PENDING'::character varying, 'VERIFIED'::character varying, 'REJECTED'::character varying])::text[]))) | BE1 – An
user_bank_accounts | n | user_bank_accounts_account_holder_not_null | NOT NULL account_holder | BE1 – An
user_bank_accounts | n | user_bank_accounts_account_number_masked_not_null | NOT NULL account_number_masked | BE1 – An
user_bank_accounts | n | user_bank_accounts_account_number_token_not_null | NOT NULL account_number_token | BE1 – An
user_bank_accounts | n | user_bank_accounts_bank_account_id_not_null | NOT NULL bank_account_id | BE1 – An
user_bank_accounts | n | user_bank_accounts_bank_code_not_null | NOT NULL bank_code | BE1 – An
user_bank_accounts | n | user_bank_accounts_bank_name_not_null | NOT NULL bank_name | BE1 – An
user_bank_accounts | n | user_bank_accounts_created_at_not_null | NOT NULL created_at | BE1 – An
user_bank_accounts | n | user_bank_accounts_environment_not_null | NOT NULL environment | BE1 – An
user_bank_accounts | n | user_bank_accounts_is_active_not_null | NOT NULL is_active | BE1 – An
user_bank_accounts | n | user_bank_accounts_is_default_not_null | NOT NULL is_default | BE1 – An
user_bank_accounts | PRIMARY KEY | user_bank_accounts_pkey | PRIMARY KEY (bank_account_id) | BE1 – An
user_bank_accounts | n | user_bank_accounts_user_id_not_null | NOT NULL user_id | BE1 – An
user_bank_accounts | n | user_bank_accounts_verification_status_not_null | NOT NULL verification_status | BE1 – An
user_roles | CHECK | ck_user_role_status | CHECK (((approval_status)::text = ANY ((ARRAY['PENDING'::character varying, 'ACTIVE'::character varying, 'REJECTED'::character varying, 'REVOKED'::character varying])::text[]))) | BE1 – An
user_roles | n | user_roles_approval_status_not_null | NOT NULL approval_status | BE1 – An
user_roles | n | user_roles_created_at_not_null | NOT NULL created_at | BE1 – An
user_roles | PRIMARY KEY | user_roles_pkey | PRIMARY KEY (user_id, role_id) | BE1 – An
user_roles | n | user_roles_role_id_not_null | NOT NULL role_id | BE1 – An
user_roles | n | user_roles_user_id_not_null | NOT NULL user_id | BE1 – An
users | CHECK | ck_user_ai_credits | CHECK ((ai_credits_balance >= 0)) | BE1 – An
users | n | users_account_status_not_null | NOT NULL account_status | BE1 – An
users | n | users_ai_credits_balance_not_null | NOT NULL ai_credits_balance | BE1 – An
users | n | users_created_at_not_null | NOT NULL created_at | BE1 – An
users | UNIQUE | users_email_key | UNIQUE (email) | BE1 – An
users | n | users_email_not_null | NOT NULL email | BE1 – An
users | n | users_email_verified_not_null | NOT NULL email_verified | BE1 – An
users | n | users_full_name_not_null | NOT NULL full_name | BE1 – An
users | UNIQUE | users_google_id_key | UNIQUE (google_id) | BE1 – An
users | n | users_password_hash_not_null | NOT NULL password_hash | BE1 – An
users | n | users_phone_verified_not_null | NOT NULL phone_verified | BE1 – An
users | PRIMARY KEY | users_pkey | PRIMARY KEY (user_id) | BE1 – An
users | n | users_user_id_not_null | NOT NULL user_id | BE1 – An
wallet_ledgers | CHECK | ck_ledger_balance | CHECK (((balance_after >= (0)::numeric) AND (signed_amount <> (0)::numeric))) | BE2 – Khang
wallet_ledgers | CHECK | ck_ledger_bucket | CHECK (((balance_bucket)::text = ANY ((ARRAY['PENDING'::character varying, 'AVAILABLE'::character varying, 'HELD'::character varying])::text[]))) | BE2 – Khang
wallet_ledgers | CHECK | ck_ledger_one_source | CHECK ((num_nonnulls(transaction_id, seller_earning_id) = 1)) | BE2 – Khang
wallet_ledgers | n | wallet_ledgers_balance_after_not_null | NOT NULL balance_after | BE2 – Khang
wallet_ledgers | n | wallet_ledgers_balance_bucket_not_null | NOT NULL balance_bucket | BE2 – Khang
wallet_ledgers | n | wallet_ledgers_created_at_not_null | NOT NULL created_at | BE2 – Khang
wallet_ledgers | n | wallet_ledgers_entry_type_not_null | NOT NULL entry_type | BE2 – Khang
wallet_ledgers | UNIQUE | wallet_ledgers_idempotency_key_key | UNIQUE (idempotency_key) | BE2 – Khang
wallet_ledgers | n | wallet_ledgers_idempotency_key_not_null | NOT NULL idempotency_key | BE2 – Khang
wallet_ledgers | n | wallet_ledgers_ledger_id_not_null | NOT NULL ledger_id | BE2 – Khang
wallet_ledgers | PRIMARY KEY | wallet_ledgers_pkey | PRIMARY KEY (ledger_id) | BE2 – Khang
wallet_ledgers | n | wallet_ledgers_signed_amount_not_null | NOT NULL signed_amount | BE2 – Khang
wallet_ledgers | n | wallet_ledgers_wallet_id_not_null | NOT NULL wallet_id | BE2 – Khang
wallets | CHECK | ck_wallet_nonnegative | CHECK (((pending_balance >= (0)::numeric) AND (available_balance >= (0)::numeric) AND (held_balance >= (0)::numeric))) | BE2 – Khang
wallets | CHECK | ck_wallet_sandbox | CHECK (((environment)::text = 'SANDBOX'::text)) | BE2 – Khang
wallets | n | wallets_available_balance_not_null | NOT NULL available_balance | BE2 – Khang
wallets | n | wallets_environment_not_null | NOT NULL environment | BE2 – Khang
wallets | n | wallets_held_balance_not_null | NOT NULL held_balance | BE2 – Khang
wallets | n | wallets_pending_balance_not_null | NOT NULL pending_balance | BE2 – Khang
wallets | PRIMARY KEY | wallets_pkey | PRIMARY KEY (wallet_id) | BE2 – Khang
wallets | UNIQUE | wallets_user_id_key | UNIQUE (user_id) | BE2 – Khang
wallets | n | wallets_user_id_not_null | NOT NULL user_id | BE2 – Khang
wallets | n | wallets_wallet_id_not_null | NOT NULL wallet_id | BE2 – Khang
ai_requests | INDEX | ai_requests_pkey | CREATE UNIQUE INDEX ai_requests_pkey ON public.ai_requests USING btree (ai_request_id) | BE2 – Khang
ai_requests | INDEX | ix_ai_requests_base_version_id | CREATE INDEX ix_ai_requests_base_version_id ON public.ai_requests USING btree (base_version_id) | BE2 – Khang
ai_requests | INDEX | ix_ai_requests_model_id | CREATE INDEX ix_ai_requests_model_id ON public.ai_requests USING btree (model_id) | BE2 – Khang
ai_requests | INDEX | ix_ai_requests_user_id | CREATE INDEX ix_ai_requests_user_id ON public.ai_requests USING btree (user_id) | BE2 – Khang
ai_requests | INDEX | ix_ai_requests_user_id_status_created_at | CREATE INDEX ix_ai_requests_user_id_status_created_at ON public.ai_requests USING btree (user_id, status, created_at) | BE2 – Khang
ai_requests | INDEX | uq_ai_requests_model_id_ai_request_id | CREATE UNIQUE INDEX uq_ai_requests_model_id_ai_request_id ON public.ai_requests USING btree (model_id, ai_request_id) | BE2 – Khang
ai_requests | INDEX | uq_ai_requests_provider_name_provider_job_reference | CREATE UNIQUE INDEX uq_ai_requests_provider_name_provider_job_reference ON public.ai_requests USING btree (provider_name, provider_job_reference) | BE2 – Khang
audit_logs | INDEX | audit_logs_pkey | CREATE UNIQUE INDEX audit_logs_pkey ON public.audit_logs USING btree (audit_log_id) | BE1 – An
audit_logs | INDEX | idx_audit_logs_actor_user_id | CREATE INDEX idx_audit_logs_actor_user_id ON public.audit_logs USING btree (actor_user_id) | BE1 – An
cart_items | INDEX | cart_items_pkey | CREATE UNIQUE INDEX cart_items_pkey ON public.cart_items USING btree (cart_item_id) | BE1 – An
cart_items | INDEX | idx_cart_items_variant | CREATE INDEX idx_cart_items_variant ON public.cart_items USING btree (variant_id) | BE1 – An
cart_items | INDEX | uq_cart_variant | CREATE UNIQUE INDEX uq_cart_variant ON public.cart_items USING btree (cart_id, variant_id) | BE1 – An
carts | INDEX | carts_pkey | CREATE UNIQUE INDEX carts_pkey ON public.carts USING btree (cart_id) | BE1 – An
carts | INDEX | carts_user_id_key | CREATE UNIQUE INDEX carts_user_id_key ON public.carts USING btree (user_id) | BE1 – An
model_files | INDEX | ix_model_files_model_version_id | CREATE INDEX ix_model_files_model_version_id ON public.model_files USING btree (model_version_id) | BE2 – Khang
model_files | INDEX | ix_model_files_model_version_id_file_role | CREATE INDEX ix_model_files_model_version_id_file_role ON public.model_files USING btree (model_version_id, file_role) | BE2 – Khang
model_files | INDEX | model_files_pkey | CREATE UNIQUE INDEX model_files_pkey ON public.model_files USING btree (file_id) | BE2 – Khang
model_files | INDEX | uq_model_primary_file | CREATE UNIQUE INDEX uq_model_primary_file ON public.model_files USING btree (model_version_id) WHERE (is_primary = true) | BE2 – Khang
model_versions | INDEX | ix_model_versions_model_id_created_at | CREATE INDEX ix_model_versions_model_id_created_at ON public.model_versions USING btree (model_id, created_at) | BE2 – Khang
model_versions | INDEX | ix_model_versions_parent_version_id | CREATE INDEX ix_model_versions_parent_version_id ON public.model_versions USING btree (parent_version_id) | BE2 – Khang
model_versions | INDEX | model_versions_ai_request_id_key | CREATE UNIQUE INDEX model_versions_ai_request_id_key ON public.model_versions USING btree (ai_request_id) | BE2 – Khang
model_versions | INDEX | model_versions_pkey | CREATE UNIQUE INDEX model_versions_pkey ON public.model_versions USING btree (model_version_id) | BE2 – Khang
model_versions | INDEX | uq_model_versions_model_id_model_version_id | CREATE UNIQUE INDEX uq_model_versions_model_id_model_version_id ON public.model_versions USING btree (model_id, model_version_id) | BE2 – Khang
model_versions | INDEX | uq_model_versions_model_id_version_number | CREATE UNIQUE INDEX uq_model_versions_model_id_version_number ON public.model_versions USING btree (model_id, version_number) | BE2 – Khang
models_3d | INDEX | models_3d_pkey | CREATE UNIQUE INDEX models_3d_pkey ON public.models_3d USING btree (model_id) | BE2 – Khang
notifications | INDEX | idx_notifications_recipient_user_id | CREATE INDEX idx_notifications_recipient_user_id ON public.notifications USING btree (recipient_user_id) | BE2 – Khang
notifications | INDEX | notifications_pkey | CREATE UNIQUE INDEX notifications_pkey ON public.notifications USING btree (notification_id) | BE2 – Khang
notifications | INDEX | uq_notification_dedupe | CREATE UNIQUE INDEX uq_notification_dedupe ON public.notifications USING btree (recipient_user_id, dedupe_key) WHERE (dedupe_key IS NOT NULL) | BE2 – Khang
order_shipping_package_items | INDEX | ix_package_items_order | CREATE INDEX ix_package_items_order ON public.order_shipping_package_items USING btree (physical_order_id, physical_order_item_id) | BE1 – An
order_shipping_package_items | INDEX | ix_package_items_order_item | CREATE INDEX ix_package_items_order_item ON public.order_shipping_package_items USING btree (physical_order_item_id) | BE1 – An
order_shipping_package_items | INDEX | ix_package_items_product_variant | CREATE INDEX ix_package_items_product_variant ON public.order_shipping_package_items USING btree (product_id, variant_id) | BE1 – An
order_shipping_package_items | INDEX | ix_package_items_variant | CREATE INDEX ix_package_items_variant ON public.order_shipping_package_items USING btree (variant_id) | BE1 – An
order_shipping_package_items | INDEX | order_shipping_package_items_pkey | CREATE UNIQUE INDEX order_shipping_package_items_pkey ON public.order_shipping_package_items USING btree (shipping_package_item_id) | BE1 – An
order_shipping_package_items | INDEX | order_shipping_package_items_shipping_package_id_physical_o_key | CREATE UNIQUE INDEX order_shipping_package_items_shipping_package_id_physical_o_key ON public.order_shipping_package_items USING btree (shipping_package_id, physical_order_item_id) | BE1 – An
order_shipping_packages | INDEX | ix_package_profile | CREATE INDEX ix_package_profile ON public.order_shipping_packages USING btree (packaging_profile_id) | BE1 – An
order_shipping_packages | INDEX | order_shipping_packages_package_code_key | CREATE UNIQUE INDEX order_shipping_packages_package_code_key ON public.order_shipping_packages USING btree (package_code) | BE1 – An
order_shipping_packages | INDEX | order_shipping_packages_physical_order_id_package_index_key | CREATE UNIQUE INDEX order_shipping_packages_physical_order_id_package_index_key ON public.order_shipping_packages USING btree (physical_order_id, package_index) | BE1 – An
order_shipping_packages | INDEX | order_shipping_packages_physical_order_id_shipping_package__key | CREATE UNIQUE INDEX order_shipping_packages_physical_order_id_shipping_package__key ON public.order_shipping_packages USING btree (physical_order_id, shipping_package_id) | BE1 – An
order_shipping_packages | INDEX | order_shipping_packages_pkey | CREATE UNIQUE INDEX order_shipping_packages_pkey ON public.order_shipping_packages USING btree (shipping_package_id) | BE1 – An
order_status_history | INDEX | ix_order_history_actor | CREATE INDEX ix_order_history_actor ON public.order_status_history USING btree (changed_by_user_id) | BE1 – An
order_status_history | INDEX | ix_order_history_order_time | CREATE INDEX ix_order_history_order_time ON public.order_status_history USING btree (physical_order_id, changed_at) | BE1 – An
order_status_history | INDEX | order_status_history_pkey | CREATE UNIQUE INDEX order_status_history_pkey ON public.order_status_history USING btree (order_status_history_id) | BE1 – An
order_status_history | INDEX | order_status_history_source_event_id_key | CREATE UNIQUE INDEX order_status_history_source_event_id_key ON public.order_status_history USING btree (source_event_id) | BE1 – An
packaging_profiles | INDEX | packaging_profiles_code_key | CREATE UNIQUE INDEX packaging_profiles_code_key ON public.packaging_profiles USING btree (code) | BE1 – An
packaging_profiles | INDEX | packaging_profiles_pkey | CREATE UNIQUE INDEX packaging_profiles_pkey ON public.packaging_profiles USING btree (packaging_profile_id) | BE1 – An
physical_order_items | INDEX | ix_physical_orders_item_physical_order_id | CREATE INDEX ix_physical_orders_item_physical_order_id ON public.physical_order_items USING btree (physical_order_id) | BE1 – An
physical_order_items | INDEX | ix_physical_orders_item_variant_id | CREATE INDEX ix_physical_orders_item_variant_id ON public.physical_order_items USING btree (variant_id) | BE1 – An
physical_order_items | INDEX | physical_order_items_pkey | CREATE UNIQUE INDEX physical_order_items_pkey ON public.physical_order_items USING btree (physical_order_item_id) | BE1 – An
physical_order_items | INDEX | uq_order_items_order_item | CREATE UNIQUE INDEX uq_order_items_order_item ON public.physical_order_items USING btree (physical_order_id, physical_order_item_id) | BE1 – An
physical_orders | INDEX | idx_physical_orders_checkout_group | CREATE INDEX idx_physical_orders_checkout_group ON public.physical_orders USING btree (checkout_group_id) WHERE (checkout_group_id IS NOT NULL) | BE1 – An
physical_orders | INDEX | ix_order_reservation_expiry | CREATE INDEX ix_order_reservation_expiry ON public.physical_orders USING btree (reservation_expires_at) WHERE ((reservation_status)::text = 'RESERVED'::text) | BE1 – An
physical_orders | INDEX | ix_physical_orders_buyer_user_id | CREATE INDEX ix_physical_orders_buyer_user_id ON public.physical_orders USING btree (buyer_user_id) | BE1 – An
physical_orders | INDEX | ix_physical_orders_storefront_id | CREATE INDEX ix_physical_orders_storefront_id ON public.physical_orders USING btree (storefront_id) | BE1 – An
physical_orders | INDEX | ix_physical_orders_storefront_id_order_status | CREATE INDEX ix_physical_orders_storefront_id_order_status ON public.physical_orders USING btree (storefront_id, order_status) | BE1 – An
physical_orders | INDEX | physical_orders_order_code_key | CREATE UNIQUE INDEX physical_orders_order_code_key ON public.physical_orders USING btree (order_code) | BE1 – An
physical_orders | INDEX | physical_orders_pkey | CREATE UNIQUE INDEX physical_orders_pkey ON public.physical_orders USING btree (physical_order_id) | BE1 – An
physical_orders | INDEX | uq_order_checkout_seller | CREATE UNIQUE INDEX uq_order_checkout_seller ON public.physical_orders USING btree (buyer_user_id, idempotency_key, storefront_id) WHERE (idempotency_key IS NOT NULL) | BE1 – An
platform_configs | INDEX | platform_configs_config_key_key | CREATE UNIQUE INDEX platform_configs_config_key_key ON public.platform_configs USING btree (config_key) | BE1 – An
platform_configs | INDEX | platform_configs_pkey | CREATE UNIQUE INDEX platform_configs_pkey ON public.platform_configs USING btree (config_id) | BE1 – An
print_materials | INDEX | print_materials_pkey | CREATE UNIQUE INDEX print_materials_pkey ON public.print_materials USING btree (material_id) | BE2 – Khang
print_quote_items | INDEX | print_quote_items_pkey | CREATE UNIQUE INDEX print_quote_items_pkey ON public.print_quote_items USING btree (print_quote_item_id) | BE2 – Khang
print_quote_items | INDEX | uq_print_quotes_item_print_quote_id_print_request_item_id | CREATE UNIQUE INDEX uq_print_quotes_item_print_quote_id_print_request_item_id ON public.print_quote_items USING btree (print_quote_id, print_request_item_id) | BE2 – Khang
print_quotes | INDEX | idx_print_quotes_print_request_id | CREATE INDEX idx_print_quotes_print_request_id ON public.print_quotes USING btree (print_request_id) | BE2 – Khang
print_quotes | INDEX | ix_print_quotes_quoted_by_user_id | CREATE INDEX ix_print_quotes_quoted_by_user_id ON public.print_quotes USING btree (quoted_by_user_id) | BE2 – Khang
print_quotes | INDEX | print_quotes_pkey | CREATE UNIQUE INDEX print_quotes_pkey ON public.print_quotes USING btree (print_quote_id) | BE2 – Khang
print_quotes | INDEX | uq_print_quotes_print_request_id_version_number | CREATE UNIQUE INDEX uq_print_quotes_print_request_id_version_number ON public.print_quotes USING btree (print_request_id, version_number) | BE2 – Khang
print_quotes | INDEX | uq_quote_request_quote | CREATE UNIQUE INDEX uq_quote_request_quote ON public.print_quotes USING btree (print_request_id, print_quote_id) | BE2 – Khang
print_request_file_versions | INDEX | ix_print_file_uploader | CREATE INDEX ix_print_file_uploader ON public.print_request_file_versions USING btree (uploaded_by_user_id) | BE2 – Khang
print_request_file_versions | INDEX | print_request_file_versions_pkey | CREATE UNIQUE INDEX print_request_file_versions_pkey ON public.print_request_file_versions USING btree (file_version_id) | BE2 – Khang
print_request_file_versions | INDEX | print_request_file_versions_print_request_id_version_key | CREATE UNIQUE INDEX print_request_file_versions_print_request_id_version_key ON public.print_request_file_versions USING btree (print_request_id, version) | BE2 – Khang
print_request_items | INDEX | ix_print_requests_item_material_id | CREATE INDEX ix_print_requests_item_material_id ON public.print_request_items USING btree (material_id) | BE2 – Khang
print_request_items | INDEX | ix_print_requests_item_model_version_id | CREATE INDEX ix_print_requests_item_model_version_id ON public.print_request_items USING btree (model_version_id) | BE2 – Khang
print_request_items | INDEX | ix_print_requests_item_print_request_id | CREATE INDEX ix_print_requests_item_print_request_id ON public.print_request_items USING btree (print_request_id) | BE2 – Khang
print_request_items | INDEX | print_request_items_pkey | CREATE UNIQUE INDEX print_request_items_pkey ON public.print_request_items USING btree (print_request_item_id) | BE2 – Khang
print_request_spec_versions | INDEX | ix_print_spec_creator | CREATE INDEX ix_print_spec_creator ON public.print_request_spec_versions USING btree (created_by_user_id) | BE2 – Khang
print_request_spec_versions | INDEX | print_request_spec_versions_pkey | CREATE UNIQUE INDEX print_request_spec_versions_pkey ON public.print_request_spec_versions USING btree (spec_version_id) | BE2 – Khang
print_request_spec_versions | INDEX | print_request_spec_versions_print_request_id_version_key | CREATE UNIQUE INDEX print_request_spec_versions_print_request_id_version_key ON public.print_request_spec_versions USING btree (print_request_id, version) | BE2 – Khang
print_request_status_history | INDEX | ix_print_history_actor | CREATE INDEX ix_print_history_actor ON public.print_request_status_history USING btree (changed_by_user_id) | BE2 – Khang
print_request_status_history | INDEX | ix_print_history_request_time | CREATE INDEX ix_print_history_request_time ON public.print_request_status_history USING btree (print_request_id, changed_at) | BE2 – Khang
print_request_status_history | INDEX | print_request_status_history_pkey | CREATE UNIQUE INDEX print_request_status_history_pkey ON public.print_request_status_history USING btree (print_status_history_id) | BE2 – Khang
print_request_status_history | INDEX | print_request_status_history_source_event_id_key | CREATE UNIQUE INDEX print_request_status_history_source_event_id_key ON public.print_request_status_history USING btree (source_event_id) | BE2 – Khang
print_request_technical_reviews | INDEX | ix_print_review_actor | CREATE INDEX ix_print_review_actor ON public.print_request_technical_reviews USING btree (reviewer_user_id) | BE2 – Khang
print_request_technical_reviews | INDEX | ix_print_review_request | CREATE INDEX ix_print_review_request ON public.print_request_technical_reviews USING btree (print_request_id) | BE2 – Khang
print_request_technical_reviews | INDEX | print_request_technical_reviews_pkey | CREATE UNIQUE INDEX print_request_technical_reviews_pkey ON public.print_request_technical_reviews USING btree (technical_review_id) | BE2 – Khang
print_requests | INDEX | ix_print_current_quote | CREATE INDEX ix_print_current_quote ON public.print_requests USING btree (current_quote_id) | BE2 – Khang
print_requests | INDEX | ix_print_handled_by | CREATE INDEX ix_print_handled_by ON public.print_requests USING btree (handled_by_user_id) | BE2 – Khang
print_requests | INDEX | ix_print_requests_customer_user_id | CREATE INDEX ix_print_requests_customer_user_id ON public.print_requests USING btree (customer_user_id) | BE2 – Khang
print_requests | INDEX | ix_print_requests_status_created_at | CREATE INDEX ix_print_requests_status_created_at ON public.print_requests USING btree (status, created_at) | BE2 – Khang
print_requests | INDEX | print_requests_pkey | CREATE UNIQUE INDEX print_requests_pkey ON public.print_requests USING btree (print_request_id) | BE2 – Khang
product_media | INDEX | idx_product_media_product_id | CREATE INDEX idx_product_media_product_id ON public.product_media USING btree (product_id) | BE1 – An
product_media | INDEX | product_media_pkey | CREATE UNIQUE INDEX product_media_pkey ON public.product_media USING btree (media_id) | BE1 – An
product_variants | INDEX | idx_product_variants_product_id | CREATE INDEX idx_product_variants_product_id ON public.product_variants USING btree (product_id) | BE1 – An
product_variants | INDEX | product_variants_pkey | CREATE UNIQUE INDEX product_variants_pkey ON public.product_variants USING btree (variant_id) | BE1 – An
product_variants | INDEX | product_variants_sku_key | CREATE UNIQUE INDEX product_variants_sku_key ON public.product_variants USING btree (sku) | BE1 – An
product_variants | INDEX | uq_variants_product_variant | CREATE UNIQUE INDEX uq_variants_product_variant ON public.product_variants USING btree (product_id, variant_id) | BE1 – An
products | INDEX | ix_product_created_by | CREATE INDEX ix_product_created_by ON public.products USING btree (created_by_user_id) | BE1 – An
products | INDEX | products_pkey | CREATE UNIQUE INDEX products_pkey ON public.products USING btree (product_id) | BE1 – An
refund_request_items | INDEX | ix_refund_items_order_item | CREATE INDEX ix_refund_items_order_item ON public.refund_request_items USING btree (physical_order_item_id) | BE1 – An
refund_request_items | INDEX | ix_refund_items_product | CREATE INDEX ix_refund_items_product ON public.refund_request_items USING btree (product_id) | BE1 – An
refund_request_items | INDEX | refund_request_items_pkey | CREATE UNIQUE INDEX refund_request_items_pkey ON public.refund_request_items USING btree (refund_request_item_id) | BE1 – An
refund_request_items | INDEX | refund_request_items_refund_request_id_physical_order_item__key | CREATE UNIQUE INDEX refund_request_items_refund_request_id_physical_order_item__key ON public.refund_request_items USING btree (refund_request_id, physical_order_item_id) | BE1 – An
refund_requests | INDEX | ix_refund_completed_by | CREATE INDEX ix_refund_completed_by ON public.refund_requests USING btree (completed_by_user_id) | BE1 – An
refund_requests | INDEX | ix_refund_customer_status | CREATE INDEX ix_refund_customer_status ON public.refund_requests USING btree (customer_user_id, status) | BE1 – An
refund_requests | INDEX | ix_refund_reviewed_by | CREATE INDEX ix_refund_reviewed_by ON public.refund_requests USING btree (reviewed_by_user_id) | BE1 – An
refund_requests | INDEX | ix_refund_source | CREATE INDEX ix_refund_source ON public.refund_requests USING btree (source_type, source_id) | BE1 – An
refund_requests | INDEX | ix_refund_transaction | CREATE INDEX ix_refund_transaction ON public.refund_requests USING btree (transaction_id) | BE1 – An
refund_requests | INDEX | refund_requests_idempotency_key_key | CREATE UNIQUE INDEX refund_requests_idempotency_key_key ON public.refund_requests USING btree (idempotency_key) | BE1 – An
refund_requests | INDEX | refund_requests_pkey | CREATE UNIQUE INDEX refund_requests_pkey ON public.refund_requests USING btree (refund_request_id) | BE1 – An
rental_contracts | INDEX | ix_rental_contracts_designer_user_id | CREATE INDEX ix_rental_contracts_designer_user_id ON public.rental_contracts USING btree (designer_user_id) | BE2 – Khang
rental_contracts | INDEX | ix_rental_contracts_rental_offer_id | CREATE INDEX ix_rental_contracts_rental_offer_id ON public.rental_contracts USING btree (rental_offer_id) | BE2 – Khang
rental_contracts | INDEX | ix_rental_contracts_renter_user_id | CREATE INDEX ix_rental_contracts_renter_user_id ON public.rental_contracts USING btree (renter_user_id) | BE2 – Khang
rental_contracts | INDEX | ix_rental_contracts_renter_user_id_status | CREATE INDEX ix_rental_contracts_renter_user_id_status ON public.rental_contracts USING btree (renter_user_id, status) | BE2 – Khang
rental_contracts | INDEX | ix_rental_contracts_status_end_at | CREATE INDEX ix_rental_contracts_status_end_at ON public.rental_contracts USING btree (status, end_at) | BE2 – Khang
rental_contracts | INDEX | rental_contracts_pkey | CREATE UNIQUE INDEX rental_contracts_pkey ON public.rental_contracts USING btree (rental_contract_id) | BE2 – Khang
rental_offers | INDEX | ix_rental_offers_model_version_id | CREATE INDEX ix_rental_offers_model_version_id ON public.rental_offers USING btree (model_version_id) | BE2 – Khang
rental_offers | INDEX | ix_rental_offers_storefront_id | CREATE INDEX ix_rental_offers_storefront_id ON public.rental_offers USING btree (storefront_id) | BE2 – Khang
rental_offers | INDEX | ix_rental_offers_storefront_id_status | CREATE INDEX ix_rental_offers_storefront_id_status ON public.rental_offers USING btree (storefront_id, status) | BE2 – Khang
rental_offers | INDEX | rental_offers_pkey | CREATE UNIQUE INDEX rental_offers_pkey ON public.rental_offers USING btree (rental_offer_id) | BE2 – Khang
rental_offers | INDEX | uq_rental_offers_offer_id_version_id | CREATE UNIQUE INDEX uq_rental_offers_offer_id_version_id ON public.rental_offers USING btree (rental_offer_id, model_version_id) | BE2 – Khang
rental_plans | INDEX | idx_rental_plans_rental_offer_id | CREATE INDEX idx_rental_plans_rental_offer_id ON public.rental_plans USING btree (rental_offer_id) | BE2 – Khang
rental_plans | INDEX | rental_plans_pkey | CREATE UNIQUE INDEX rental_plans_pkey ON public.rental_plans USING btree (rental_plan_id) | BE2 – Khang
rental_plans | INDEX | uq_rental_plans_offer_id_plan_id | CREATE UNIQUE INDEX uq_rental_plans_offer_id_plan_id ON public.rental_plans USING btree (rental_offer_id, rental_plan_id) | BE2 – Khang
reports | INDEX | idx_reports_reported_user_id | CREATE INDEX idx_reports_reported_user_id ON public.reports USING btree (reported_user_id) | BE1 – An
reports | INDEX | ix_reports_product_id | CREATE INDEX ix_reports_product_id ON public.reports USING btree (product_id) | BE1 – An
reports | INDEX | ix_reports_rental_offer_id | CREATE INDEX ix_reports_rental_offer_id ON public.reports USING btree (rental_offer_id) | BE1 – An
reports | INDEX | ix_reports_reporter_user_id | CREATE INDEX ix_reports_reporter_user_id ON public.reports USING btree (reporter_user_id) | BE1 – An
reports | INDEX | reports_pkey | CREATE UNIQUE INDEX reports_pkey ON public.reports USING btree (report_id) | BE1 – An
review_merchant_replies | INDEX | ix_merchant_reply_user | CREATE INDEX ix_merchant_reply_user ON public.review_merchant_replies USING btree (replied_by_user_id) | BE1 – An
review_merchant_replies | INDEX | review_merchant_replies_pkey | CREATE UNIQUE INDEX review_merchant_replies_pkey ON public.review_merchant_replies USING btree (reply_id) | BE1 – An
review_merchant_replies | INDEX | review_merchant_replies_review_id_key | CREATE UNIQUE INDEX review_merchant_replies_review_id_key ON public.review_merchant_replies USING btree (review_id) | BE1 – An
reviews | INDEX | ix_reviews_order | CREATE INDEX ix_reviews_order ON public.reviews USING btree (physical_order_id) | BE1 – An
reviews | INDEX | ix_reviews_product_status | CREATE INDEX ix_reviews_product_status ON public.reviews USING btree (product_id, status, created_at) | BE1 – An
reviews | INDEX | ix_reviews_user | CREATE INDEX ix_reviews_user ON public.reviews USING btree (user_id) | BE1 – An
reviews | INDEX | reviews_physical_order_item_id_key | CREATE UNIQUE INDEX reviews_physical_order_item_id_key ON public.reviews USING btree (physical_order_item_id) | BE1 – An
reviews | INDEX | reviews_pkey | CREATE UNIQUE INDEX reviews_pkey ON public.reviews USING btree (review_id) | BE1 – An
roles | INDEX | roles_pkey | CREATE UNIQUE INDEX roles_pkey ON public.roles USING btree (role_id) | BE1 – An
roles | INDEX | roles_role_code_key | CREATE UNIQUE INDEX roles_role_code_key ON public.roles USING btree (role_code) | BE1 – An
seller_earnings | INDEX | ix_seller_earnings_earning_status_release_eligible_at | CREATE INDEX ix_seller_earnings_earning_status_release_eligible_at ON public.seller_earnings USING btree (earning_status, release_eligible_at) | BE2 – Khang
seller_earnings | INDEX | ix_seller_earnings_seller_user_id | CREATE INDEX ix_seller_earnings_seller_user_id ON public.seller_earnings USING btree (seller_user_id) | BE2 – Khang
seller_earnings | INDEX | ix_seller_earnings_wallet_id | CREATE INDEX ix_seller_earnings_wallet_id ON public.seller_earnings USING btree (wallet_id) | BE2 – Khang
seller_earnings | INDEX | seller_earnings_physical_order_id_key | CREATE UNIQUE INDEX seller_earnings_physical_order_id_key ON public.seller_earnings USING btree (physical_order_id) | BE2 – Khang
seller_earnings | INDEX | seller_earnings_pkey | CREATE UNIQUE INDEX seller_earnings_pkey ON public.seller_earnings USING btree (earning_id) | BE2 – Khang
shipments | INDEX | ix_shipments_physical_order_id | CREATE INDEX ix_shipments_physical_order_id ON public.shipments USING btree (physical_order_id) | BE1 – An
shipments | INDEX | ix_shipments_print_request_id | CREATE INDEX ix_shipments_print_request_id ON public.shipments USING btree (print_request_id) | BE1 – An
shipments | INDEX | shipments_pkey | CREATE UNIQUE INDEX shipments_pkey ON public.shipments USING btree (shipment_id) | BE1 – An
storefront_subscriptions | INDEX | ix_storefronts_subscription_storefront_id | CREATE INDEX ix_storefronts_subscription_storefront_id ON public.storefront_subscriptions USING btree (storefront_id) | BE1 – An
storefront_subscriptions | INDEX | ix_storefronts_subscription_storefront_id_status_end_at | CREATE INDEX ix_storefronts_subscription_storefront_id_status_end_at ON public.storefront_subscriptions USING btree (storefront_id, status, end_at) | BE1 – An
storefront_subscriptions | INDEX | storefront_subscriptions_pkey | CREATE UNIQUE INDEX storefront_subscriptions_pkey ON public.storefront_subscriptions USING btree (subscription_id) | BE1 – An
storefronts | INDEX | storefronts_owner_user_id_key | CREATE UNIQUE INDEX storefronts_owner_user_id_key ON public.storefronts USING btree (owner_user_id) | BE1 – An
storefronts | INDEX | storefronts_pkey | CREATE UNIQUE INDEX storefronts_pkey ON public.storefronts USING btree (storefront_id) | BE1 – An
transaction_attempts | INDEX | idx_attempt_status_created | CREATE INDEX idx_attempt_status_created ON public.transaction_attempts USING btree (attempt_status, created_at) | BE1 – An
transaction_attempts | INDEX | idx_attempt_transaction | CREATE INDEX idx_attempt_transaction ON public.transaction_attempts USING btree (transaction_id) | BE1 – An
transaction_attempts | INDEX | idx_attempt_verified_by | CREATE INDEX idx_attempt_verified_by ON public.transaction_attempts USING btree (verified_by_user_id) | BE1 – An
transaction_attempts | INDEX | ix_attempt_reconciliation | CREATE INDEX ix_attempt_reconciliation ON public.transaction_attempts USING btree (attempt_status, last_queried_at, expires_at) | BE1 – An
transaction_attempts | INDEX | transaction_attempts_idempotency_key_key | CREATE UNIQUE INDEX transaction_attempts_idempotency_key_key ON public.transaction_attempts USING btree (idempotency_key) | BE1 – An
transaction_attempts | INDEX | transaction_attempts_pkey | CREATE UNIQUE INDEX transaction_attempts_pkey ON public.transaction_attempts USING btree (attempt_id) | BE1 – An
transaction_attempts | INDEX | uq_attempt_external_reference | CREATE UNIQUE INDEX uq_attempt_external_reference ON public.transaction_attempts USING btree (provider_name, external_reference) | BE1 – An
transaction_attempts | INDEX | uq_attempt_number | CREATE UNIQUE INDEX uq_attempt_number ON public.transaction_attempts USING btree (transaction_id, attempt_number) | BE1 – An
transaction_attempts | INDEX | uq_attempt_one_success | CREATE UNIQUE INDEX uq_attempt_one_success ON public.transaction_attempts USING btree (transaction_id) WHERE ((attempt_status)::text = 'SUCCESS'::text) | BE1 – An
transaction_attempts | INDEX | uq_provider_transaction | CREATE UNIQUE INDEX uq_provider_transaction ON public.transaction_attempts USING btree (provider_name, provider_transaction_id) WHERE (provider_transaction_id IS NOT NULL) | BE1 – An
transactions | INDEX | idx_transactions_payee_user_id | CREATE INDEX idx_transactions_payee_user_id ON public.transactions USING btree (payee_user_id) | BE1 – An
transactions | INDEX | idx_transactions_payer_user_id | CREATE INDEX idx_transactions_payer_user_id ON public.transactions USING btree (payer_user_id) | BE1 – An
transactions | INDEX | idx_transactions_requested_by_user_id | CREATE INDEX idx_transactions_requested_by_user_id ON public.transactions USING btree (requested_by_user_id) | BE1 – An
transactions | INDEX | idx_transactions_reviewed_by_user_id | CREATE INDEX idx_transactions_reviewed_by_user_id ON public.transactions USING btree (reviewed_by_user_id) | BE1 – An
transactions | INDEX | ix_transactions_environment_status | CREATE INDEX ix_transactions_environment_status ON public.transactions USING btree (environment, status) | BE1 – An
transactions | INDEX | ix_transactions_original_transaction_id | CREATE INDEX ix_transactions_original_transaction_id ON public.transactions USING btree (original_transaction_id) | BE1 – An
transactions | INDEX | ix_transactions_payee_bank_account_id | CREATE INDEX ix_transactions_payee_bank_account_id ON public.transactions USING btree (payee_bank_account_id) | BE1 – An
transactions | INDEX | ix_transactions_physical_order_id | CREATE INDEX ix_transactions_physical_order_id ON public.transactions USING btree (physical_order_id) | BE1 – An
transactions | INDEX | ix_transactions_print_request_id | CREATE INDEX ix_transactions_print_request_id ON public.transactions USING btree (print_request_id) | BE1 – An
transactions | INDEX | ix_transactions_rental_contract_id | CREATE INDEX ix_transactions_rental_contract_id ON public.transactions USING btree (rental_contract_id) | BE1 – An
transactions | INDEX | ix_transactions_storefront_subscription_id | CREATE INDEX ix_transactions_storefront_subscription_id ON public.transactions USING btree (storefront_subscription_id) | BE1 – An
transactions | INDEX | ix_transactions_transaction_type_status_created_at | CREATE INDEX ix_transactions_transaction_type_status_created_at ON public.transactions USING btree (transaction_type, status, created_at) | BE1 – An
transactions | INDEX | ix_transactions_wallet_id | CREATE INDEX ix_transactions_wallet_id ON public.transactions USING btree (wallet_id) | BE1 – An
transactions | INDEX | transactions_pkey | CREATE UNIQUE INDEX transactions_pkey ON public.transactions USING btree (transaction_id) | BE1 – An
transactions | INDEX | uq_payment_active_key | CREATE UNIQUE INDEX uq_payment_active_key ON public.transactions USING btree (active_key) WHERE (active_key IS NOT NULL) | BE1 – An
transactions | INDEX | uq_transactions_operation_key | CREATE UNIQUE INDEX uq_transactions_operation_key ON public.transactions USING btree (operation_key) | BE1 – An
user_addresses | INDEX | idx_user_addresses_user_id | CREATE INDEX idx_user_addresses_user_id ON public.user_addresses USING btree (user_id) | BE1 – An
user_addresses | INDEX | uq_users_address_default | CREATE UNIQUE INDEX uq_users_address_default ON public.user_addresses USING btree (user_id) WHERE (is_default = true) | BE1 – An
user_addresses | INDEX | user_addresses_pkey | CREATE UNIQUE INDEX user_addresses_pkey ON public.user_addresses USING btree (address_id) | BE1 – An
user_bank_accounts | INDEX | ix_users_bank_account_user_id | CREATE INDEX ix_users_bank_account_user_id ON public.user_bank_accounts USING btree (user_id) | BE1 – An
user_bank_accounts | INDEX | ix_users_bank_account_user_id_is_active | CREATE INDEX ix_users_bank_account_user_id_is_active ON public.user_bank_accounts USING btree (user_id, is_active) | BE1 – An
user_bank_accounts | INDEX | uq_bank_default_active_sandbox | CREATE UNIQUE INDEX uq_bank_default_active_sandbox ON public.user_bank_accounts USING btree (user_id, environment) WHERE ((is_default = true) AND (is_active = true)) | BE1 – An
user_bank_accounts | INDEX | uq_user_bank_accounts_user_id_account_id | CREATE UNIQUE INDEX uq_user_bank_accounts_user_id_account_id ON public.user_bank_accounts USING btree (user_id, bank_account_id) | BE1 – An
user_bank_accounts | INDEX | user_bank_accounts_pkey | CREATE UNIQUE INDEX user_bank_accounts_pkey ON public.user_bank_accounts USING btree (bank_account_id) | BE1 – An
user_roles | INDEX | ix_users_role_granted_by_user_id | CREATE INDEX ix_users_role_granted_by_user_id ON public.user_roles USING btree (granted_by_user_id) | BE1 – An
user_roles | INDEX | ix_users_role_role_id | CREATE INDEX ix_users_role_role_id ON public.user_roles USING btree (role_id) | BE1 – An
user_roles | INDEX | user_roles_pkey | CREATE UNIQUE INDEX user_roles_pkey ON public.user_roles USING btree (user_id, role_id) | BE1 – An
users | INDEX | users_email_key | CREATE UNIQUE INDEX users_email_key ON public.users USING btree (email) | BE1 – An
users | INDEX | users_google_id_key | CREATE UNIQUE INDEX users_google_id_key ON public.users USING btree (google_id) | BE1 – An
users | INDEX | users_pkey | CREATE UNIQUE INDEX users_pkey ON public.users USING btree (user_id) | BE1 – An
wallet_ledgers | INDEX | ix_wallets_ledger_seller_earning_id | CREATE INDEX ix_wallets_ledger_seller_earning_id ON public.wallet_ledgers USING btree (seller_earning_id) | BE2 – Khang
wallet_ledgers | INDEX | ix_wallets_ledger_transaction_id | CREATE INDEX ix_wallets_ledger_transaction_id ON public.wallet_ledgers USING btree (transaction_id) | BE2 – Khang
wallet_ledgers | INDEX | ix_wallets_ledger_wallet_id | CREATE INDEX ix_wallets_ledger_wallet_id ON public.wallet_ledgers USING btree (wallet_id) | BE2 – Khang
wallet_ledgers | INDEX | ix_wallets_ledger_wallet_id_created_at | CREATE INDEX ix_wallets_ledger_wallet_id_created_at ON public.wallet_ledgers USING btree (wallet_id, created_at) | BE2 – Khang
wallet_ledgers | INDEX | wallet_ledgers_idempotency_key_key | CREATE UNIQUE INDEX wallet_ledgers_idempotency_key_key ON public.wallet_ledgers USING btree (idempotency_key) | BE2 – Khang
wallet_ledgers | INDEX | wallet_ledgers_pkey | CREATE UNIQUE INDEX wallet_ledgers_pkey ON public.wallet_ledgers USING btree (ledger_id) | BE2 – Khang
wallets | INDEX | uq_wallets_user_id_wallet_id | CREATE UNIQUE INDEX uq_wallets_user_id_wallet_id ON public.wallets USING btree (user_id, wallet_id) | BE2 – Khang
wallets | INDEX | wallets_pkey | CREATE UNIQUE INDEX wallets_pkey ON public.wallets USING btree (wallet_id) | BE2 – Khang
wallets | INDEX | wallets_user_id_key | CREATE UNIQUE INDEX wallets_user_id_key ON public.wallets USING btree (user_id) | BE2 – Khang

## Integration
Cross-feature integration contracts
Giữ 10 integration task gốc và bổ sung boundary v2. Không đánh Done một integration chỉ vì hai bên có endpoint riêng. Ownership bảng xem DB48.
Task ID | Boundary | Owners | Tables | Dependencies | Status | API liên quan hiện có | Đã có / còn thiếu | Acceptance contract
BE-INT-01 | Order → Payment | BE1 – An + BE2 – Khang | physical_orders, transaction_attempts, transactions | Related ownership tasks | In-progress | POST /api/orders/checkout POST /api/payments/zalopay POST /api/payments/zalopay/callback | Physical payment->PAID và processing consume có local tests; chưa provider end-to-end/cancel compensation. | Service contract + ownership + retry/idempotency + permission tests; không cập nhật bảng người khác bằng DTO từ FE.
BE-INT-02 | Storefront → Rental | BE1 – An + BE2 – Khang | rental_offers, storefront_subscriptions, storefronts | Related ownership tasks | In-progress | Không có endpoint integration riêng | Chưa có contract/integration test đầy đủ cho boundary này. | Service contract + ownership + retry/idempotency + permission tests; không cập nhật bảng người khác bằng DTO từ FE.
BE-INT-03 | Shipment → POD | BE1 – An + BE2 – Khang | print_requests, shipments | Related ownership tasks | In-progress | POST /api/orders/{orderId}/shipment GET /api/orders/{orderId}/shipments GET /api/seller/orders/{orderId}/shipments PATCH /api/shipments/{shipmentId}/event POST /api/print/requests/create GET /api/print/requests/getAll GET /api/print/requests/getId/{printRequestId} GET /api/print/requests/getId/{printRequestId}/file | Physical shipment và POD drafts có riêng; chưa POD dispatch gate/parent print_request. | Service contract + ownership + retry/idempotency + permission tests; không cập nhật bảng người khác bằng DTO từ FE.
BE-INT-04 | User → Model | BE1 – An + BE2 – Khang | models_3d, users | Related ownership tasks | In-progress | Không có endpoint integration riêng | Chưa có contract/integration test đầy đủ cho boundary này. | Service contract + ownership + retry/idempotency + permission tests; không cập nhật bảng người khác bằng DTO từ FE.
BE-INT-05 | User → Rental | BE1 – An + BE2 – Khang | rental_contracts, users | Related ownership tasks | In-progress | Không có endpoint integration riêng | Chưa có contract/integration test đầy đủ cho boundary này. | Service contract + ownership + retry/idempotency + permission tests; không cập nhật bảng người khác bằng DTO từ FE.
BE-INT-06 | Physical → Earnings | BE1 – An + BE2 – Khang | physical_orders, seller_earnings, wallets | Related ownership tasks | In-progress | Không có endpoint integration riêng | Chưa có contract/integration test đầy đủ cho boundary này. | Service contract + ownership + retry/idempotency + permission tests; không cập nhật bảng người khác bằng DTO từ FE.
BE-INT-07 | Cart → Payment | BE1 – An + BE2 – Khang | cart_items, carts, physical_orders, transactions | Related ownership tasks | In-progress | POST /api/orders/checkout POST /api/payments/zalopay POST /api/payments/zalopay/callback | Checkout replay+price ack/expiry có tests; failed/late refund compensation chưa đầy đủ. | Service contract + ownership + retry/idempotency + permission tests; không cập nhật bảng người khác bằng DTO từ FE.
BE-INT-08 | POD → Payment | BE2 – Khang | print_quotes, print_requests, transactions | Related ownership tasks | In-progress | Không có endpoint integration riêng | Chưa có contract/integration test đầy đủ cho boundary này. | Service contract + ownership + retry/idempotency + permission tests; không cập nhật bảng người khác bằng DTO từ FE.
BE-INT-09 | Rental → Payment | BE2 – Khang | rental_contracts, transactions | Related ownership tasks | In-progress | Không có endpoint integration riêng | Chưa có contract/integration test đầy đủ cho boundary này. | Service contract + ownership + retry/idempotency + permission tests; không cập nhật bảng người khác bằng DTO từ FE.
BE-INT-10 | Events → Audit | BE1 – An + BE2 – Khang | audit_logs, notifications, transactions | Related ownership tasks | In-progress | Không có endpoint integration riêng | Audit JSONB và shipping/order history có code; Notifications event outbox/dedupe chưa có. | Service contract + ownership + retry/idempotency + permission tests; không cập nhật bảng người khác bằng DTO từ FE.
BE-V2-INT-01 | BE1 Payment -> BE2 Wallet credit | BE1 + BE2 | transactions, transaction_attempts, wallets, wallet_ledgers | BE-V2-WAL-HANDLER-01 | In-progress | Không có endpoint integration riêng | Chưa triển khai boundary hoàn chỉnh. | Verified outcome gọi handler đúng một lần; unique ledger key và wallet lock; unknown không credit.
BE-V2-INT-02 | BE2 POD quote/deposit -> BE1 provider callback | BE1 + BE2 | print_requests, print_quotes, print_quote_items, transactions | BE-V2-POD-QUOTE-01, BE-FR-PAY-02-01 | In-progress | Không có endpoint integration riêng | Chưa triển khai boundary hoàn chỉnh. | Deposit success chỉ queue đúng accepted file/spec snapshot; remaining chỉ sau production; callback replay không double lock.
BE-V2-INT-03 | BE1 Refund -> BE2 balance/earning correction | BE1 + BE2 | refund_requests, refund_request_items, transactions, seller_earnings, wallet_ledgers | BE-V2-REF-03 | In-progress | Không có endpoint integration riêng | Chưa triển khai boundary hoàn chỉnh. | Approved amount<=paid-unrefunded; reversal có entry bù; không update/delete ledger.
BE-V2-INT-04 | BE2 Notification -> BE1 order/shipping events | BE1 + BE2 | notifications, physical_orders, order_status_history, shipments | BE-V2-NOTIF-01 | In-progress | Không có endpoint integration riêng | Chưa triển khai boundary hoàn chỉnh. | recipient+dedupe_key unique; event actor/source/time; deep links vẫn authorize server-side.

## Schema Gaps
Schema / policy gaps — cần chốt trước
Giữ backlog tương lai từ file (3). In-progress ở đây có thể nghĩa chưa bắt đầu/chờ schema/policy; không ngầm khẳng định đã code. Không tạo thêm bảng trong lần lập kế hoạch này.
Task ID | Feature | Owner | Status | Gap cụ thể | Hành động cần làm | Priority
BE-FR-AIG-03-02 | Credit operation ledger reserve/consume/restore | BE2 – Khang | In-progress | Có balance và credits_used nhưng không có credit operation ledger/reservation idempotency; phải chốt persistence trước triển khai. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | High
BE-FR-CAS-03-01 | Completed-transaction review eligibility và aggregate rating | BE1 – An | In-progress | reviews v2 chỉ FK Physical order/item; review POD/Rental/Design cần mở rộng source contract. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | High
BE-FR-CHT-01-01 | Context conversation participant/message APIs (Optional) | BE2 – Khang | In-progress | Optional: không có conversations/participants/messages; notifications.conversation_id không có FK và không phải hệ thống chat. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | Medium
BE-FR-DES-01-01 | Internal Design request/review/assignment authorization | BE2 – Khang | In-progress | Schema 48 bảng chưa có design_requests/assignments/quotes/revisions/deliveries. Không thể đánh Done chỉ bằng users/models/transactions. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | Medium
BE-FR-DES-02-01 | Design quote acceptance/deposit và work gate | BE2 – Khang | In-progress | Schema 48 bảng chưa có design_requests/assignments/quotes/revisions/deliveries. Không thể đánh Done chỉ bằng users/models/transactions. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | Medium
BE-FR-DES-03-01 | Preview/revision/allowance/approval + Additional Quote | BE2 – Khang | In-progress | Schema 48 bảng chưa có design_requests/assignments/quotes/revisions/deliveries. Không thể đánh Done chỉ bằng users/models/transactions. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | Medium
BE-FR-DES-03-02 | Additional Design Quote linkage guard | BE2 – Khang | In-progress | Schema 48 bảng chưa có design_requests/assignments/quotes/revisions/deliveries. Không thể đánh Done chỉ bằng users/models/transactions. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | Medium
BE-FR-DES-04-01 | Remaining paid final access + ownership handover transaction | BE2 – Khang | In-progress | Schema 48 bảng chưa có design_requests/assignments/quotes/revisions/deliveries. Không thể đánh Done chỉ bằng users/models/transactions. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | Medium
BE-FR-DIG-01-01 | Current-owner listing và SALE/RENTAL active exclusion | BE2 – Khang | In-progress | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | Low
BE-FR-DIG-02-01 | Digital checkout reservation/concurrent payment protection | BE2 – Khang | In-progress | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | Low
BE-FR-DIG-02-02 | Exclusive sale concurrency/reservation mechanism | BE2 – Khang | In-progress | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | Low
BE-FR-DIG-03-01 | Ownership transfer + access grant exactly once | BE2 – Khang | In-progress | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | Low
BE-FR-DIG-03-02 | Ownership entitlement retry/compensation worker | BE2 – Khang | In-progress | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | Low
BE-FR-DIG-04-01 | Provenance/resale eligibility và digital completion | BE2 – Khang | In-progress | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | Low
BE-FR-DIG-05-01 | Exceptional digital case/ownership compensation guard | BE2 – Khang | In-progress | Schema 48 bảng chưa có Digital SALE offer/order/ownership chain/entitlements. rental_offers chỉ phục vụ Rental; chưa đủ SALE mode. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | Low
BE-FR-LIB-04-01 | Project VIEW/EDIT grant/revoke authorization | BE2 – Khang | In-progress | 48 bảng chưa có project membership/access grants VIEW/EDIT; ownership users không thay thế membership. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | High
BE-FR-MOD-01-01 | Hybrid moderation adapter và revision evidence | BE1 – An | In-progress | products có moderation_reason/status nhưng chưa có moderation job/revision/provider evidence normalized. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | High
BE-FR-MOD-01-02 | Moderation async scan/result correlation | BE1 – An | In-progress | Chưa có revision marker+scan correlation persistence; audit không thay hoàn toàn moderation jobs. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | High
BE-FR-MOD-02-01 | Manual moderation decision transaction | BE1 – An | In-progress | Cần revision concurrency guard/self-review policy; v2 chưa có moderation revision entity. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | High
BE-FR-OPS-01-01 | Versioned config/effective time và historical snapshots | BE1 – An | In-progress | platform_configs chỉ current value/updated_at; chưa có version/effective-time history để đáp ứng đầy đủ task. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | High
BE-FR-POD-05-01 | Production runs/post-processing/defect metadata APIs | BE2 – Khang | In-progress | Có production_status từng item và status history; chưa có print_runs/defects/preview assets/workload normalized. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | High
BE-FR-POD-05-02 | Workload/ETA theo print technology | BE2 – Khang | In-progress | Chưa có schema workload/capacity/technology queues để tính ETA đáng tin cậy. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | High
BE-FR-POD-07-01 | Manufacturing defect/remedy/full refund policy service | BE2 – Khang | In-progress | refund_requests hỗ trợ evidence/refund; repair/reprint/replacement/remedy lifecycle chưa có bảng chuyên biệt. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | High
BE-FR-POD-07-02 | POD defect evidence + remediation transaction | BE2 – Khang | In-progress | Thiếu normalized remediation/run references; không nhét toàn bộ vào audit_logs. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | High
BE-FR-REN-02-01 | Access deadline guard và rental completion hold | BE2 – Khang | In-progress | Rental contract/expiry có bảng, entitlement granularity và income completion cần chốt; seller_earnings physical-only. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | Low
BE-FR-REN-02-02 | Rental expiry/release job và request-time access guard | BE2 – Khang | In-progress | Rental contract/expiry có bảng, entitlement granularity và income completion cần chốt; seller_earnings physical-only. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | Low
BE-FR-SEL-02-01 | Listing update/revision và moderation invalidation | BE1 – An | In-progress | products chưa có revision/optimistic lock marker; chốt revision persistence trước async moderation. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | High
BE-FR-WAL-03-01 | Atomic financial finalization/commission/release | BE2 – Khang | In-progress | seller_earnings hiện chỉ physical_order_id NOT NULL UNIQUE; thu nhập Digital/Rental cần persistence riêng hoặc schema mở rộng. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | High
BE-FR-WAL-03-02 | Financial deadline/release scheduler | BE2 – Khang | In-progress | Scheduler Digital/Rental earnings bị giới hạn seller_earnings physical-only; cần chốt revenue/settlement policy. | Chốt persistence/decision trước khi implement; không phát minh FK/bảng trong danh sách Related Tables. | High